## Implementation Plan MASTER
KRA |  |  | Phase | Activity No. | Activity | Inception USD 2024 - 2025 | Phase 1 USD 2024 - 2029 | Indicative Cost USD '000 2024 - 2033 | Funds Raised | Total Funding Raised USD | Work Plan Funding USD '000 2024 - 2029 |  | 2024 (Actual) | 2025 (Actual) | 2026 | 2027 | 2028 | 2029 | COSPPac
KRA 1 GOVERNANCE, MANAGEMENT AND COORDINATION | [5 empty] | 2340000 | 10150000 | 20310 | 41885% | 8506926.512 | 7884.1015 | #REF! | 1222.6074 | 1268.8137 | 1675.6842 | 1369.8823 | 1253.557 | 1093.557
Output 1.1 WRP governance, management and financing mechanisms established, mandated and equipped to coordinate a Pacific-led, integrated, and sustainable programme
1 |  | Output 1.1 WRP governance, management and financing mechanisms established, mandated and equipped to coordinate a Pacific-led, integrated, and sustainable programme | 11 | 1.1.1 | Establish the PMU, Operational Processes and WRP pooled fund | 550000 | 550000 | 550 | 61605% | 338827.7952 | 338.8278 |  | 0 | 118.4852 | 210.3426 | 10 | 0 | 0 | **ESS??
1 |  | Output 1.1 WRP governance, management and financing mechanisms established, mandated and equipped to coordinate a Pacific-led, integrated, and sustainable programme | 12 | 1.1.2 | Operational Phase of PMU and coordination activities | 300000 | 880000 | 1470 | 176576% | 2595673.8667 | 2595.6739 |  | 1121.2618 | 612.1429 | 451.7438 | 177.7253 | 196.4 | 36.4 | COSPPac - shared travel cost for meetings and coordination
1 |  | Output 1.1 WRP governance, management and financing mechanisms established, mandated and equipped to coordinate a Pacific-led, integrated, and sustainable programme | 13 | 1.1.3 | MERL framework establishment and operationalisation | incl above | incl above | incl above |  | 156434 | 153.434 |  | 0 | 57.948 | 20.486 | 75 | 0 | 0 | COSPPac - overlap in the MERL reporting and indicators, coordination efficiency for sustainability and broader alignment with other pacific and national reporting of the NMHSs
1 |  | Output 1.1 WRP governance, management and financing mechanisms established, mandated and equipped to coordinate a Pacific-led, integrated, and sustainable programme | 14 | 1.1.4 | PMU Staff (Management and Delivery Support roles) | 1490000 | 8720000 | 18290 | 27470% | 5024246.34 | 4404.4213 |  | 101.3456 | 292.022 | 854.5828 | 1052.157 | 1052.157 | 1052.157 | COSPPac - shared resources in GEDSI, MERL, communications
1 |  | Output 1.1 WRP governance, management and financing mechanisms established, mandated and equipped to coordinate a Pacific-led, integrated, and sustainable programme | 16 | 1.1.5 | NMHS Staff to expand capacity to support programme delivery | new | new | new |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | COSPPac - shared resources in GEDSI, overlap in stakeholder engagement, develoment of tools and frameworks for executing staff
1 | Output 1.2 Sustainable hydrometerological financing facility and resource mobilisation approach established and operational | [11 empty] | 0 | 0
1 |  | Output 1.2 Sustainable hydrometerological financing facility and resource mobilisation approach established and operational | 17 | 1.2.1 | Sustainable hydrometeorological financing investment facility | new | new | new |  | 100000 | 100 |  | 0 | 0 | 50 | 50 | 0 | 0
1 | Output 1.3 Transformative GEDSI strategy adopted and integrated across governance, management and partner programming
1 |  | Output 1.3 Transformative GEDSI strategy adopted and integrated across governance, management and partner programming | 81 | 1.3.1 | GEDSI and social safeguards mainstreamed into WRP | incl above | incl above | incl above |  | 291744.51 | 291.7445 |  | 0 | 188.2155 | 88.529 | 5 | 5 | 5 | COSPPac - shared resources in GEDSI, overlap in stakeholder engagement, develoment of tools and frameworks for executing staff
1 |  | Output 1.3 Transformative GEDSI strategy adopted and integrated across governance, management and partner programming | 82 | 1.3.2 | Cultivating a diverse and GEDSI responsive hydrometeorological service and warning institutions | new | new | new |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
KRA 2 PEOPLE CAPABILITY (previously KRA 5 Training and Capacity) | [5 empty] | 330000 | 5480000 | 20640 | 18998% | 3921139.4715 | 2921.1395 | #REF! | 227.937 | 766.3291 | 1159.9354 | 440.414 | 163.262 | 163.262
OP2.1 WMO-designated Pacific Regional Training Centre established and sustainably managed
2 |  | OP2.1 WMO-designated Pacific Regional Training Centre established and sustainably managed | 21 | 2.1.1 | Establish and operate a Regional Training Centre (RTC) | 20000 | 920000 | 920 | 133068% | 1224228.48 | 224.2285 |  | 0 | 139.2285 | 85 | 0 | 0 | 0 | COSPPac - training content to contribute (data mangement CLiDE, tide gauge maintenance, SPC ocean science, climate science)
OP2.2 Inclusive leadership and technical capability strengthening programmes established and delivering ongoing training to industry standards
2 |  | OP2.2 Inclusive leadership and technical capability strengthening programmes established and delivering ongoing training to industry standards | 22 | 2.2.1 | Training of forecasters to BIP-M standard | 110000 | 1350000 | 2700 | 30059% | 811592.75 | 811.5928 |  | 7.195 | 278.4984 | 345.8994 | 180 | 0 | 0
2 |  | OP2.2 Inclusive leadership and technical capability strengthening programmes established and delivering ongoing training to industry standards | 23 | 2.2.2 | Training on specialised forecasting services, and assessment of competencies (e.g. marine, aviation, hydrology/ hydrography) |  |  | 2440 | 4508% | 110000 | 110 |  | 0 | 0 | 30 | 80 | 0 | 0
2 |  | OP2.2 Inclusive leadership and technical capability strengthening programmes established and delivering ongoing training to industry standards | 24 | 2.2.3 | Training of observers, technicians and ICT specialists, and assessment of competencies |  | 480000 | 3240 | 8390% | 271846.277 | 271.8463 |  | 0 | 124.0202 | 147.8261 | 0 | 0 | 0
2 |  | OP2.2 Inclusive leadership and technical capability strengthening programmes established and delivering ongoing training to industry standards | 25 | 2.2.4 | Establish and deliver a Pacific Meteorology Leadership Programme for mid and senior level staff |  | 600000 | 1040 | 12994% | 135133.073 | 135.1331 |  | 0 | 0 | 135.1331 | 0 | 0 | 0
2 |  | OP2.2 Inclusive leadership and technical capability strengthening programmes established and delivering ongoing training to industry standards | 26 | 2.2.5 | Specialised regional workshops and training courses | 200000 | 2130000 | 9330 | 1757% | 163893.6649 | 163.8937 |  | 0 | 0 | 163.8937 | 0 | 0 | 0 | COSPPac - partnership with SPC and SPREP in communication capacity development of NMHSs (forecast communication, climate drivers, social media, channels, talking points). Traditional knowledge training.
2 |  | OP2.2 Inclusive leadership and technical capability strengthening programmes established and delivering ongoing training to industry standards | 27 | 2.2.6 | Provide additional staff for training and capacity development | new | new | new |  | 714374.2267 | 714.3742 |  | 0 | 17.4051 | 207.1832 | 163.262 | 163.262 | 163.262 | COSPPac - capacity development role contribute to PIETR panel and the RTC task team.
OP2.3 Continuous learning and mentoring opportunities provided
2 |  | OP2.3 Continuous learning and mentoring opportunities provided | 28 | 2.3.1 | Twinning programme, ongoing mentoring and communities of practices |  |  | 970 | 50523% | 490071 | 490.071 |  | 220.742 | 207.177 | 45 | 17.152 | 0 | 0 | COSPPac - on the job training NMHSs and LSDs for tide gauge network (GNSS network). Trained to C1 for NMHSs and C2 for SPC technicians, based on Bureau competency framework.
KRA 3 OBSERVATION NETWORK INFRASTRUCTURE (previously KRA 4) | [5 empty] | 3550000 | 9880000 | 89160 | 30666% | 27342206.2978 | 11842.2063 | #REF! | 1906.335 | 1380.5639 | 5264.4573 | 2661.142 | 319.854 | 309.854
Output 3.2 WMO-designated Pacific Regional Instrument Centre established and sustainably managed
3 |  | Output 3.2 WMO-designated Pacific Regional Instrument Centre established and sustainably managed | 31 | 3.2.1 | Establish and operate a Regional Instrument Centre (RIC) |  | 1860000 | 1860 | 56479% | 1050504.3478 | 50.5043 |  | 0 | 0 | 50.5043 | 0 | 0 | 0 | COPPac - SPC barometers sent to fiji met. Sea level calibration is dependent on Bureau metrology lab. Jeff is trying to test if longer calibration time can be acceptable. Lots of import duties.
Output 3.1 Interoperable, affordable and resilient observation network progressively remediated, expanded and sustained
3 |  | Output 3.1 Interoperable, affordable and resilient observation network progressively remediated, expanded and sustained | 32 | 3.1.1 | Implement observation network plans, asset management, standardised infrastructure, data management and maintenance practices | 1050000 | 1000000 | 1000 | 91670% | 916699 | 916.699 |  | 0.29 | 354.162 | 177.247 | 355 | 20 | 10 | COSPPac - $120k asset managemen system for sea leve assets from asset miantenance perspective only. Metadata needs to be consistent in CLiDE. Contributed to PMC paper to identify priority stations for high quality surface network stations. Pacific sea level stations are captured in the Bureau asset mangaement plan for sea level. SPC may not have costs, as Bureau procurement. COSPPac will work with NIWA and WRP to standard maintenance regimes.
|  | Output 3.1 Interoperable, affordable and resilient observation network progressively remediated, expanded and sustained | [17 empty] | Output 2. AWS and Manual Station Observation Network Sustainability Planning and Refurbishment (Network Plan)
3 |  | Output 3.1 Interoperable, affordable and resilient observation network progressively remediated, expanded and sustained | 33 | 3.1.2 | Provide asset management and maintenance staff to expand capacity (e.g. SPREP, SPC, NMHS) |  | 220000 | 470 | 229336% | 1077879.95 | 1077.88 |  | 0 | 45.0559 | 163.262 | 289.854 | 289.854 | 289.854 | COSPPac - funding staff in BOM (2 FTE), SPC (2 FTE). SPC coordinates 6 monthly maintenance plan for the sea level. Bureau purchases directly any consumables for NMHSs and Land survey departments for repairs and maintenance purposes (e.g. tools, safety equipment etc).
3 |  | Output 3.1 Interoperable, affordable and resilient observation network progressively remediated, expanded and sustained | 71 | 3.1.3 | Revitalise and expand automatic and manual weather stations |  | 2000000 | 11340 | 13095% | 1484971 | 1484.971 |  | 0 | 8.975 | 940.769 | 535.227 | 0 | 0
3 |  | Output 3.1 Interoperable, affordable and resilient observation network progressively remediated, expanded and sustained | 72 | 3.1.4 | Revitalise and expand river gauges and rain gauges |  |  | 8050 | 0% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | COSPPac - no river guages data stored in CLiDE, but rain is and in theory can ingest other rainfall data from other pacific agencies.
3 |  | Output 3.1 Interoperable, affordable and resilient observation network progressively remediated, expanded and sustained | 73 | 3.1.5 | Establish weather watch radars | 2500000 | 2500000 | 11650 | 195812% | 22812152 | 8312.152 |  | 1906.045 | 972.371 | 3932.675 | 1481.061 | 10 | 10 | COSPPac - no radar data stored in CLiDE
3 |  | Output 3.1 Interoperable, affordable and resilient observation network progressively remediated, expanded and sustained | 74 | 3.1.6 | Revitalise and expand wave buoys |  | 2300000 | 19750 | 0% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | COSPPac - no formal deliverables other than SPC technical resources funded
3 |  | Output 3.1 Interoperable, affordable and resilient observation network progressively remediated, expanded and sustained | 75 | 3.1.7 | Revitalise and expand tide gauges |  |  | 13930 | 0% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | COSPPac - 14 guages maintains, SPC planning to deploy 2 more. Tokelau tide gauges.
3 |  | Output 3.1 Interoperable, affordable and resilient observation network progressively remediated, expanded and sustained | 76 | 3.1.8 | Revitalise and expand Meteorological balloon launching systems |  |  | 20520 | 0% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | COSPPac - ability to store in CLiDE, but not done for a long time. There historical data in various places not archived in CLiDE. Unclear where the Fiji stores/archives and sends this data.
3 |  | Output 3.1 Interoperable, affordable and resilient observation network progressively remediated, expanded and sustained | 77 | 3.1.9 | Data capture from aircraft observation using the aircraft meteorological data relay system |  |  | 590 | 0% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | COSPPac - no AMDAR data stored in CLiDE
KRA 4 FORECAST AND WARNING PRODUCTION (previously KRA 2) | [5 empty] | 300000 | 9000000 | 45760 | 12500% | 5720031.2717 | 4592.941 | #REF! | 386.3489 | 473.4037 | 2316.3814 | 1076.807 | 170 | 170
Output 4.1 An integrated Pacific forecasting platform established and operating sustainably to global standards
4 |  | Output 4.1 An integrated Pacific forecasting platform established and operating sustainably to global standards | 41 | 4.1.1 | Develop an Integrated Forecasting Platform and strengthen RSMCs (incl WIS, CAP) | 100000 | 1000000 | 18220 | 9809% | 1787191.4617 | 1757.1915 |  | 55.2349 | 0 | 901.9565 | 800 | 0 | 0 | **check where NZ met obs are coming from. COSPPac - CLiDE database to automatically transfer data to WIS2 (but only hourly obs). Maybe a small subset of AWS not feeding into CLiDE yet (e.g. aviation)
1 | OP4.2 Pacific forecasting capacity expanded and maintained
4 |  | OP4.2 Pacific forecasting capacity expanded and maintained | 42 | 4.2.1 | Strengthen aviation forecasting |  |  | 1980 | 1515% | 30000 | 30 |  | 0 | 0 | 30 | 0 | 0 | 0 | COSPPac- CLiDE have the ability to support METAR and SPECI. Some met services use it to enter manual data and produce the message automatically and provides first pass QC. This is beneficial before going into WIS2.
4 |  | OP4.2 Pacific forecasting capacity expanded and maintained | 43 | 4.2.2 | Strengthen public forecasting |  |  | 6930 | 8624% | 597647 | 597.647 |  | 331.114 | 159.336 | 107.197 | 0 | 0 | 0
4 |  | OP4.2 Pacific forecasting capacity expanded and maintained | 44 | 4.2.3 | Strengthen marine forecasting |  |  | incl above |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | COSPPac - expanding fixed marine obs (ingesting ocean buoys and tide guages). Some tide gauge data but issues with ingesting near real-time currently and working to resolve with the tidal centre.
4 |  | OP4.2 Pacific forecasting capacity expanded and maintained | 45 | 4.2.4 | Strengthen coastal inundation forecasting | 200000 | 4900000 | 12250 | 9836% | 1204926.96 | 1204.927 |  | 0 | 300.8046 | 797.3153 | 106.807 | 0 | 0 | COSPPac - SPC oceans portal has weather usages with 7 days forecast (based on bureau dataset), tide predictions from Bureau and calendar production and distribution. Conversations of potential transition to SPC on tide prediction and Andy Taylor. Tokelau 3 tide gauges.
4 |  | OP4.2 Pacific forecasting capacity expanded and maintained | 46 | 4.2.5 | Strengthen hydrological services and riverine flood forecasting |  | incl above | incl above |  | 1190064 | 92.9737 |  | 0 | 0 | 92.9737 | 0 | 0 | 0 | COSPPac - rainfall data from NMHSs going into CLiDE and there is an API. It would be valuable to ingest historical data as data rescue activity. No ability to ingest water level station data. Need to think how to better safeguard CLiDE.
4 |  | OP4.2 Pacific forecasting capacity expanded and maintained | 47 | 4.2.6 | Provide additional ICT and other technical staff to expand capacity | - | 3100000 | 6380 | 14266% | 910201.85 | 910.2018 |  | 0 | 13.2631 | 386.9388 | 170 | 170 | 170 | COSPPac - funding SPREP IT staff (1FTE), SPC (1FTE), NIWA and Bureau to build ICT capability within NMHSs. There is also allocated additional funding for ICT services focussed on climate and ocean products and services (not directly met).
KRA 5 COMMUNICATION AND DELIVERY OF FORECASTS AND WARNINGS TO END USERS (previously KRA 3) | [5 empty] | 860000 | 2560000 | 9520 | 6387% | 608061.7281 | 608.0617 | #REF! | 0 | 39.3247 | 335.475 | 70 | 0 | 163.262
Output 5.1 Pacific capacity and collaborative approaches to deliver locally-relevant, impact-based, inclusive and accessible forecasts and warnings for end users strengthened and sustained
5 |  | Output 5.1 Pacific capacity and collaborative approaches to deliver locally-relevant, impact-based, inclusive and accessible forecasts and warnings for end users strengthened and sustained | 51 | 5.1.1 | Planning for delivery of impact-based messages and warnings to end-users, considering persons with disabilities and vulnerable groups. | 710000 | 660000 | 660 | 10606% | 70000.0009 | 70 |  | 0 | 0 | 0 | 70 | 0 | 0 | COSPPac - climate time scale impact based forecasting for climate sensitive sectors. UNEP - additionally funding for 2 countries further focussed at national level (cook is, tuvalu)
5 |  | Output 5.1 Pacific capacity and collaborative approaches to deliver locally-relevant, impact-based, inclusive and accessible forecasts and warnings for end users strengthened and sustained | 52 | 5.1.2 | Prepare impact-based, location specific warnings, based on assessments and modelling, and incorporating traditional knowledge |  | 1000000 | 3930 | 0% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | COSPPac - collating traditional knowedge and data rescue mangement and a database and procedures in SPREP. Most of the data is weather TK. Funding SPREP TK advisor who runs workshops in country assisting the NMHSs to collect data. SPREP IT funded to maintain database (built by Bureau and transitioned)
5 |  | Output 5.1 Pacific capacity and collaborative approaches to deliver locally-relevant, impact-based, inclusive and accessible forecasts and warnings for end users strengthened and sustained | 53 | 5.1.3 | Deliver and continuously review impact based messaging including translation into local languages |  | 400000 | 4430 | 0% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | COSPPac - support NMHSs for translation framework of climate bulletins into local languages where possible.
5 |  | Output 5.1 Pacific capacity and collaborative approaches to deliver locally-relevant, impact-based, inclusive and accessible forecasts and warnings for end users strengthened and sustained | 54 | 5.1.4 | Inclusive Community Education and Information-Exchange collectives | 50000 | incl above | incl above |  | 194543.8967 | 194.5439 |  | 0 | 0 | 194.5439 | 0 | 0 | 0 | COSPPac - supports NCOF. Bureau, SPC, SPREP funded staff is supporting NMHSs promote climate bulletins/products and services at a community level. COSPPac also actively developing that two-way network, referred to as knowledge brokering. Significant improvement needed in this space. Questions often arise from comunity on weather servies which can't be addressed by COSPPac. e.g. National climate outlook forum along side a National Weather outlook forum.
5 |  | Output 5.1 Pacific capacity and collaborative approaches to deliver locally-relevant, impact-based, inclusive and accessible forecasts and warnings for end users strengthened and sustained | 55 | 5.1.5 | Develop innovative approaches for dissemination of forecasts and warnings to end-users (e.g. cell broadcasting, mobile apps, social media) |  | incl above | incl above |  | 22530.7 | 22.5307 |  | 0 | 22.5307 | 0 | 0 | 0 | 0 | COSPPac - supports NMHSs in communicating via social media, radio, and traditional media. SPC has a tide's app for the region with national level info and tide predictions at national level. It has sunrise, sunset etc.
5 |  | Output 5.1 Pacific capacity and collaborative approaches to deliver locally-relevant, impact-based, inclusive and accessible forecasts and warnings for end users strengthened and sustained | 56 | 5.1.6 | Install communication internet access equipment and operational costs | 100000 | 500000 | 500 | 31545% | 157725.1304 | 157.7251 |  | 0 | 16.794 | 140.9311 | 0 | 0 | 0 | COSPPac - Flexi-fund is contributing to this with comms/starlink. Celine? Used to pay tuvalu internet services. Gap infrastructure to connect to government communication link, which may negate the need for ongoing satellite communication cost. (WRP could contribute??)
5 |  | Output 5.1 Pacific capacity and collaborative approaches to deliver locally-relevant, impact-based, inclusive and accessible forecasts and warnings for end users strengthened and sustained | 57 | 5.1.7 | Provide additional staff for warning communication and engagement to expand capacity | new | new | new |  | 163262 | 163.262 |  | 0 | 0 | 0 | 0 | 0 | 163.262 | COSPPac - approx. 10 officers in NMHSs for science communications 2 years $1.2Mill and flexi-fund may also contribute. They develop communication plans and map stakeholders, to tailor and improve operatinoal products to community. Implement engagement activities with the community. These roles may be supporting weather information delivery.
KRA6 RISK INFORMATION AND PREPAREDNESS (new) | [5 empty] | 0 | 0 | TBD | #VALUE! | 0 | TBD |  | TBD | TBD | TBD | TBD | TBD | TBD
OP6.1 Standardised, interoperable and inclusive multi-hazard data produced, stored and shared with resilience partners
6 |  | OP6.1 Standardised, interoperable and inclusive multi-hazard data produced, stored and shared with resilience partners |  |  | TBD by decadal investment plan to align with EW4All |  |  |  |  | 0
OP6.2 Roles and responsibilities established for coordinating, updating, and reviewing hazard inputs into risk knowledge products, preparedness and response plans and procedures
6 |  | OP6.2 Roles and responsibilities established for coordinating, updating, and reviewing hazard inputs into risk knowledge products, preparedness and response plans and procedures |  |  | TBD by decadal investment plan to align with EW4All |  |  |  |  | 0
CONTINGENCY AND OTHER | [5 empty] | 330000 | 3000000 | 5560 | 10999% | 611540.85 | 611.5408 | #REF! | 0 | 11.5409 | 150 | 150 | 150 | 150
0 |  | Contingency and Other | 00 |  | Contingency and Other |  |  |  |  | 611540.85 | 611.5408 |  | 0 | 11.5409 | 150 | 150 | 150 | 150
[5 empty] | GRAND TOTAL (excl. SPREP program fees) | 7710000 | 40070000 | 190950 |  | 46709906.1311 | 28459.9909 | #REF! | 3743.2283 | 3939.976 | 10901.9333 | 5768.2453 | 2056.673 | 2049.935
Note on G14: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Increased $100k as CAP training moved from KRA3 to 5
Note on H14: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Total increased CAP training $100k moved from KRA3 to KRA5
Note on I14: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Total increased by CAP training $200k from KRA2 to 5
Note on G22: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Short term capacity development workshop $100k CAP training - $100k moved from KRA3 to KRA5
Note on H22: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: CAP training - $100k moved from KRA3 to KRA5
Note on I22: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: CAP training - $200k moved from KRA3 to KRA5 Merged with QMS training 980k
Note on H26: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Total reduced by Moved ICT infrastructure with cybersecurity to KRA4 $700k
Note on I26: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Reduced by ICT infrastructure, cybersecurity, forecaster workstations to KRA4 $7.22M
Note on G30: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: $1M network plans 50k regional principles and standards
Note on H32: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: cost of SPC staff only. Asset management and maintenance staff not budgeted originally.
Note on I32: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: cost of SPC staff only. Asset management and maintenance staff not budgeted originally.
Note on I33: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Reduced by $1M and move to network plans above
Note on F36: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Check with SPC if they prefer this terminology of ocean monitoring rather than be specific to wave buoys, as there is a lot of technology options
Note on H40: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Added ICT infrastructure with cybersecurity from KRA4 $700k
Note on I40: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Added ICT infrastructure and cybersecurity and forecaster workstations $7.22M
Note on H42: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: IFP - $100k WIS - $200k High accessibility ICT infrastructure with cybersecurity $700k from KRA4
Note on I42: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: IFP $11M ICT infrastructure with cybersecurity, standalone forecaster work stations and technical workshops $7.22M transferred from KRA4
Note on G50: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Moved CAP training $100k to KRA2 people capability, so total reduced
Note on H50: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Moved CAP training $100k to KRA5, so total reduced by $100k
Note on I50: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Moved CAP training $200k to KRA5, so total reduced by $200k
Note on G52: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: National workshops 500k Regional workshop 160k Engagement strategy vulnerable groups 50k
Note on H52: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: National workshops 500k Regional workshop 160k
Note on I52: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: National workshops 500k Regional workshop 160k
Note on I54: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: combined delivery of impact based message $3.93M review of end user response $500k
Note on F56: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: tools, channels? instead of approaches

## Project Register (hidden)
KRA | Output | Activity No. | Activity Ref | Activity | Project Title | Phase | Task | Concept No. | Project No. | Project Type | Executing Agency | Pacific-led (ie. decisions made by the Pacific, for the Pacific) institution (Yes/No) | Pacific institution type (regional, national, sub-national) | PMU Lead | Project Manager Executing Agency | Procurement/ Recruitment | Actions | May 2026 DFAT spend | Beneficiaries | Funding Modality | Total Allocated Funding USD | Co-funder | Co-Funding & In-Kind USD | Co-funding estimate basis | WRP Funding Source | WRP Funding Allocated USD | 2024 Budget | 2025 Budget | 2024 | 2025 | 2026 Budget | 2027 Budget | 2028 Budget | 2029 Budget | 2030 Budget | 2031 Budget | 2032 Budget | 2033 Budget | 2024 Actual | Jan-June 2025 Actual | 2025 Actual | Actual Spend USD | Committed Spend USD | % Spend WRP funding | No. Risks (sig/severe) | No. Adaptions / Changes | Actions Identified (Y/N) | No. Actions Identified | No. Action Completed | % Actions Completed | Sustainability Actions % Implemented | GEDSI Actions % Implemented | ESS Actions % Implemented | MERL Table Reported (Y/N) | No. Pacific Assets Registered | Progress | Progress Sep25 | % Progress | % Progress Sep25 | Status | Status Sep25 | Comment Jan25 (financial variance 2025) | Comment Sep25
1 | Output 1.1 WRP governance, management and financing mechanisms established, mandated and equipped to coordinate a Pacific-led, integrated, and sustainable programme | 1.1.2 | 12 | Operational Phase of PMU and coordination activities | NZ Met Services Technical support/ Governance/ Programme Management | 12 |  |  |  | Major | NZ Met Services | [7 empty] | All | Other Support | 1008186 |  |  |  | MFAT-NZ | 1008186 |  |  | 694231 | 193639 | 120316 | [7 empty] | 694231 | 111806.02 | 193639 | 887870 |  | 88.07% | 1 | 1 | Y | 5 | 2 | 40% | 30% | 50% | 100% | Y | 1 | 4 Implementation In Progress | 4 Implementation In Progress | 64% | 64% | Green | Green | Effort less than forecasted | -
1 | Output 1.1 WRP governance, management and financing mechanisms established, mandated and equipped to coordinate a Pacific-led, integrated, and sustainable programme | 1.1.2 | 12 | Operational Phase of PMU and coordination activities | ESNZ Project technical support, governance, reporting, adaptive management, communications | 12 |  |  |  | Standard | ESNZ | [7 empty] | All | Other Support | 464653 |  |  |  | MFAT-NZ | 464653 |  |  | 160871 | 260376 | 30000 | 13406 | [6 empty] | 160871 | 163132 | 260111 | 420982 |  | 90.6% | 1 | 1 | Y | 10 |  | 0% |  |  |  | Y | 1 | 4 Implementation In Progress | 4 Implementation In Progress | 90.6% | 90.6% | Green | Green | Effort greater than forecasted
1 | Output 1.1 WRP governance, management and financing mechanisms established, mandated and equipped to coordinate a Pacific-led, integrated, and sustainable programme | 1.1.1 | 11 | Establish the PMU, Operational Processes and WRP pooled fund | Revised WRP Investment plan and implementation plan aligned with EW4ALL | 11 | 05 |  | 1105 | Standard | WRP |  |  | Ofa |  | 2025 | [1/8/25] Awaiting tender to close mid August |  | All | Ring-Fenced | 54069.5652 |  |  |  | MFAT- SPREP | 54069.5652 |  |  |  |  | 54069.5652 | [10 empty] | 0 |  | 0% | 1 |  | N |  |  | #DIV/0! | [5 empty] | 3 Agreement | 3 Agreement | 10% | 10% | Green | Green | Procurement deferred to 2026. | -
4 | Output 4.1 An integrated Pacific forecasting platform established and operating sustainably to global standards | 4.1.1 | 41 | Develop an Integrated Forecasting Platform and strengthen RSMCs (incl WIS, CAP) | Initial consultation and workshop on an integrated forecast platform and other workshops | 41 | 07 |  | 4107 | Standard | WRP |  |  | Salesa |  |  |  |  | All | Ring-Fenced | 55234.94 |  |  |  | UK WISER | 55234.94 |  |  | 55234.94 | [9 empty] | 55234.94 |  |  | 55234.94 |  | 100% | 1 |  |  |  |  | #DIV/0! | [5 empty] | 5 Completion Evaluation | 5 Completion Evaluation | 100% | 100% | Green | Green | . | Workshop held in Melbourne from 11-14 June. Closure Report submitted.
1 | Output 1.3 Transformative GEDSI strategy adopted and integrated across governance, management and partner programming | 1.3.1 | 81 | GEDSI and social safeguards mainstreamed into WRP | Operational budget for mainstreaming GEDSI into WRP implementation | 81 | 01 |  | 8101 | Standard | WRP |  |  | Ofa |  |  |  |  | All | Ring-Fenced | 190344.51 |  |  |  | UK WISER | 190344.51 |  | #REF! |  | 101815.47 | 88529.04 | [8 empty] | 75651.12 | 101815.47 | 101815.47 |  | 53.49% | 1 |  |  |  |  | #DIV/0! | [5 empty] | 4 Implementation In Progress | 4 Implementation In Progress | 75% | 75% | Green | Green | Delayed implementation. Budget tranferred to 2026. | GEDSI strategy prepared and tabled for SC approval.
1 | Output 1.3 Transformative GEDSI strategy adopted and integrated across governance, management and partner programming | 1.3.1 | 81 | GEDSI and social safeguards mainstreamed into WRP | Operational budget for mainstreaming GEDSI into WRP implementation | 81 |  |  |  | Standard | WRP |  |  | Ofa |  |  |  | 0 | All | Ring-Fenced | 15000 |  |  |  | DFAT | 15000 | [5 empty] | 5000 | 5000 | 5000 | [7 empty] | 0 |  | 0% | 1 |  |  |  |  | #DIV/0! | [5 empty] | Not Started |  | 0% |  | - |  | .
5 | Output 5.1 Pacific capacity and collaborative approaches to deliver locally-relevant, impact-based, inclusive and accessible forecasts and warnings for end users strengthened and sustained | 5.1.4 | 54 | Inclusive Community Education and Information-Exchange collectives | Translation and printing of COPE books | 54 | 01 |  | 5401 | Standard | WRP |  |  | Terry |  | 2025 | [1/8/25] Get quotes from Tokelau and Niue for translation of COPE Booklets, for WRP to procure |  | Tokelau, Niue | Ring-Fenced | 107587.375 |  |  |  | UK WISER | 107587.375 |  |  |  |  | 107587.375 | [10 empty] | 0 |  | 0% | 1 |  |  |  |  | #DIV/0! | [5 empty] | 3 Agreement | 3 Agreement | 30% | 30% | Amber | Amber | Deferred to 2026 after PMU staff recruited | Progressing procurement. Delays against WISER project timeline.
2 | OP2.2 Inclusive leadership and technical capability strengthening programmes established and delivering ongoing training to industry standards | 2.2.5 | 26 | Specialised regional workshops and training courses | Installation and training in the common alerting protocol and Regional workshop | 26 | 01 |  | 2601 | Standard | WRP |  |  | Terry |  | 2025 | [1/8/25] 'Ofa to chase WMO for cost for this workshop |  | All | Ring-Fenced | 109824.0996 |  |  |  | UK WISER | 109824.0996 |  |  |  |  | 109824.0996 | [10 empty] | 0 |  | 0% | 1 |  |  |  |  | #DIV/0! | [5 empty] | Not Started | Not Started | 0% | 0% | - | - | Training deferred to 2026. | -
4 | Output 4.1 An integrated Pacific forecasting platform established and operating sustainably to global standards | 4.1.1 | 41 | Develop an Integrated Forecasting Platform and strengthen RSMCs (incl WIS, CAP) | Peer review of IFP | 41 | 01 | 2501 | 4101 | Standard | BOM, UK Met Office |  |  | Ofa |  | 2025 | [1/8/25] Honsol to discuss with procurement whether to use LOA or standard contract with Bureau. Salesa to support discussions with SPREP legal on non-binding language. Concept Note finalised and work is progressing. | 0 | All | Ring-Fenced | 30000 |  |  |  | DFAT | 30000 |  |  |  |  | 30000 | [10 empty] | 0 |  | 0% | 0 |  |  |  |  | #DIV/0! | [5 empty] | 5 Completion Evaluation | 4 Implementation In Progress | 100% | 20% | Green | Green | Invoicing in 2026, though work completed in 2025. | Progress as of Sep 2025 is report complete being tabled to steering committee.
4 | Output 4.1 An integrated Pacific forecasting platform established and operating sustainably to global standards | 4.1.1 | 41 | Develop an Integrated Forecasting Platform and strengthen RSMCs (incl WIS, CAP) | IFP Design and ICT Architecture | 41 | 08 | 2602 | 4108 | Standard | BOM, NZ MetServices |  |  | Ofa |  | 2025 | [1/8/25] Paused until outcome of peer review in Sept. | 0 | All | Ring-Fenced | 75000 |  |  |  | DFAT | 75000 |  |  |  |  | 75000 | [10 empty] | 0 |  | 0% | [5 empty] | #DIV/0! | [5 empty] | Not Started | Not Started | 0% | 0% | - | - | Deferred to 2026. Concept note and project team formation took time. | Updated work plan cost based on IFP peer review estimates for architecture design, subject to SC approval.
4 | Output 4.1 An integrated Pacific forecasting platform established and operating sustainably to global standards | 4.1.1 | 41 | Develop an Integrated Forecasting Platform and strengthen RSMCs (incl WIS, CAP) | IFP Implementation and Roll Out - Progressively by country | 41 | 04 | 2602 | 4104 | Major | BOM, NZ MetServices |  |  | Ofa |  | 2026 |  |  | All | Ring-Fenced | 1550000 |  |  |  | DFAT | 1550000 |  |  |  |  | 750000 | 800000 | [9 empty] | 0 |  | 0% | [5 empty] | #DIV/0! | [5 empty] | Not Started | Not Started | 0% | 0% | - | - | . | Upated work plan cost based on IFP peer review estimates for Phase 1 and 2. Subject to SC approval. Need to look for co-funding for Phase 3. Most likely from the World bank and UNEP/UNDP SOFF related work on data exchange.
1 | Output 1.1 WRP governance, management and financing mechanisms established, mandated and equipped to coordinate a Pacific-led, integrated, and sustainable programme | 1.1.3 | 13 | MERL framework establishment and operationalisation | Regional M&E Workshop | 13 | 03 |  | 1303 | Standard | WRP |  |  | Ofa |  |  |  |  | All | Ring-Fenced | 0 |  |  |  | MFAT- SPREP | 0 | [15 empty] | 0 |  | - | [5 empty] | #DIV/0! | [5 empty] | Paused | Paused | 0% | 0% | - | - | . | Funding reallocated to Investment Plan review budget, as there may not be a need for this workshop.
4 | OP4.2 Pacific forecasting capacity expanded and maintained | 4.2.6 | 47 | Provide additional ICT and other technical staff to expand capacity | Secondment of ICT Specialist to progress IFP, KRA 2 and 3. | 47 | 09 | 2509 | 4709 | Standard | BOM |  |  | Terry |  | 2025 | [1/8/25] Paused until outcome of peer review in Sept. If proceed will need LOA with BOM | 108469.375 | All | Ring-Fenced | 216938.75 |  |  |  | DFAT | 216938.75 |  |  |  |  | 216938.75 | [10 empty] | 0 |  | 0% | 0 |  |  |  |  | #DIV/0! | [5 empty] | 4 Implementation In Progress | Paused | 15% | 0% | Green | - | Invoicing in 2026, specialist engaged in 2025. | Awaiting SC direction.
1 | Output 1.1 WRP governance, management and financing mechanisms established, mandated and equipped to coordinate a Pacific-led, integrated, and sustainable programme | 1.1.2 | 12 | Operational Phase of PMU and coordination activities | PMU Travel and Workshops | 12 | 02 |  | 1202 | Standard | WRP |  |  | Honsol |  |  |  |  | All | Ring-Fenced | 84877.6207 |  |  |  | MFAT- SPREP | 84877.6207 |  |  | 27584.2 | 27293.42 | 30000.0007 | [7 empty] | 27584.2 | 28422.68 | 27293.42 | 54877.62 |  | 64.65% | [5 empty] | #DIV/0! | [5 empty] | 4 Implementation In Progress | 4 Implementation In Progress | 30% | 30% | Green | Green | . | -
1 | Output 1.1 WRP governance, management and financing mechanisms established, mandated and equipped to coordinate a Pacific-led, integrated, and sustainable programme | 1.1.1 | 11 | Establish the PMU, Operational Processes and WRP pooled fund | Branding and advertising | 11 | 01 |  | 1101 | Standard | WRP |  |  | Ofa |  |  |  |  | All | Ring-Fenced | 34758.23 |  |  |  | MFAT- SPREP | 34758.23 |  |  |  | 4758.23 | 20000 | 10000 | [8 empty] | 4758.23 | 4758.23 |  | 13.69% | [5 empty] | #DIV/0! | [5 empty] | Not Started | Not Started | 0% | 0% | - | - | Delayed recruitment of Communication Officer. Funds deferred to 2026 and 2027. | -
1 | Output 1.1 WRP governance, management and financing mechanisms established, mandated and equipped to coordinate a Pacific-led, integrated, and sustainable programme | 1.1.2 | 12 | Operational Phase of PMU and coordination activities | Hosting of WRP Steering and Liaison Platform | 12 | 01 |  | 1201 | Standard | WRP |  |  | Ofa |  |  |  |  | All | Ring-Fenced | 180264.4661 |  |  |  | MFAT- SPREP | 180264.4661 |  |  |  | 96456.64 | 83807.8261 | [8 empty] | 44101.86 | 96456.64 | 96456.64 |  | 53.51% | [5 empty] | #DIV/0! | [5 empty] | 4 Implementation In Progress | 4 Implementation In Progress | 20% | 20% | Green | Green | . | -
3 | Output 3.1 Interoperable, affordable and resilient observation network progressively remediated, expanded and sustained | 3.1.1 | 32 | Implement observation network plans, asset management, standardised infrastructure, data management and maintenance practices | Upper Air network plan | 32 | 06 |  | 3206 | Standard | WRP |  |  | Marica |  | 2025 | [1/8/25] 'Ofa to confirm with NZ will they be developing this | 0 | All | Ring-Fenced | 10000 |  |  |  | DFAT | 10000 | [5 empty] | 10000 | [9 empty] | 0 |  | 0% | [5 empty] | #DIV/0! | [5 empty] | Not Started | Not Started | 0% | 0% | - | - | . | Need to identify which organisation will do this work.
3 | Output 3.1 Interoperable, affordable and resilient observation network progressively remediated, expanded and sustained | 3.1.1 | 32 | Implement observation network plans, asset management, standardised infrastructure, data management and maintenance practices | Asset Management Information System Implementation (software & training) | 32 | 04 |  | 3204 | Major | WRP |  |  | Marica |  | 2025 | [1/8/25] Tender specifications from BoM needs to be reviewed. Need to discuss if BoM does procurement or SPREP? | 37500 | All | Ring-Fenced | 230000 |  |  |  | DFAT | 230000 |  |  |  |  | 75000 | 125000 | 20000 | 10000 | [7 empty] | 0 |  | 0% | [5 empty] | #DIV/0! | [5 empty] | 1 Concept | 1 Concept | 2% | 2% | Green | Green | . | Concept Note drafted and provided to World Bank to TA for this work. In discussion with COSPPac to collaborate with their procurement of an asset management system which is in their work scope also.
1 | Output 1.1 WRP governance, management and financing mechanisms established, mandated and equipped to coordinate a Pacific-led, integrated, and sustainable programme | 1.1.3 | 13 | MERL framework establishment and operationalisation | MERL and Sustainability Framework | 13 | 02 |  | 1302 | Standard | MFAT - MERL |  |  | Ofa |  |  |  |  | All | Other Support | 81434 |  | 3000 |  | MFAT-NZ | 78434 |  |  |  | 57948 | 20486 | [8 empty] | 28905 | 57948 | 57948 |  | 73.88% | [5 empty] | #DIV/0! | [5 empty] | 4 Implementation In Progress | 4 Implementation In Progress | 60% | 60% | Green | Green | . | Progress as of Sep 2025 is framework complete being tabled to steering committee.
1 | Output 1.1 WRP governance, management and financing mechanisms established, mandated and equipped to coordinate a Pacific-led, integrated, and sustainable programme | 1.1.2 | 12 | Operational Phase of PMU and coordination activities | Staff start up cost (IT, furniture) and communicating & promotion | 12 | 03 |  | 1203 | Standard | WRP |  |  | Honsol |  |  |  |  | - | Ring-Fenced | 16575.84 |  |  |  | MFAT- SPREP | 16575.84 |  |  | 1508.18 | 15067.66 | [8 empty] | 1508.18 | 2915.16 | 15067.66 | 16575.84 |  | 100% | [5 empty] | #DIV/0! | [5 empty] | 4 Implementation In Progress | 4 Implementation In Progress | 20% | 20% | Green | Green | Actual cost higher than budgeted. | -
3 | Output 3.1 Interoperable, affordable and resilient observation network progressively remediated, expanded and sustained | 3.1.5 | 73 | Establish weather watch radars | Samoa Radar | 73 | 07 | 2510 | 7307 | Major | WRP, BOM, NZMetServices |  |  | Marica |  | 2025 | [1/8/25] 'Ofa's chase NZMet for Concept Note and cost to Project Manage Radar and for copy of Solomon specfications to review. [13/8/25] Start routing process for NZ Met, need to provide Why go direct. Need concept note and cost. Due 16 Sept for Sept 30 Procurement meeting. Awaiting Pacific Radar Strategy managed by NZMFAT or an asset policy that requires standardise supply of radars. Planning to tender and establish radar preferred supplier list. | 1687500 | Samoa | Ring-Fenced | 3375000 |  |  |  | DFAT | 3375000 |  |  |  |  | 1995000 | 1360000 | 10000 | 10000 | [7 empty] | 0 |  | 0% | [5 empty] | #DIV/0! | [5 empty] | 3 Agreement | 3 Agreement | 10% | 10% | Green | Green | . | Preparing EOI procurement to be released to establish ongoing preferred supplier contracts. Progress as of Sep 2025 is EOI released.
3 | Output 3.1 Interoperable, affordable and resilient observation network progressively remediated, expanded and sustained | 3.1.5 | 73 | Establish weather watch radars | PNG Radar |  |  |  |  | External | BOM | [7 empty] | PNG |  | 2000000 | DFAT | 2000000 |  |  | 0 | [15 empty] | 0 |  | - | [5 empty] | #DIV/0! | [7 empty] | - | - | - | - | . | Site selection in progress. DFAT Port Morsby in principle supportive of regional standardised procurement approach through Samoa radar.
3 | Output 3.1 Interoperable, affordable and resilient observation network progressively remediated, expanded and sustained | 3.1.5 | 73 | Establish weather watch radars | 5 Atolls Radars |  |  |  |  | External | UNEP/ICAO | [9 empty] | 12500000 | UNEP | 12500000 |  |  | 0 | [15 empty] | 0 |  | - | [5 empty] | #DIV/0! | [7 empty] | - | - | - | - | . | -
3 | Output 3.1 Interoperable, affordable and resilient observation network progressively remediated, expanded and sustained | 3.1.5 | 73 | Establish weather watch radars | FSM Radar | 73 | 02 |  | 7302 | Major | WRP | [7 empty] | FSM |  | 0 |  |  |  | DFAT | 0 | [15 empty] | 0 |  | - | [5 empty] | #DIV/0! | [5 empty] | Not Started | Not Started | 0% | 0% | - | - | . | -
3 | Output 3.1 Interoperable, affordable and resilient observation network progressively remediated, expanded and sustained | 3.1.5 | 73 | Establish weather watch radars | Kiribati Radar | 73 | 03 |  | 7303 | Major | WRP | [7 empty] | Kiribati |  | 0 |  |  |  | DFAT | 0 | [15 empty] | 0 |  | - | [5 empty] | #DIV/0! | [5 empty] | Not Started | Not Started | 0% | 0% | - | - | . | -
2 | OP2.1 WMO-designated Pacific Regional Training Centre established and sustainably managed | 2.1.1 | 21 | Establish and operate a Regional Training Centre (RTC) | Regional workshop to advance discussions for the establishment of the Regional Training Centre | 21 | 02 |  | 2102 | Standard | WRP |  |  | Ofa |  |  |  |  | All | Ring-Fenced | 64228.48 |  |  |  | MFAT- SPREP | 64228.48 |  |  |  | 64228.48 | [10 empty] | 64228.48 | 64228.48 |  | 100% | [5 empty] | #DIV/0! | [5 empty] | 5 Completion Evaluation | 4 Implementation In Progress | 95% | 80% | Green | Green | Actual cost lower than forecasted | Workshop took place 14-18 July 2025 in Suva with key stakeholders and specialists invited. Minutes and outcomes still to be shared.
2 | OP2.2 Inclusive leadership and technical capability strengthening programmes established and delivering ongoing training to industry standards | 2.2.1 | 22 | Training of forecasters to BIP-M standard | Meteorologists Training in 2025 | 22 | 02 |  | 2202 | Major | NZ Met Services |  |  | Terry |  |  |  |  | Kiribati, Tonga | Other Support | 219240 |  |  |  | MFAT-NZ | 219240 |  |  | 7195 | 202272 | 9773 | [7 empty] | 7185.62 | 155266 | 202272 | 209457.62 |  | 95.54% | [5 empty] | #DIV/0! | [5 empty] | 4 Implementation In Progress | 4 Implementation In Progress | 50% | 50% | Green | Green | Remaining cost flowing over to 2026. | -
1 | Output 1.1 WRP governance, management and financing mechanisms established, mandated and equipped to coordinate a Pacific-led, integrated, and sustainable programme | 1.1.1 | 11 | Establish the PMU, Operational Processes and WRP pooled fund | Review of WRP governance and alignment with EW4All | 11 | 04 |  | 1104 | Standard | WRP |  |  | Ofa |  |  |  |  | All | Other Support | 75000 |  |  |  | ADB | 75000 |  |  |  | 75000 | [9 empty] | 75000 |  | 0 |  | 0% | [5 empty] | #DIV/0! | [5 empty] | 4 Implementation In Progress | 4 Implementation In Progress | 80% | 80% | Green | Green | . | Alignment review report completed and endorsed by steering committee. WRP governance review options paper being drafted for PMC to approve changes including to membership.
3 | Output 3.2 WMO-designated Pacific Regional Instrument Centre established and sustainably managed | 3.2.1 | 31 | Establish and operate a Regional Instrument Centre (RIC) | Training of FMS Staff to support ISO/IEC 17025 certification of RIC | 31 | 02 |  | 3102 | Standard | WRP |  |  | Terry |  | 2025 | [1/8/25] Awaiting quotes from Fiji Met Service for SPREP to procure. |  | Fiji | Ring-Fenced | 50504.3478 |  |  |  | MFAT- SPREP | 50504.3478 |  |  |  |  | 50504.3478 | [10 empty] | 0 |  | 0% | [5 empty] | #DIV/0! | [5 empty] | 3 Agreement | 3 Agreement | 10% | 10% | Green | Green |  | Fiji Met is sourcing quotes for training
2 | OP2.2 Inclusive leadership and technical capability strengthening programmes established and delivering ongoing training to industry standards | 2.2.4 | 25 | Establish and deliver a Pacific Meteorology Leadership Programme for mid and senior level staff | Liaison with regional institutions for the development of a Leadership Program for mid-level to senior staff level and deliver the course | 25 | 01 |  | 2501 | Major | WRP |  |  | Terry |  |  |  |  | All | Ring-Fenced | 135133.073 |  |  |  | MFAT- SPREP | 135133.073 |  |  |  |  | 135133.073 | [10 empty] | 0 |  | 0% | [5 empty] | #DIV/0! | [5 empty] | Not Started | Not Started | 0% | 0% | - | - | . | -
2 | OP2.2 Inclusive leadership and technical capability strengthening programmes established and delivering ongoing training to industry standards | 2.2.3 | 24 | Training of observers, technicians and ICT specialists, and assessment of competencies | BIP MT Training | 24 | 01 |  | 2401 | Standard | WRP |  |  | Terry |  |  | Is this for 2026 or 2027? |  | - | Ring-Fenced | 124020.19 |  |  |  | MFAT- SPREP | 124020.19 |  |  |  | 124020.19 | [9 empty] | 50548.06 | 124020.19 | 124020.19 |  | 100% | [5 empty] | #DIV/0! | [5 empty] | 4 Implementation In Progress | 4 Implementation In Progress | 50% | 50% | Green | Green | Actual cost lower than forecasted | Training in Fiji in progress for BIP-MT
2 | OP2.2 Inclusive leadership and technical capability strengthening programmes established and delivering ongoing training to industry standards | 2.2.3 | 24 | Training of observers, technicians and ICT specialists, and assessment of competencies | BIP MT Training | 24 | 01 |  | 2401 | Standard | WRP |  |  | Terry |  |  |  | 73913.0435 | - | Ring-Fenced | 147826.087 |  |  |  | DFAT | 147826.087 |  |  |  |  | 147826.087 | [10 empty] | 0 |  | 0% | [5 empty] | #DIV/0! | [5 empty] | Not Started | Not Started | 0% | 0% | - | - | . | -
2 | OP2.2 Inclusive leadership and technical capability strengthening programmes established and delivering ongoing training to industry standards | 2.2.5 | 26 | Specialised regional workshops and training courses | ISO 9001 / QMS Training delivered at Fiji Met in partnership with Fiji National University | 26 | 03 |  | 2603 | Standard | WRP |  |  | Terry |  | 2025 | Ofa is this work completed? |  | Fiji | Ring-Fenced | 54069.5652 |  |  |  | MFAT- SPREP | 54069.5652 |  |  |  |  | 54069.5652 | [10 empty] | 0 |  | 0% | [5 empty] | #DIV/0! | [5 empty] | Not Started | Not Started | 0% | 0% | - | - | . | -
2 | OP2.3 Continuous learning and mentoring opportunities provided | 2.3.1 | 28 | Twinning programme, ongoing mentoring and communities of practices | HydroMet Technician Training and Peer Network | 28 | 01 |  | 2801 | Standard | ESNZ |  |  | Marica |  |  |  |  | All | Other Support | 91640 |  |  |  | MFAT-NZ | 91640 |  |  |  | 29488 | 45000 | 17152 | [8 empty] | 29488 | 29488 |  | 32.18% | [5 empty] | #DIV/0! | [5 empty] | 4 Implementation In Progress | 4 Implementation In Progress | 10% | 10% | Green | Green | Commencement delayed. | -
3 | Output 3.1 Interoperable, affordable and resilient observation network progressively remediated, expanded and sustained | 3.1.1 | 32 | Implement observation network plans, asset management, standardised infrastructure, data management and maintenance practices | AWS and Manual Stations Observing Network Sustainability Planning and Refurbishment (part 1 - plans) | 32 | 01 |  | 3201 | Major | ESNZ |  |  | Marica |  |  |  |  | All | Other Support | 255029 |  |  |  | MFAT-NZ | 255029 |  |  |  | 255029 | [10 empty] | 274004 | 274004 |  | 107.4% | [5 empty] | #DIV/0! | [5 empty] | 4 Implementation In Progress | 4 Implementation In Progress | 5% | 5% | Green | Green | . | -
3 | Output 3.1 Interoperable, affordable and resilient observation network progressively remediated, expanded and sustained | 3.1.3 | 71 | Revitalise and expand automatic and manual weather stations | AWS and Manual Stations Observing Network Sustainability Planning and Refurbishment (part 2 - refurbishment) | 71 | 01 |  | 7101 | Major | ESNZ |  |  | Marica |  |  |  |  | - | Other Support | 1484971 |  |  |  | MFAT-NZ | 1484971 |  |  |  | 8975 | 940769 | 535227 | [9 empty] | 0 |  | 0% | [5 empty] | #DIV/0! | [5 empty] | Not Started | Not Started | 0% | 0% | - | - | . | -
3 | Output 3.1 Interoperable, affordable and resilient observation network progressively remediated, expanded and sustained | 3.1.1 | 32 | Implement observation network plans, asset management, standardised infrastructure, data management and maintenance practices | Radar Network Plan/Strategy | 32 | 03 |  | 3203 | Major | NZ Met Services |  |  | Marica |  |  |  |  | All | Other Support | 49300 |  |  |  | MFAT-NZ | 49300 |  |  | 290 | 37063 | 11947 | [7 empty] | 290 | 2283.46 | 37063 | 37353 |  | 75.77% | [5 empty] | #DIV/0! | [5 empty] | 4 Implementation In Progress | 4 Implementation In Progress | 85% | 85% | Green | Green | Delayed commencement | Progress as of Sep 2025, consultations completed and preliminary recommnedations report prepared for SC. Full report still to be developed.
1 | Output 1.1 WRP governance, management and financing mechanisms established, mandated and equipped to coordinate a Pacific-led, integrated, and sustainable programme | 1.1.2 | 12 | Operational Phase of PMU and coordination activities | PMU Travel and Workshops | 12 | 02 |  | 1202 | Standard | WRP |  |  | Honsol |  |  |  |  | All | Ring-Fenced | 295801.41 |  |  |  | DFAT Inception | 295801.41 |  |  | 55801.41 |  | 100000 | 80000 | 60000 | [5 empty] | 55801.41 |  |  | 55801.41 |  | 18.86% | [5 empty] | #DIV/0! | [5 empty] | 4 Implementation In Progress | 4 Implementation In Progress | 20% | 20% | Green | Green | . | -
3 | Output 3.1 Interoperable, affordable and resilient observation network progressively remediated, expanded and sustained | 3.1.5 | 73 | Establish weather watch radars | Tonga Radar | 73 | 06 |  | 7306 | Major | NZ Met Services |  |  | Marica |  |  |  |  | Tonga | Other Support | 2356378 |  |  |  | MFAT-NZ | 2356378 |  |  | 1906045 | 208211 | 121061 | 121061 | [6 empty] | 1906045.3 | 123389.2 | 208211 | 2114256.3 |  | 89.72% | [5 empty] | #DIV/0! | [5 empty] | 4 Implementation In Progress | 4 Implementation In Progress | 85% | 85% | Amber | Amber | Cost incurred earlier than forecasted. Budget brought forward. | Quality issues with radar being rectified and managed currently. We are in maintenance and support phase over next 2 years.
1 | Output 1.1 WRP governance, management and financing mechanisms established, mandated and equipped to coordinate a Pacific-led, integrated, and sustainable programme | 1.1.2 | 12 | Operational Phase of PMU and coordination activities | Workshops funded by UK | 12 | 01 |  | 1201 | Standard | WRP |  |  | Ofa |  |  |  |  | All | Ring-Fenced | 118130.35 |  |  |  | UK WISER | 118130.35 |  |  | 118130.35 | [9 empty] | 118130.35 |  |  | 118130.35 |  | 100% | [5 empty] | #DIV/0! | [5 empty] | 5 Completion Evaluation | 5 Completion Evaluation | 100% | 100% | Green | Green | . | -
3 | Output 3.1 Interoperable, affordable and resilient observation network progressively remediated, expanded and sustained | 3.1.5 | 73 | Establish weather watch radars | Solomon Islands Radar | 73 | 05 |  | 7305 | Major | NZ Met Services |  |  | Marica |  |  |  |  | Solomon Island | Other Support | 2580774 |  |  |  | MFAT-NZ | 2580774 |  |  |  | 764160 | 1816614 | [8 empty] | 66700 | 764160 | 764160 |  | 29.61% | [5 empty] | #DIV/0! | [5 empty] | 3 Agreement | 3 Agreement | 10% | 10% | Green | Green | Cost incurred earlier than forecasted. Budget brought forward. | -
1 | Output 1.1 WRP governance, management and financing mechanisms established, mandated and equipped to coordinate a Pacific-led, integrated, and sustainable programme | 1.1.2 | 12 | Operational Phase of PMU and coordination activities | Hosting of WRP Steering and Liaison Platform | 12 | 01 |  | 1201 | Major | WRP |  |  | Ofa |  |  |  |  | All | Ring-Fenced | 239251.48 |  |  |  | DFAT Inception | 239251.48 |  |  | 41332.18 |  | 50000 | 47919.3 | 100000 | [5 empty] | 41332.18 |  |  | 41332.18 |  | 17.28% | [5 empty] | #DIV/0! | [5 empty] | 4 Implementation In Progress | 4 Implementation In Progress | 20% | 20% | Green | Green | . | -
3 | Output 3.2 WMO-designated Pacific Regional Instrument Centre established and sustainably managed | 3.2.1 | 31 | Establish and operate a Regional Instrument Centre (RIC) | Construction and operationalisation of Regional Instrumentation Centre |  |  |  |  | External | JICA | [7 empty] | All |  | 1000000 | JICA | 1000000 |  | JICA | 0 | [15 empty] | 0 |  | - | [5 empty] | #DIV/0! | [7 empty] | - | - | - | - |  | -
2 | OP2.1 WMO-designated Pacific Regional Training Centre established and sustainably managed | 2.1.1 | 21 | Establish and operate a Regional Training Centre (RTC) | Construction and operationalisation of Regional Training Centre |  |  |  |  | External | JICA | [7 empty] | All |  | 1000000 | JICA | 1000000 |  | JICA | 0 | [15 empty] | 0 |  | - | [5 empty] | #DIV/0! | [7 empty] | - | - | - | - | . | -
3 | Output 3.1 Interoperable, affordable and resilient observation network progressively remediated, expanded and sustained | 3.1.1 | 32 | Implement observation network plans, asset management, standardised infrastructure, data management and maintenance practices | Guidance Document for Standardisation and Maintenance of Meteorological Equipment | 32 | 02 |  | 3202 | Major | ESNZ |  |  | Marica |  |  |  |  | All | Other Support | 102370 |  |  |  | MFAT-NZ | 102370 |  |  |  | 62070 | 40300 | [9 empty] | 62070 | 62070 |  | 60.63% | [5 empty] | #DIV/0! | [5 empty] | 4 Implementation In Progress | 4 Implementation In Progress | 10% | 10% | Green | Green | . | Draft TOC for consultation
4 | OP4.2 Pacific forecasting capacity expanded and maintained | 4.2.1 | 42 | Strengthen aviation forecasting | Aviation industry workshop | 42 | 01 |  | 4201 | Standard | WRP |  |  | Ofa |  |  |  | 30000 | All | Ring-Fenced | 30000 |  |  |  | DFAT | 30000 |  |  |  |  | 30000 | [10 empty] | 0 |  | 0% | [5 empty] | #DIV/0! | [5 empty] | Not Started | Not Started | 0% | 0% | - | - | . | -
2 | OP2.1 WMO-designated Pacific Regional Training Centre established and sustainably managed | 2.1.1 | 21 | Establish and operate a Regional Training Centre (RTC) | Governance framework for RTC and RIC | 21 | 03 |  | 2103 | Major | ADB |  |  | Marica |  |  |  |  | All | Other Support | 75000 |  |  |  | ADB | 75000 |  |  |  | 75000 | [11 empty] | 0 |  | 0% | [5 empty] | #DIV/0! | [5 empty] | 4 Implementation In Progress | 4 Implementation In Progress | 30% | 30% | Green | Green | . | Proress as of Sep 2025, options report completed and to be tabled at SC.
4 | OP4.2 Pacific forecasting capacity expanded and maintained | 4.2.2 | 43 | Strengthen public forecasting | Severe Weather Pilot (3 countries) - strengthen public forecasting | 43 |  |  |  | Major | NZ Met Services | [7 empty] | Fiji, Tonga, Niue | Other Support | 597647 |  |  |  | MFAT-NZ | 597647 |  |  | 331114 | 159336 | 107197 | [7 empty] | 309766.6667 | 154883.3333 | 337025 | 646791.6667 | 0 | 108.2% | [5 empty] | #DIV/0! | [5 empty] | 5 Completion Evaluation | 5 Completion Evaluation | 80% | 80% | Green | Green | Effort less than forecasted | Draft completion report prepared
2 | OP2.3 Continuous learning and mentoring opportunities provided | 2.3.1 | 28 | Twinning programme, ongoing mentoring and communities of practices | Severe Weather Pilot (3 countries) - twinning and community of practice | 28 |  |  |  | Major | NZ Met Services | [6 empty] | 177689 | Fiji, Tonga, Niue | Other Support | 398431 |  |  |  | MFAT-NZ | 398431 |  |  | 220742 | 177689 | [8 empty] | 206511.3333 | 103255.6667 |  | 206511.3333 | 0 | 51.83% | [5 empty] | #DIV/0! | [5 empty] | 5 Completion Evaluation | 5 Completion Evaluation | 80% | 80% | Green | Green | . | Draft completion report prepared
2 | OP2.3 Continuous learning and mentoring opportunities provided | 2.3.1 | 28 | Twinning programme, ongoing mentoring and communities of practices | Strengthen public weather forecasting practices, community of practice and twinning | 28 |  |  |  | Major | WRP | [6 empty] | 0 | All | Ring-Fenced | 0 |  |  |  | DFAT | 0 | [15 empty] | 0 |  | - | [5 empty] | #DIV/0! | [5 empty] | Not Started | Not Started | 0% | 0% | - | - | . | Recommendation from IFP peer review, continue to strengthen public weather forecasting capabilities and community of practice as sucessfully demonstrated in severe weather forecasting pilot project.
4 | Output 4.1 An integrated Pacific forecasting platform established and operating sustainably to global standards | 4.1.1 | 41 | Develop an Integrated Forecasting Platform and strengthen RSMCs (incl WIS, CAP) | Technical partners Integrated Forecast System Workshop | 41 | 03 | 2601 | 4103 | Standard | WRP |  |  | Ofa |  |  |  |  | All | Ring-Fenced | 26956.5217 |  |  |  | MFAT- SPREP | 26956.5217 |  |  |  |  | 26956.5217 | [10 empty] | 0 |  | 0% | [5 empty] | #DIV/0! | [5 empty] | Not Started | Not Started | 0% | 0% | - | - | . | -
2 | OP2.2 Inclusive leadership and technical capability strengthening programmes established and delivering ongoing training to industry standards | 2.2.1 | 22 | Training of forecasters to BIP-M standard | Meteorologists Training in 2024 | 22 | 02 |  | 2202 | Standard | BOM |  |  | Terry |  |  |  | 76226.37 | Samoa | Ring-Fenced | 139379 |  |  |  | DFAT | 139379 |  |  |  | 76226.37 | 63152.63 | [8 empty] | 76226.37 | 76226.37 | 76226.37 |  | 54.69% | [5 empty] | #DIV/0! | [5 empty] | 5 Completion Evaluation | 5 Completion Evaluation | 100% | 100% | Green | Green | Actual cost greater than forecasted. | Additional invoice to be issued by Bureau to be paid
2 | OP2.2 Inclusive leadership and technical capability strengthening programmes established and delivering ongoing training to industry standards | 2.2.1 | 22 | Training of forecasters to BIP-M standard | Meteorologists Training | 22 | 02 | 2507 | 2202 | Standard | BOM |  |  | Terry |  | 2025 | [1/8/25] Concept note and contract with BoM needed | 90000 | - | Ring-Fenced | 360000 |  |  |  | DFAT | 360000 |  |  |  |  | 180000 | 180000 | [9 empty] | 0 |  | 0% | [5 empty] | #DIV/0! | [5 empty] | 4 Implementation In Progress | 1 Concept | 5% | 5% | Green | Green | . | Vanautu (1) and Fiji (2) candidate. Potentially 1 candidate more from Fiji.
2 | OP2.2 Inclusive leadership and technical capability strengthening programmes established and delivering ongoing training to industry standards | 2.2.2 | 23 | Training on specialised forecasting services, and assessment of competencies (e.g. marine, aviation, hydrology/ hydrography) | Hydrologists Training | 23 | 01 |  | 2301 | Standard | PAGASA |  |  | Terry |  | 2025 | [1/8/25] 'Ofa chasing PAGASA/WMO for course costs and details to finalise procurement. | 0 | - | Ring-Fenced | 110000 |  |  |  | DFAT | 110000 |  |  |  |  | 30000 | 80000 | [9 empty] | 0 |  | 0% | [5 empty] | #DIV/0! | [5 empty] | 3 Agreement | 3 Agreement | 5% | 5% | Green | Green | Deferred to 2026. Limited hydrology training available. | PAGASA/WMO to confirm course content, costs and timing. WRP organising student travel and accom.
2 | OP2.2 Inclusive leadership and technical capability strengthening programmes established and delivering ongoing training to industry standards | 2.2.1 | 22 | Training of forecasters to BIP-M standard | Development of bridging and/or support for BIP-M in collaboration with RTC, USP and PIETR. | 22 | 03 |  | 2203 | Standard | WRP, BOM |  |  | Terry |  | 2025 | on hold til after 14-19 July workshop |  | - | Ring-Fenced | 92973.75 |  |  |  | DFAT | 92973.75 |  |  |  |  | 92973.75 | [10 empty] | 0 |  | 0% | [5 empty] | #DIV/0! | [5 empty] | Paused | Paused | 0% | 0% | - | - | . | Training Workshop in Suva scheduled 14-18 July. PEITR panel task team for RTC established. This activity and budget can be assigned to them for implementation.
3 | Output 3.1 Interoperable, affordable and resilient observation network progressively remediated, expanded and sustained | 3.1.2 | 33 | Provide asset management and maintenance staff to expand capacity (e.g. SPREP, SPC, NMHS) | Staff: Asset Manager | 33 | 0 |  |  | Staff | WRP |  |  | Marica |  |  |  |  | All | Ring-Fenced | 379776 |  |  |  | DFAT | 379776 | [5 empty] | 126592 | 126592 | 126592 | [7 empty] | 0 |  | 0% | [5 empty] | #DIV/0! | [5 empty] | Paused | Paused | 5% | 5% | - | - | . | JD drafted. Paused while finalising recruitment of Infrastructure and ICT adviser and World Bank TA availability, to inform the exact need for this role and timing.
3 | Output 3.1 Interoperable, affordable and resilient observation network progressively remediated, expanded and sustained | 3.1.1 | 32 | Implement observation network plans, asset management, standardised infrastructure, data management and maintenance practices | Establish pacific Asset Management Capability, Plans and Lifecycle Cost Forecast | 32 | 05 | 2504 | 3205 | Major | WRP |  |  | Marica |  | 2025 | awaiting world bank | 25000 | All | Ring-Fenced | 200000 |  |  |  | DFAT | 200000 |  |  |  |  | 50000 | 150000 | [9 empty] | 0 |  | 0% | [5 empty] | #DIV/0! | [5 empty] | 1 Concept | 1 Concept | 5% | 5% | Green | Green | . | Concept Note drafted. World Bank briefed also as a possible alternative funder for TA/consultant.
4 | Output 4.1 An integrated Pacific forecasting platform established and operating sustainably to global standards | 4.1.1 | 41 | Develop an Integrated Forecasting Platform and strengthen RSMCs (incl WIS, CAP) | COSPPac Data management, products and services |  |  |  |  | External | BOM | [9 empty] | 0 | DFAT/MFAT | ?? |  |  | 0 | [15 empty] | 0 |  | - | [5 empty] | #DIV/0! | [7 empty] | - | - | - | - | . | -
4 | OP4.2 Pacific forecasting capacity expanded and maintained | 4.2.4 | 45 | Strengthen coastal inundation forecasting | Tokelau Data Collection and Inundation Forecasting | 45 | 01 |  | 4501 | Major | ESNZ |  |  | Terry |  |  |  |  | Tokelau | Other Support | 435000 |  |  |  | MFAT-NZ | 435000 |  |  |  | 21387 | 306806 | 106807 | [8 empty] | 21387 | 21387 |  | 4.917% | [5 empty] | #DIV/0! | [5 empty] | 4 Implementation In Progress | 4 Implementation In Progress | 0% | 0% | Green | Green | Major work delayed to 2026 due to logistics. | -
4 | Output 4.1 An integrated Pacific forecasting platform established and operating sustainably to global standards | 4.1.1 | 41 | Develop an Integrated Forecasting Platform and strengthen RSMCs (incl WIS, CAP) | Secondment of Forecasting Specialist to progress IFP, KRA 2 and 3. | 41 | 02 |  | 4102 | Standard | WRP |  |  | Terry |  | 2025 | [1/8/25] 'Ofa to confirm if plan to change WISER grant to fund this secondment |  | All |  | 0 |  |  |  | DFAT | 0 | [15 empty] | 0 |  | - | [5 empty] | #DIV/0! | [5 empty] | Paused | Paused | 0% | 0% | - | - | . | -
4 | OP4.2 Pacific forecasting capacity expanded and maintained | 4.2.4 | 45 | Strengthen coastal inundation forecasting | Develop Lidar strategy for the Pacific | 45 | 03 |  | 4503 | Major | SPC |  |  | Terry |  | 2025 | [1/8/25] Concept Note missing. Honsol finalising SPC LOA with procurement. Need 'Ofa to review | 0 | All | Ring-Fenced | 12396.5 |  |  |  | DFAT | 12396.5 |  |  |  |  | 12396.5 | [10 empty] | 0 |  | 0% | [5 empty] | #DIV/0! | [5 empty] | 3 Agreement | 3 Agreement | 1% | 1% | Green | Green | Work started in 2025 and to be completed in 2026. | Contract/LOA in finalisation
4 | OP4.2 Pacific forecasting capacity expanded and maintained | 4.2.4 | 45 | Strengthen coastal inundation forecasting | Complete Lidar surveys for the Marshall Islands | 45 | 02 |  | 4502 | Major | SPC |  |  | Terry |  | 2025 | [1/8/25] Concept Note missing. Honsol finalising SPC LOA with procurement. Need 'Ofa to review | 279417.63 | Marshall Islands | Ring-Fenced | 757530.46 |  |  |  | DFAT | 757530.46 |  |  |  | 279417.63 | 478112.83 | [9 empty] | 279417.63 | 279417.63 |  | 36.89% | [5 empty] | #DIV/0! | [5 empty] | 3 Agreement | 3 Agreement | 1% | 1% | Green | Green | Work started in 2025 and to be completed in 2026. | Contract/LOA in finalisation. SPC targeting procurement in Q3 and work completion in Q4/Q1.
5 | Output 5.1 Pacific capacity and collaborative approaches to deliver locally-relevant, impact-based, inclusive and accessible forecasts and warnings for end users strengthened and sustained | 5.1.6 | 56 | Install communication internet access equipment and operational costs | Plan for roll out of satellite communication, capacity development with the community, with units for selected countries | 56 | 01 |  | 5601 | Major | Tonga, Solomon Islands, Kiribati |  |  | Marica |  | 2025 | [1/8/25] 'Ofa chase starlink quotes from Solomon island, for SPREP to procure. Jess & Sue meeting with Jope on ESS screening on 8/8/25. Need meeting on sustainability screening with Kat, in order to finalise concept notes from Tonga and Kiribati. | 0 | Tonga, Solomon Islands, Kiribati | Ring-Fenced | 40931.14 |  |  |  | DFAT | 40931.14 |  |  |  |  | 40931.14 | [10 empty] | 0 |  | 0% | [5 empty] | #DIV/0! | [5 empty] | 1 Concept | 1 Concept | 10% | 10% | Green | Green | Agreement/procurement deferred to 2026. Concept drafted in 2025. | Tonga and Solomon Islands have submitted Concept Notes to WRP for approval. Kiribitis still to develop. LOA being prepared.
0 | Contingency and Other | 0 | 00 | Contingency and Other | MHEWS Readiness Fund (flexi-fund) | 90 |  |  |  | Standard | NMHS |  |  | Honsol |  | 2025 | [1/8/25] 'Ofa to send to directors MHEWS Readiness Fund information pack, so we can receive their concept note proposals for review. | 11540.85 | All | Ring-Fenced | 611540.85 |  |  |  | DFAT | 611540.85 |  |  |  | 11540.85 | 150000 | 150000 | 150000 | 150000 | [6 empty] | 11540.85 | 11540.85 |  | 1.887% | [5 empty] | #DIV/0! | [5 empty] | 1 Concept | 1 Concept | 5% | 5% | Amber | Amber | Most beneficiary countries did not submit concepts/request in 2025. Budget reallocated. | Flexible fund procedure developed for SC approval. One concept received from Vanautu. Risk of not spending funding allocated.
1 | Output 1.1 WRP governance, management and financing mechanisms established, mandated and equipped to coordinate a Pacific-led, integrated, and sustainable programme | 1.1.4 | 14 | PMU Staff (Management and Delivery Support roles) | Staff: Programme Manager | 14 | 0 |  |  | Staff | WRP | [6 empty] | 241150.8533 | All | Ring-Fenced | 1044482.92 |  |  |  | DFAT Inception | 1044482.92 |  |  | 91567.4 | 158387.52 | 198632 | 198632 | 198632 | 198632 |  |  |  |  | 89105.92 | 65371.06 | 158387.52 | 247493.44 |  | 23.7% | [5 empty] | #DIV/0! | [5 empty] | 5 Completion Evaluation | 5 Completion Evaluation | 100% | 100% | Green | Green | Known over-estimate in salary cost. | -
3 | Output 3.1 Interoperable, affordable and resilient observation network progressively remediated, expanded and sustained | 3.1.2 | 33 | Provide asset management and maintenance staff to expand capacity (e.g. SPREP, SPC, NMHS) | Staff: Technical Adviser Infrastructure & ICT | 33 | 0 |  |  | Staff | WRP | [6 empty] | 113081.7833 | All | Ring-Fenced | 698103.95 |  |  |  | DFAT Inception | 698103.95 |  |  |  | 45055.95 | 163262 | 163262 | 163262 | 163262 | [6 empty] | 45055.95 | 45055.95 |  | 6.454% | [5 empty] | #DIV/0! | [5 empty] | 4 Implementation In Progress | 4 Implementation In Progress | 80% | 80% | Green | Green | . | Recruitment close to finalisation
1 | Output 1.1 WRP governance, management and financing mechanisms established, mandated and equipped to coordinate a Pacific-led, integrated, and sustainable programme | 1.1.4 | 14 | PMU Staff (Management and Delivery Support roles) | Staff: Finance Accountant | 14 | 0 |  |  | Staff | WRP | [6 empty] | 128065.9067 | All | Ring-Fenced | 665010.49 |  |  |  | DFAT Inception | 665010.49 |  |  |  | 65630.49 | 149845 | 149845 | 149845 | 149845 | [5 empty] | 6334.15 | 65630.49 | 65630.49 |  | 9.869% | [5 empty] | #DIV/0! | [5 empty] | 5 Completion Evaluation | 5 Completion Evaluation | 100% | 100% | Green | Green | Known over-estimate in salary cost. | Role recruited, in June 2025.
1 | Output 1.1 WRP governance, management and financing mechanisms established, mandated and equipped to coordinate a Pacific-led, integrated, and sustainable programme | 1.1.4 | 14 | PMU Staff (Management and Delivery Support roles) | Staff: Finance & Administration Officer | 14 | 0 |  |  | Staff | WRP | [6 empty] | 44774.4567 | All | Ring-Fenced | 187780.96 |  |  |  | DFAT Inception | 187780.96 |  |  | 9778.17 | 29282.79 | 37180 | 37180 | 37180 | 37180 |  |  |  |  | 12239.65 | 13723.23 | 29282.79 | 41522.44 |  | 22.11% | [5 empty] | #DIV/0! | [5 empty] | 5 Completion Evaluation | 5 Completion Evaluation | 100% | 100% | Green | Green | Known over-estimate in salary cost. | Role recruited, in Sept 2024.
1 | Output 1.3 Transformative GEDSI strategy adopted and integrated across governance, management and partner programming | 1.3.1 | 81 | GEDSI and social safeguards mainstreamed into WRP | GEDSI and Social Safeguard Specialist | 81 | 0 |  |  | Standard | WRP | [7 empty] | All | Other Support | 86400 |  |  |  | UNDRR | 86400 |  |  |  | 86400 | [9 empty] | 57600 |  | 0 |  | 0% | [5 empty] | #DIV/0! | [5 empty] | 4 Implementation In Progress | 4 Implementation In Progress | 80% | 80% | Green | Green | . | GEDSI Advisor Sue contracted by UNDRR.
1 | Output 1.1 WRP governance, management and financing mechanisms established, mandated and equipped to coordinate a Pacific-led, integrated, and sustainable programme | 1.1.4 | 14 | PMU Staff (Management and Delivery Support roles) | Staff: ESS/GEDSI Officer | 14 | 0 |  |  | Staff | WRP |  |  |  |  | 2025 | [1/8/25] Honsol awaiting procurement to extend Sue's contract. Pomate to obtain copy of standard SPREP Job description needed for new Officer | 23433.5069 | All | Ring-Fenced | 461171.4167 |  |  |  | DFAT Inception | 461171.4167 |  |  |  |  | 56240.4167 | 134977 | 134977 | 134977 | [7 empty] | 0 |  | 0% | [5 empty] | #DIV/0! | [5 empty] | 1 Concept | 1 Concept | 10% | 10% | Amber | Amber | Recruitment deferred to 2026. | JD drafted. Recruitment delayed.
2 | OP2.2 Inclusive leadership and technical capability strengthening programmes established and delivering ongoing training to industry standards | 2.2.6 | 27 | Provide additional staff for training and capacity development | Staff: Support to WRP PMU Human Resource | 27 | 03 |  | 2703 | Staff | WRP |  |  |  |  | 2025 | [1/8/25] 'Ofa to shortlist and interview |  | All | Ring-Fenced | 129352.06 |  |  |  | UK WISER | 129352.06 |  |  |  | 17405.06 | 111947 | [9 empty] | 17405.06 | 17405.06 |  | 13.46% | [5 empty] | #DIV/0! | [5 empty] | 3 Agreement | 3 Agreement | 50% | 50% | Amber | Amber | Recruitment delayed | Advertisement closed. Recruitment delayed.
2 | OP2.2 Inclusive leadership and technical capability strengthening programmes established and delivering ongoing training to industry standards | 2.2.6 | 27 | Provide additional staff for training and capacity development | Staff: Technical Adviser Capability Training | 27 | 0 |  |  | Staff | WRP | [7 empty] | All | Ring-Fenced | 585022.1667 |  |  |  | DFAT | 585022.1667 |  |  |  |  | 95236.1667 | 163262 | 163262 | 163262 | [7 empty] | 0 |  | 0% | [5 empty] | #DIV/0! | [5 empty] | 3 Agreement | 3 Agreement | 50% | 50% | Amber | Amber | . | Advertisement closed. Recruitment delayed.
5 | Output 5.1 Pacific capacity and collaborative approaches to deliver locally-relevant, impact-based, inclusive and accessible forecasts and warnings for end users strengthened and sustained | 5.1.7 | 57 | Provide additional staff for warning communication and engagement to expand capacity | Staff: Technical Adviser Forecasting | 57 | 0 |  |  | Staff | WRP |  |  |  |  | 2025 | [1/8/25] 'Ofa to draft job description | 0 | All | Ring-Fenced | 163262 |  |  |  | DFAT | 163262 | [7 empty] | 163262 | [7 empty] | 0 |  | 0% | [5 empty] | #DIV/0! | [5 empty] | Paused | Paused | 0% | 0% | - | - | . | Postpone recruitment and focus efforts on other KRAs with existing committed funding.
1 | Output 1.1 WRP governance, management and financing mechanisms established, mandated and equipped to coordinate a Pacific-led, integrated, and sustainable programme | 1.1.4 | 14 | PMU Staff (Management and Delivery Support roles) | Staff: Procurement and Contracts Officer | 14 | 0 |  |  | Staff | WRP |  |  |  |  | 2025 | [1/8/25] 'Ofa to interview | 94961.6367 | All | Ring-Fenced | 578629.22 |  |  |  | DFAT | 578629.22 |  |  |  | 38721.22 | 134977 | 134977 | 134977 | 134977 | [6 empty] | 38721.22 | 38721.22 |  | 6.692% | [5 empty] | #DIV/0! | [5 empty] | 2 Appraisal | 2 Appraisal | 50% | 50% | Amber | Amber | Actual cost higher than budgeted. | Advertisement closed. Recruitment delayed.
1 | Output 1.1 WRP governance, management and financing mechanisms established, mandated and equipped to coordinate a Pacific-led, integrated, and sustainable programme | 1.1.4 | 14 | PMU Staff (Management and Delivery Support roles) | Staff: Communications and Knowledge Management Officer | 14 | 0 |  |  | Staff | WRP |  |  |  |  | 2025 | [1/8/25] Awaiting job ad to close 15 August | 56240.4167 | All | Ring-Fenced | 539908 |  |  |  | DFAT | 539908 |  |  |  |  | 134977 | 134977 | 134977 | 134977 | [7 empty] | 0 |  | 0% | [5 empty] | #DIV/0! | [5 empty] | 2 Appraisal | 2 Appraisal | 50% | 50% | Amber | Amber | Recruitment deferred to 2026. | Advertisement closed. Recruitment delayed.
5 | Output 5.1 Pacific capacity and collaborative approaches to deliver locally-relevant, impact-based, inclusive and accessible forecasts and warnings for end users strengthened and sustained | 5.1.1 | 51 | Planning for delivery of impact-based messages and warnings to end-users, considering persons with disabilities and vulnerable groups. | National consultation workshops with selected countries to review existing messages and warnings | 51 | 01 |  | 5101 | Major | WRP |  |  | Terry |  |  |  |  | All | Ring-Fenced | 20000.0007 |  |  |  | MFAT- SPREP | 20000.0007 | [5 empty] | 20000.0007 | [9 empty] | 0 |  | 0% | [5 empty] | #DIV/0! | [5 empty] | Not Started | Not Started | 0% | 0% | - | - | . | -
1 | Output 1.1 WRP governance, management and financing mechanisms established, mandated and equipped to coordinate a Pacific-led, integrated, and sustainable programme | 1.1.4 | 14 | PMU Staff (Management and Delivery Support roles) | Staff: Monitoring , Evaluation, Research , Learning and Adaptation Officer (MERLA) | 14 | 0 |  |  | Staff | WRP |  |  |  |  | 2025 | [1/8/25] Pomate to obtain copy of standard SPREP Job description needed for new Officer | 37493.6111 | All | Ring-Fenced | 494915.6667 |  |  |  | DFAT | 494915.6667 |  |  |  |  | 89984.6667 | 134977 | 134977 | 134977 | [7 empty] | 0 |  | 0% | [5 empty] | #DIV/0! | [5 empty] | 1 Concept | 1 Concept | 10% | 10% | Amber | Amber | Recruitment deferred to 2026. | JD drafted. Recruitment delayed.
1 | Output 1.1 WRP governance, management and financing mechanisms established, mandated and equipped to coordinate a Pacific-led, integrated, and sustainable programme | 1.1.4 | 14 | PMU Staff (Management and Delivery Support roles) | Staff: Resource Mobilisation Officer | 14 | 0 |  |  | Staff | WRP | [5 empty] | [25/8/25] Engage consultant or TA instead to develop strategy and support implementation |  | All | Ring-Fenced | 0 |  |  |  | DFAT | 0 | [15 empty] | 0 |  | - | [5 empty] | #DIV/0! | [5 empty] | Paused | Paused | 0% | 0% | - | - | . | Decision to prioritise development of resource mobilisation strategy and paused recruitment (budget allocation removed for now)
1 | Output 1.1 WRP governance, management and financing mechanisms established, mandated and equipped to coordinate a Pacific-led, integrated, and sustainable programme | 1.1.4 | 14 | PMU Staff (Management and Delivery Support roles) | Staff: WRP Secretariat and PMC Technical Support Officer | 14 | 0 |  |  | Staff | WRP |  |  |  |  | 2026 |  | 21977.7778 | All | Ring-Fenced | 432522.6667 |  |  |  | DFAT | 432522.6667 |  |  |  |  | 52746.6667 | 126592 | 126592 | 126592 | [7 empty] | 0 |  | 0% | [5 empty] | #DIV/0! | [5 empty] | Not Started | Not Started | 0% | 0% | Amber | Amber | . | Recruitment delayed.
1 | Output 1.1 WRP governance, management and financing mechanisms established, mandated and equipped to coordinate a Pacific-led, integrated, and sustainable programme | 1.1.4 | 14 | PMU Staff (Management and Delivery Support roles) | Staff: ICT Officer | 14 | 0 |  |  | Staff | WRP | [7 empty] | All | Ring-Fenced | 0 |  |  |  | DFAT | 0 | [15 empty] | 0 |  | - | [5 empty] | #DIV/0! | [5 empty] | Not Started | Not Started | 0% | 0% | - | - | . | -
1 | Output 1.1 WRP governance, management and financing mechanisms established, mandated and equipped to coordinate a Pacific-led, integrated, and sustainable programme | 1.1.4 | 14 | PMU Staff (Management and Delivery Support roles) | Staff: Finance Investment Advisor | 14 | 0 |  |  | Staff | WRP | [7 empty] | All | Ring-Fenced | 0 |  |  |  | DFAT | 0 | [15 empty] | 0 |  | - | [5 empty] | #DIV/0! | [5 empty] | Not Started | Not Started | 0% | 0% | - | - | . | -
1 | Output 1.1 WRP governance, management and financing mechanisms established, mandated and equipped to coordinate a Pacific-led, integrated, and sustainable programme | 1.1.1 | 11 | Establish the PMU, Operational Processes and WRP pooled fund | Communication Strategy and Action Plan | 11 | 06 |  | 1106 | Standard | WRP |  |  | Ange |  |  |  | 0 | All | Ring-Fenced | 0 |  |  |  | DFAT | 0 |  |  |  |  | 0 | [10 empty] | 0 |  | - | [5 empty] | #DIV/0! | [5 empty] | Not Started | Not Started | 0% | 0% | - | - | . | Awaiting Communication Officer to be onboard. Expected in Q4 2025.
1 | Output 1.1 WRP governance, management and financing mechanisms established, mandated and equipped to coordinate a Pacific-led, integrated, and sustainable programme | 1.1.1 | 11 | Establish the PMU, Operational Processes and WRP pooled fund | Resource Mobilisation Strategy | 11 | 07 |  | 1107 | Standard | WRP |  |  | Ofa |  | 2025 | [1/8/25] Ofa to confirm if world bank can fund the development |  | All | Ring-Fenced | 50000 |  |  |  | DFAT | 50000 |  |  |  |  | 50000 | [10 empty] | 0 |  | 0% | [5 empty] | #DIV/0! | [5 empty] | 1 Concept | 1 Concept | 5% | 5% | Green | Green | . | Decision to prioritise development of resource mobilisation strategy to be excuted by Ofa, Sal and Salome. The need for a resource mobilisation officer to be reviewed (paused for now and removed from budgeting). World bank confirmed funding TA to develop strategy as aligns well with the Investment facility and asset management activity.
1 | Output 1.1 WRP governance, management and financing mechanisms established, mandated and equipped to coordinate a Pacific-led, integrated, and sustainable programme | 1.1.1 | 11 | Establish the PMU, Operational Processes and WRP pooled fund | Environmental and Social Safeguard Framework | 11 | 08 |  | 1108 | Standard | WRP |  |  | Ofa |  | 2025 | [1/8/25] Jess & Sue to meet with Jope 8/8/25 to confirm if procurement needed for ESS framework to be developed for WRP | 0 | All | Ring-Fenced | 25000 |  |  |  | DFAT | 25000 |  |  |  |  | 25000 | [10 empty] | 0 |  | 0% | [5 empty] | #DIV/0! | [5 empty] | 1 Concept | 1 Concept | 5% | 5% | Green | Green | . | SPREP ESS team to undertake initial programme screening per SPREP process and develop WRP operations manual chapter.
1 | Output 1.1 WRP governance, management and financing mechanisms established, mandated and equipped to coordinate a Pacific-led, integrated, and sustainable programme | 1.1.1 | 11 | Establish the PMU, Operational Processes and WRP pooled fund | Pooled fund - Legal and financial framework around the WRP Investment Facility | 11 | 09 |  | 1109 | Major | WRP |  |  | Honsol |  | 2025 | Honsol to confirm if this is pooled fund consultant? | 38727 | All | Ring-Fenced | 100000 |  |  |  | DFAT | 100000 |  |  |  | 38727 | 61273 | [9 empty] | 38727 | 38727 |  | 38.73% | [5 empty] | #DIV/0! | [5 empty] | 4 Implementation In Progress | 4 Implementation In Progress | 70% | 70% | Green | Green | Consultant commenced in 2025 and work will be completed in 2026. | UK consultant "MDY" engaged and completed options report for SPREP and SC.
1 | Output 1.1 WRP governance, management and financing mechanisms established, mandated and equipped to coordinate a Pacific-led, integrated, and sustainable programme | 1.1.2 | 12 | Operational Phase of PMU and coordination activities | Staff start up cost (IT, furniture) and communicating & promotion Office space and operational costs | 12 | 03 |  | 1203 | Standard | WRP |  |  | Honsol |  |  |  | 34985.21 | - | Ring-Fenced | 187933.7 |  |  |  | DFAT Inception | 187933.7 |  |  | 21803.49 | 19310.21 | 37620 | 36400 | 36400 | 36400 |  |  |  |  | 21803.49 | 640.89 | 19310.21 | 41113.7 |  | 21.88% | [5 empty] | #DIV/0! | [5 empty] | 4 Implementation In Progress | 4 Implementation In Progress | 20% | 20% | Green | Green | Actual cost higher than budgeted. | -
5 | Output 5.1 Pacific capacity and collaborative approaches to deliver locally-relevant, impact-based, inclusive and accessible forecasts and warnings for end users strengthened and sustained | 5.1.1 | 51 | Planning for delivery of impact-based messages and warnings to end-users, considering persons with disabilities and vulnerable groups. | Regional workshop with NDMOs, NMHS, EW4All to review existing messaging and develop plan for preparation and delivery of response-based messaging and warnings to end users | 51 | 02 |  | 5102 | Standard | WRP |  |  | Terry |  |  |  |  | All | Ring-Fenced | 50000.0002 |  |  |  | MFAT- SPREP | 50000.0002 | [5 empty] | 50000.0002 | [9 empty] | 0 |  | 0% | [5 empty] | #DIV/0! | [5 empty] | Not Started | Not Started | 0% | 0% | - | - | . | -
3 | Output 3.1 Interoperable, affordable and resilient observation network progressively remediated, expanded and sustained | 3.1.1 | 32 | Implement observation network plans, asset management, standardised infrastructure, data management and maintenance practices | Ocean and tides network plan | 32 | 07 |  | 3207 | Major | WRP |  |  | Marica |  | 2025 | [1/8/15] To discuss with this can be added to SPC LOA scope. | 0 | All | Ring-Fenced | 20000 |  |  |  | DFAT | 20000 | [5 empty] | 20000 | [9 empty] | 0 |  | 0% | [5 empty] | #DIV/0! | [5 empty] | Not Started | Not Started | 0% | 0% | - | - | Deferred to 2027 | Need to identify which organisation will do this work.
3 | Output 3.1 Interoperable, affordable and resilient observation network progressively remediated, expanded and sustained | 3.1.1 | 32 | Implement observation network plans, asset management, standardised infrastructure, data management and maintenance practices | Flood and hydrology network plan | 32 | 08 |  | 3208 | Major | WRP |  |  | Marica |  | 2025 | [1/8/15] To discuss with this can be added to SPC LOA scope. | 0 | All | Ring-Fenced | 20000 |  |  |  | DFAT | 20000 | [5 empty] | 20000 | [9 empty] | 0 |  | 0% | [5 empty] | #DIV/0! | [5 empty] | Not Started | Not Started | 0% | 0% | - | - | Deferred to 2027, after hydrology stategy is devloped in 2026. | Need to identify which organisation will do this work.
3 | Output 3.1 Interoperable, affordable and resilient observation network progressively remediated, expanded and sustained | 3.1.1 | 32 | Implement observation network plans, asset management, standardised infrastructure, data management and maintenance practices | ICT Network plan | 32 | 09 |  | 3209 | Major | WRP |  |  | Terry |  | 2026 |  | 0 | All | Ring-Fenced | 10000 |  |  |  | DFAT | 10000 | [5 empty] | 10000 | [9 empty] | 0 |  | 0% | [5 empty] | #DIV/0! | [5 empty] | Not Started | Not Started | 0% | 0% | - | - | . | Need to identify which organisation will do this work.
3 | Output 3.1 Interoperable, affordable and resilient observation network progressively remediated, expanded and sustained | 3.1.1 | 32 | Implement observation network plans, asset management, standardised infrastructure, data management and maintenance practices | Geohazard Network Plan | 32 | 10 |  | 3210 | Major | WRP |  |  | Terry |  | 2026 |  | 0 | All | Ring-Fenced | 20000 |  |  |  | DFAT | 20000 | [5 empty] | 20000 | [9 empty] | 0 |  | 0% | [5 empty] | #DIV/0! | [11 empty] | .
5 | Output 5.1 Pacific capacity and collaborative approaches to deliver locally-relevant, impact-based, inclusive and accessible forecasts and warnings for end users strengthened and sustained | 5.1.4 | 54 | Inclusive Community Education and Information-Exchange collectives | Translation and printing of COPE books | 54 | 01 |  | 5401 | Standard | WRP |  |  | Terry |  | 2026 |  |  | - | Ring-Fenced | 86956.5217 |  |  |  | MFAT- SPREP | 86956.5217 |  |  |  |  | 86956.5217 | [10 empty] | 0 |  | 0% | [5 empty] | #DIV/0! | [5 empty] | Not Started | Not Started | 0% | 0% | - | - | . | -
3 | Output 3.1 Interoperable, affordable and resilient observation network progressively remediated, expanded and sustained | 3.1.3 | 71 | Revitalise and expand automatic and manual weather stations | Partnership for Aviation Component 1 - Provision of infrastructure for aviation weather observations |  |  |  |  | External | BOM | [9 empty] | 0 | DFAT | ?? |  |  | 0 | [15 empty] | 0 |  | - | [5 empty] | #DIV/0! | [7 empty] | - | - | - | - | . | -
2 | OP2.2 Inclusive leadership and technical capability strengthening programmes established and delivering ongoing training to industry standards | 2.2.3 | 24 | Training of observers, technicians and ICT specialists, and assessment of competencies | Partnership for Aviation Component 2 - Training for aviation weather forecasters, observers, and technicians |  |  |  |  | External | BOM | [9 empty] | 0 | DFAT | ?? |  |  | 0 | [15 empty] | 0 |  | - | [5 empty] | #DIV/0! | [7 empty] | - | - | - | - | . | -
4 | OP4.2 Pacific forecasting capacity expanded and maintained | 4.2.5 | 46 | Strengthen hydrological services and riverine flood forecasting | Development of a regional strategy for hydrology | 46 | 01 | 2502 | 4601 | Major | SPC |  |  | Terry |  | 2025 | [Jess: 1/8/25] Honsol finalising LOA. Need 'Ofa to review. | 92973.75 | All | Ring-Fenced | 842962 | SPC, WMO CREWS 3.0, Australian Water Partnership, Global Environment Facility/Food and Agriculture Organisation | 749988.25 |  | DFAT | 92973.75 |  |  |  | 0 | 92973.75 | 0 | [9 empty] | 0 |  | 0% | [5 empty] | #DIV/0! | [5 empty] | 3 Agreement | 3 Agreement | 20% | 20% | Green | Green | Work started in 2025 and to be completed in 2026. | Concept Note developed. Cotract/LOA being established.
2 | OP2.3 Continuous learning and mentoring opportunities provided | 2.3.1 | 28 | Twinning programme, ongoing mentoring and communities of practices | Twinning Arrangement Solomon Islands |  |  |  |  | External | BOM | [7 empty] | Solomon Islands |  | 0 | DFAT | ?? |  |  | 0 | [15 empty] | 0 |  | - | [5 empty] | #DIV/0! | [7 empty] | - | - | - | - |  | -
2 | OP2.3 Continuous learning and mentoring opportunities provided | 2.3.1 | 28 | Twinning programme, ongoing mentoring and communities of practices | Twinning Arrangement PNG |  |  |  |  | External | BOM | [7 empty] | PNG |  | 0 | DFAT | ?? |  |  | 0 | [15 empty] | 0 |  | - | [5 empty] | #DIV/0! | [7 empty] | - | - | - | - |  | -
3 | Output 3.1 Interoperable, affordable and resilient observation network progressively remediated, expanded and sustained | 3.1.7 | 75 | Revitalise and expand tide gauges | COSPPac Observations infrastructure and data support |  |  |  |  | External | COSPPac | [9 empty] | 0 | DFAT/MFAT | ?? |  |  | 0 | [15 empty] | 0 |  | - | [5 empty] | #DIV/0! | [7 empty] | - | - | - | - | . | -
4 | OP4.2 Pacific forecasting capacity expanded and maintained | 4.2.5 | 46 | Strengthen hydrological services and riverine flood forecasting | Hydrological database transition support |  |  |  |  | External | SPC | [7 empty] | - | Other Support | 347102 | SPC, WMO CREWS 3.0 | 347102 |  | DFAT | 0 | [15 empty] | 0 |  | - | [5 empty] | #DIV/0! | [5 empty] | Cancelled | Cancelled | - | - | - | - |  | SPC requested project removed from WRP and re-allocate funding re-allocated to hydrology strategy.
5 | Output 5.1 Pacific capacity and collaborative approaches to deliver locally-relevant, impact-based, inclusive and accessible forecasts and warnings for end users strengthened and sustained | 5.1.2 | 52 | Prepare impact-based, location specific warnings, based on assessments and modelling, and incorporating traditional knowledge | COSPPac Communications with and between key stakeholders and diverse communities |  |  |  |  | External | COSPPac | [9 empty] | 0 | DFAT/MFAT | ?? |  |  | 0 | [15 empty] | 0 |  | - | [5 empty] | #DIV/0! | [7 empty] | - | - | - | - | . | -
1 | Output 1.2 Sustainable hydrometerological financing facility and resource mobilisation approach established and operational | 1.2.1 | 17 | Sustainable hydrometeorological financing investment facility | Sustainable financing and resource mobilisation options | 17 | 02 | 2513 | 1702 | Major | WRP |  |  | Ofa |  |  |  |  | All | Ring-Fenced | 100000 |  |  |  | DFAT | 100000 |  |  |  |  | 50000 | 50000 | [9 empty] | 0 |  | 0% | [5 empty] | #DIV/0! | [5 empty] | Not Started | Not Started | - | - | - | - | . | -
4 | OP4.2 Pacific forecasting capacity expanded and maintained | 4.2.6 | 47 | Provide additional ICT and other technical staff to expand capacity | Hiring ICT staff for Pacific Island Country NMHSs | 47 | 01 | 2503 | 4701 | Major | Cook Islands, Fiji, Niue, Samoa, Solomon Islands, Tonga, Tuvalu |  |  | Terry |  | 2025 | [1/8/25] Missing cost from solomon islands. Honsol preparing LOAs for countries | 170000 | Cook Islands, Fiji, Niue, Samoa, Solomon Islands, Tonga, Tuvalu | Ring-Fenced | 693263.1 |  |  |  | DFAT | 693263.1 |  |  |  | 13263.1 | 170000 | 170000 | 170000 | 170000 | [6 empty] | 13263.1 | 13263.1 |  | 1.913% | [5 empty] | #DIV/0! | [5 empty] | 3 Agreement | 3 Agreement | 40% | 40% | Green | Green | Recruitment delays by beneficiary countries. | Concept note drafted. Increased budget required baesd on confirmed local salary costs. Awaiting SC approval of increase before proceeding with contracting/LOA.
3 | Output 3.1 Interoperable, affordable and resilient observation network progressively remediated, expanded and sustained | 3.1.3 | 71 | Revitalise and expand automatic and manual weather stations | SOFF infrastructure upgrade |  |  |  |  | External | SOFF | [9 empty] | 0 | SOFF | ?? |  |  | 0 | [15 empty] | 0 |  | - | [5 empty] | #DIV/0! | [7 empty] | - | - | - | - | . | -
5 | Output 5.1 Pacific capacity and collaborative approaches to deliver locally-relevant, impact-based, inclusive and accessible forecasts and warnings for end users strengthened and sustained | 5.1.6 | 56 | Install communication internet access equipment and operational costs | Plan for roll out of satellite communication, capacity development with the community, with units for selected countries | 56 | 01 |  | 5601 | Standard | WRP |  |  | Marica |  | 2025 | paused? delay? |  | - | Ring-Fenced | 116793.9904 |  |  |  | MFAT- SPREP | 116793.9904 |  |  |  | 16793.99 | 100000.0004 | [9 empty] | 16793.99 | 16793.99 |  | 14.38% | [5 empty] | #DIV/0! | [5 empty] | 1 Concept | 1 Concept | 10% | 10% | Green | Green | Cost brought forward from 2026 to 2025 | -
1 | Output 1.1 WRP governance, management and financing mechanisms established, mandated and equipped to coordinate a Pacific-led, integrated, and sustainable programme | 1.1.3 | 13 | MERL framework establishment and operationalisation | MERL Programmatic evaluations | 13 |  |  |  | Major | WRP |  |  | Ofa |  |  |  |  | All | Ring-Fenced | 75000 |  |  |  | DFAT | 75000 | [5 empty] | 75000 | [9 empty] | 0 |  | 0% | [5 empty] | #DIV/0! | [5 empty] | Not Started | Not Started | 0% | 0% | - | - | . | -
1 | Output 1.1 WRP governance, management and financing mechanisms established, mandated and equipped to coordinate a Pacific-led, integrated, and sustainable programme | 1.1.3 | 13 | MERL framework establishment and operationalisation | MERL Research | 13 |  |  |  | Major | WRP |  |  | Ofa |  |  |  |  | All | Ring-Fenced | 0 |  |  |  | DFAT | 0 | [15 empty] | 0 |  | - | [5 empty] | #DIV/0! | [5 empty] | Not Started | Not Started | 0% | 0% | - | - | . | -
3 | Output 3.1 Interoperable, affordable and resilient observation network progressively remediated, expanded and sustained | 3.1.2 | 33 | Provide asset management and maintenance staff to expand capacity (e.g. SPREP, SPC, NMHS) | Staff: SPC resource to coordinate oceans infrastructure and asset management | 33 |  |  |  | Staff | SPC | [7 empty] | All | Ring-Fenced | 0 |  |  |  | DFAT | 0 | [15 empty] | 0 |  | - | [5 empty] | #DIV/0! | [5 empty] | Not Started | Not Started | 0% | 0% | - | - | . | -
5 | Output 5.1 Pacific capacity and collaborative approaches to deliver locally-relevant, impact-based, inclusive and accessible forecasts and warnings for end users strengthened and sustained | 5.1.5 | 55 | Develop innovative approaches for dissemination of forecasts and warnings to end-users (e.g. cell broadcasting, mobile apps, social media) | GSMA cell broadcasting workshop and training | 55 |  |  |  | Standard | WRP |  |  | Ofa |  |  |  |  | Cook Island, Solomon Islands, Kiribati | Ring-Fenced | 22530.7 |  |  |  | MFAT- SPREP | 22530.7 |  |  |  | 22530.7 | [10 empty] | 22530.7 | 22530.7 |  | 100% | [5 empty] | #DIV/0! | [5 empty] | 4 Implementation In Progress | 4 Implementation In Progress | 80% | 80% | Green | Green | . | Ten representatives from the Cook Island, Solomon and Kiribati National Meteorological Services and the National Disaster Managers attended Global System for Mobile (GSM) Association (GSMA)-Pacific Islands Telecommunications Associations (PITA) Workshop on leveraging Cell-Broadcasting for Disaster Preparedness, Response and Recovery. 28-1 Aug
1 | Output 1.1 WRP governance, management and financing mechanisms established, mandated and equipped to coordinate a Pacific-led, integrated, and sustainable programme | 1.1.3 | 13 | MERL framework establishment and operationalisation | COSPPac - MERL framework, indicators and reporting has overlap and synergies with WRP. COSPPac outputs results in overall efficiency in for WRP and NMHS reporting. |  |  |  |  | External | COSPPac | [9 empty] | 0 |  |  |  |  | 0 | [15 empty] | 0 |  | - | [5 empty] | #DIV/0! | [7 empty] | - | - | - | - |  | -
1 | Output 1.1 WRP governance, management and financing mechanisms established, mandated and equipped to coordinate a Pacific-led, integrated, and sustainable programme | 1.1.2 | 12 | Operational Phase of PMU and coordination activities | COSPPac - shared travel cost for regional meetings and coordination |  |  |  |  | External | COSPPac | [9 empty] | 0 |  |  |  |  | 0 | [15 empty] | 0 |  | - | [5 empty] | #DIV/0! | [7 empty] | - | - | - | - |  | -
1 | Output 1.1 WRP governance, management and financing mechanisms established, mandated and equipped to coordinate a Pacific-led, integrated, and sustainable programme | 1.1.4 | 14 | PMU Staff (Management and Delivery Support roles) | COSPPac - shared resources in GEDSI, MERL, communications |  |  |  |  | External | COSPPac | [9 empty] | 0 |  |  |  |  | 0 | [15 empty] | 0 |  | - | [5 empty] | #DIV/0! | [7 empty] | - | - | - | - |  | -
1 | Output 1.3 Transformative GEDSI strategy adopted and integrated across governance, management and partner programming | 1.3.1 | 81 | GEDSI and social safeguards mainstreamed into WRP | COSPPac - shared resources in GEDSI, overlap in stakeholder engagement, develoment of tools and frameworks for executing staff |  |  |  |  | External | COSPPac | [9 empty] | 0 |  |  |  |  | 0 | [15 empty] | 0 |  | - | [5 empty] | #DIV/0! | [7 empty] | - | - | - | - | . | -
2 | OP2.1 WMO-designated Pacific Regional Training Centre established and sustainably managed | 2.1.1 | 21 | Establish and operate a Regional Training Centre (RTC) | Business model review for RTC and RIC | 21 |  |  |  | Major | WRP |  |  | Marica |  | 2025 | [1/8/25] Iinvestigate if extension of pooled fund consultant possible to do this work or World Bank |  | All | Ring-Fenced | 50000 |  |  |  | MFAT- SPREP | 50000 |  |  |  |  | 50000 | [10 empty] | 0 |  | 0% | [5 empty] | #DIV/0! | [5 empty] | Not Started | Not Started | 0% | 0% | - | - | Activity deferred to 2026, as awaiting FMS governance outcomes. | Identifying suitable consultant to undertake this work.
4 | Output 4.1 An integrated Pacific forecasting platform established and operating sustainably to global standards | 4.1.1 | 41 | Develop an Integrated Forecasting Platform and strengthen RSMCs (incl WIS, CAP) | AI-ML Weather Models | 41 |  | 2506 |  | Major | WRP |  |  | Terry |  |  |  |  | All | Ring-Fenced | 50000 | BoM | 30000 | Labour effort in-kind 6 months | DFAT | 20000 |  |  |  |  | 20000 | [10 empty] | 0 |  | 0% | [5 empty] | #DIV/0! | [5 empty] | Not Started | Not Started | 0% | 0% | - | - | . | -
1 | Output 1.1 WRP governance, management and financing mechanisms established, mandated and equipped to coordinate a Pacific-led, integrated, and sustainable programme | 1.1.4 | 14 | PMU Staff (Management and Delivery Support roles) | Bureau of Meteorology Technical input to WRP - PMU |  |  |  |  | External | BOM | [8 empty] | Other Support | 619825 | DFAT | 619825 | Labour effort & travel funded for 3 years at present |  | 0 | [15 empty] | 0 |  | - | [5 empty] | #DIV/0! | [7 empty] | 25% | 25% | - | - |  | -
2 | OP2.1 WMO-designated Pacific Regional Training Centre established and sustainably managed | 2.1.1 | 21 | Establish and operate a Regional Training Centre (RTC) | PIETR panel Training and capacity development roadmap development and implementation | 21 |  |  |  | Major | WRP |  |  | Terry |  |  |  | 35000 | All | Ring-Fenced | 35000 |  |  |  | DFAT | 35000 |  |  |  |  | 35000 | [10 empty] | 0 |  | 0% | [5 empty] | #DIV/0! | [5 empty] | Not Started | Not Started | 0% | 0% | - | - | . | Identified activity from PIETR panel RTC task team. Awaiting ToR finalisation and recruitment of WRP Training and Capacity Development advisor to progress.
5 | Output 5.1 Pacific capacity and collaborative approaches to deliver locally-relevant, impact-based, inclusive and accessible forecasts and warnings for end users strengthened and sustained | 5.1.5 | 55 | Develop innovative approaches for dissemination of forecasts and warnings to end-users (e.g. cell broadcasting, mobile apps, social media) | Radio system implementation for early warning dissemination | 55 |  |  |  | Major | WRP |  |  | Marica |  |  |  |  | Tokelau |  | 0 |  |  |  |  | 0 | [15 empty] | 0 |  | - | [5 empty] | #DIV/0! | [7 empty] | - | - | - | - | .
1 | Output 1.3 Transformative GEDSI strategy adopted and integrated across governance, management and partner programming | 1.3.2 | 82 | Cultivating a diverse and GEDSI responsive hydrometeorological service and warning institutions | GESDI responsive NMHS buidings and operations | 82 | [14 empty] | 0 |  |  |  |  | 0 | [15 empty] | 0 |  | - | [5 empty] | #DIV/0!
3 | Output 3.1 Interoperable, affordable and resilient observation network progressively remediated, expanded and sustained | 3.1.6 | 74 | Revitalise and expand wave buoys | Wave Buoys | 74 | [14 empty] | 0 |  |  |  |  | 0 | [15 empty] | 0 |  | - | [5 empty] | #DIV/0!
1 | Output 1.1 WRP governance, management and financing mechanisms established, mandated and equipped to coordinate a Pacific-led, integrated, and sustainable programme | 1.1.5 | 16 | NMHS Staff to expand capacity to support programme delivery | NMHS Project Delivery and MERL Staff | 16 | [14 empty] | 0 |  |  |  |  | 0 | [15 empty] | 0 |  | - | [5 empty] | #DIV/0!
4 | OP4.2 Pacific forecasting capacity expanded and maintained | 4.2.1 | 42 | Strengthen aviation forecasting | Quality management systems and Part 174 compliance uplift | 42 | [14 empty] | 0 |  |  |  |  | 0 | [15 empty] | 0 |  | - | [5 empty] | #DIV/0!
5 | Output 5.1 Pacific capacity and collaborative approaches to deliver locally-relevant, impact-based, inclusive and accessible forecasts and warnings for end users strengthened and sustained | 5.1.5 | 55 | Develop innovative approaches for dissemination of forecasts and warnings to end-users (e.g. cell broadcasting, mobile apps, social media) | Cell Broadcasting Strategy Implementation | 55 | [14 empty] | 0 |  |  |  |  | 0 | [15 empty] | 0 |  | - | [5 empty] | #DIV/0!
#N/A | #N/A | #N/A | #N/A |  |  | #N/A | [14 empty] | 0 |  |  |  |  | 0 | [15 empty] | 0 |  | - | [5 empty] | #DIV/0!
#N/A | #N/A | #N/A | #N/A |  |  | #N/A | [14 empty] | 0 |  |  |  |  | 0 | [15 empty] | 0 |  | - | [5 empty] | #DIV/0!
Note on AP1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: SPREP expenditure based on internal finance system (not executing agency spend)
Note on AQ1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: To be populated by WRP Finance Manager monthly, to a project level.
Note on AR1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: To be populated by WRP Finance Manager monthly, to a project level.
Note on AV1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: These are from the Sustainability, GESDI and ESS action plan
Note on AT2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: All these numbers in red a dummy numbers for illustration purposes only.
Note on AD3: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Previous design cost. Old MFAT contrct Reply: 187,106 previous value in error
Note on AE3: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Includes previous design cost project Reply: 420,982 previous figure in error
Note on V4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: funds transferred from M&E workshop to here.
Note on AE6: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Based on budget estimate in wiser submission Reply: Sue 3 months contract extension to be covered by UK WISER
Note on AF6: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Based on budget estimate in wiser submission
Note on AE8: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Based on budget estimate in wiser submission
Note on AF8: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Based on budget estimate in wiser submission
Note on AE9: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Based on budget estimate in wiser submission. Includes the travel cost for the PMU resources
Note on AH12: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Need 200k more to complete phase 2
Note on V13: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Agreed at PSC that this will not go ahead in this way
Note on AE18: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Unclear if budget is required or if NZMet can do this in their current funding envelop.
Note on X20: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: In kind time from Kat
Note on AE20: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: WRP MERL and Sustainability Framework Lead contract from 9 April 2025 with Completion Report submitted 29 December 2025 (i.e. 100% complete last year). Value USD 57,948 (if using a 0.58 conversion as the contract was in NZD). This included travel expenses from May last year. (From Kat)
Note on AF20: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: WRP MERL Framework Implementation Support contract from 5 December 2025, with the Completion Report submitted 7 May 2026 (100% completed). Value USD 20,486 (if using a 0.58 conversion rate). Travel expenses for the planning day were not included in this contract as they were covered by ADB directly. Note - this did not include any sustainability work. (From Kat)
Note on AE35: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Actual spend
Note on AF39: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: moved 2028 to 2026 for PMC
Note on AE43: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: removed budget as MFAT budget allocated for 2025, 2026, 2027
Note on AF43: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: removed budget as MFAT budget allocated for 2025, 2026, 2027
Note on AG43: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: removed budget as MFAT budget allocated for 2025, 2026, 2027
Note on H49: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: removed task number as funding doesn't come through WRP, it's direct from MFAT to NZmet
Note on AE53: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Add missing cost of accommodation, travel and stipend approx. USD65k
Note on AF54: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Previously budgeted AUD 150k, but updated for more accurate figures 4 ppl.
Note on AG54: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Previously budgeted AUD 150k, but updated for more accurate figures 4 ppl.
Note on AE55: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Previously had AUD50k budgeted. Updated to reflect more accurate cost and proposing every 2 years.
Note on AG55: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Previously had AUD50k budgeted. Updated to reflect more accurate cost and proposing every 2 years.
Note on AF58: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Moved $100k out of the $300k to 1.3.1 sustainable financing facility.
Note on AF62: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: updated from latest concept note from SPC - AUD$20k
Note on AE63: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: updated from latest concept note from SPC - AUD$1.2mill
Note on G65: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: over-ridden default number for readiness fund
Note on AE71: Honsol Chan Tung: Sue to utilize WISER GEDSI savings
Note on AE72: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Based on budget estimate in wiser submission. However did not add 12% on this cost, so it’s under-budgeted if SPREP charges fees on top.
Note on AF72: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Based on budget estimate in wiser submission. However did not add 12% on this cost, so it’s under-budgeted if SPREP charges fees on top.
Note on AF77: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Budgeted - 23532/1.15 - deferred recruitment of forecasting advisor as focus on other KRAs
Note on AF88: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Budgeted 62180/1.15- deferred recruitment of forecasting advisor as focus on other KRAs
Note on AF96: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: updated to AUD150k, and removed from hydrology database
Note on AF102: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Moved$100k from 3.1.1 asset management capability, plans and lifecycle cost to here.
Note on AJ106: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Kat recommended budgeting 135000 in 2030
Note on AM106: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Kat recommended budgeting 150000 in 2033
Note on AE114: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Reprioritsied budget from impact based forecasting to here.

## Work Plan
Work Plan - Projects
Project Type | (Multiple Items) | Do not change project type filter | Funding insufficient based on current projections to 2029 |  |  |  | Note: costs exclude 15% SPREP program fees
USD - priority funding gaps
[7 empty] | Year | [6 empty] | 30309325
KRA | Activity No. | Activity | Project Title | WRP Funding Source | Executing Agency | Funding Modality | 2024 Actual_ | 2025 Actual_ | 2026 Budget_ | 2027 Budget_ | 2028 Budget_ | 2029 Budget_ | Total WRP Funding Allocated USD_
1 | 1.1.1 | Establish the PMU, Operational Processes and WRP pooled fund | Branding and advertising | MFAT- SPREP | WRP | Ring-Fenced |  | 4758.23 | 20000 | 10000 |  |  | 34758.23
|  |  | Review of WRP governance and alignment with EW4All | ADB | WRP | Other Support |  | 75000 |  |  |  |  | 75000
|  |  | Revised WRP Investment plan and implementation plan aligned with EW4ALL | MFAT- SPREP | WRP | Ring-Fenced |  |  | 54069.5652 |  |  |  | 54069.5652
|  |  | Resource Mobilisation Strategy | DFAT | WRP | Ring-Fenced |  |  | 50000 |  |  |  | 50000
|  |  | Environmental and Social Safeguard Framework | DFAT | WRP | Ring-Fenced |  |  | 25000 |  |  |  | 25000 | 2000000 | (outside of currently implementaiton plan) greening and sustaining the met services infrastructure and operations
|  |  | Pooled fund - Legal and financial framework around the WRP Investment Facility | DFAT | WRP | Ring-Fenced |  | 38727 | 61273 |  |  |  | 100000
|  |  | Communication Strategy and Action Plan | DFAT | WRP | Ring-Fenced |  |  | 0 |  |  |  | 0
| 1.1.2 | Operational Phase of PMU and coordination activities | Hosting of WRP Steering Group and Liaison Platform | DFAT Inception | WRP | Ring-Fenced | 41332.18 | 0 | 50000 | 47919.3 | 100000 |  | 239251.48 | 200000
|  |  |  | MFAT- SPREP | WRP | Ring-Fenced |  | 96456.64 | 83807.8261 |  |  |  | 180264.4661
|  |  | Staff start up cost (IT, furniture) and communicating & promotion Office space and operational costs | DFAT Inception | WRP | Ring-Fenced | 21803.49 | 19310.21 | 37620 | 36400 | 36400 | 36400 | 187933.7
|  |  | ESNZ Project technical support, governance, reporting, adaptive management, communications | MFAT-NZ | ESNZ | Other Support | 160871 | 260376 | 30000 | 13406 |  |  | 464653
|  |  | PMU Travel and Workshops | DFAT Inception | WRP | Ring-Fenced | 55801.41 |  | 100000 | 80000 | 60000 |  | 295801.41 | 160000
|  |  |  | MFAT- SPREP | WRP | Ring-Fenced | 27584.2 | 27293.42 | 30000.0007 |  |  |  | 84877.6207
|  |  | NZ Met Services Technical support/ Governance/ Programme Management | MFAT-NZ | NZ Met Services | Other Support | 694231 | 193639 | 120316 |  |  |  | 1008186
|  |  | Workshops funded by UK | UK WISER | WRP | Ring-Fenced | 118130.35 | [5 empty] | 118130.35
|  |  | Staff start up cost (IT, furniture) and communicating & promotion | MFAT- SPREP | WRP | Ring-Fenced | 1508.18 | 15067.66 |  |  |  |  | 16575.84
| 1.1.3 | MERL framework establishment and operationalisation | MERL and Sustainability Frameworks | MFAT-NZ | MFAT - MERL | Other Support |  | 57948 | 20486 |  |  |  | 78434
|  |  | Regional M&E Workshop | MFAT- SPREP | WRP | Ring-Fenced | [6 empty] | 0
|  |  | MERL Programmatic evaluations | DFAT | WRP | Ring-Fenced |  |  |  | 75000 |  |  | 75000
|  |  | MERL Research | DFAT | WRP | Ring-Fenced | [6 empty] | 0 | 200000
| 1.1.4 | PMU Staff (Management and Delivery Support roles) | Staff: Programme Manager | DFAT Inception | WRP | Ring-Fenced | 91567.4 | 158387.52 | 198632 | 198632 | 198632 | 198632 | 1044482.92
|  |  | Staff: Finance Accountant | DFAT Inception | WRP | Ring-Fenced |  | 65630.49 | 149845 | 149845 | 149845 | 149845 | 665010.49
|  |  | Staff: Finance & Administration Officer | DFAT Inception | WRP | Ring-Fenced | 9778.17 | 29282.79 | 37180 | 37180 | 37180 | 37180 | 187780.96
|  |  | Staff: ESS/GEDSI Officer | DFAT Inception | WRP | Ring-Fenced |  |  | 56240.4167 | 134977 | 134977 | 134977 | 461171.4167
|  |  | Staff: Procurement and Contracts Officer | DFAT | WRP | Ring-Fenced |  | 38721.22 | 134977 | 134977 | 134977 | 134977 | 578629.22
|  |  | Staff: Communications and Knowledge Management Officer | DFAT | WRP | Ring-Fenced |  |  | 134977 | 134977 | 134977 | 134977 | 539908
|  |  | Staff: Resource Mobilisation Officer | DFAT | WRP | Ring-Fenced | [6 empty] | 0 | 539908
|  |  | Staff: WRP Secretariat and PMC Technical Support Officer | DFAT | WRP | Ring-Fenced |  |  | 52746.6667 | 126592 | 126592 | 126592 | 432522.6667
|  |  | Staff: ICT Officer | DFAT | WRP | Ring-Fenced | [6 empty] | 0 | 539908
|  |  | Staff: Monitoring , Evaluation, Research , Learning and Adaptation Officer (MERLA) | DFAT | WRP | Ring-Fenced |  |  | 89984.6667 | 134977 | 134977 | 134977 | 494915.6667
|  |  | Staff: Finance Investment Advisor | DFAT | WRP | Ring-Fenced | [6 empty] | 0
| 1.2.1 | Sustainable hydrometeorological financing investment facility | Sustainable financing and resource mobilisation options | DFAT | WRP | Ring-Fenced |  |  | 50000 | 50000 |  |  | 100000 | 500000
| 1.3.1 | GEDSI and social safeguards mainstreamed into WRP | GEDSI and Social Safeguard Specialist | UNDRR | WRP | Other Support |  | 86400 |  |  |  |  | 86400 | 100000
|  |  | Operational budget for mainstreaming GEDSI into WRP implementation2 | DFAT | WRP | Ring-Fenced |  |  |  | 5000 | 5000 | 5000 | 15000
|  |  |  | UK WISER | WRP | Ring-Fenced |  | 101815.47 | 88529.04 |  |  |  | 190344.51
| 1.3.2 | Cultivating a diverse and GEDSI responsive hydrometeorological service and warning institutions | GESDI responsive NMHS buidings and operations | (blank) | (blank) | (blank) | [6 empty] | 0
| 1.1.5 | NMHS Staff to expand capacity to support programme delivery | NMHS Project Delivery and MERL Staff | (blank) | (blank) | (blank) | [6 empty] | 0
2 | 2.1.1 | Establish and operate a Regional Training Centre (RTC) | Regional workshop to advance discussions for the establishment of the Regional Training Centre | MFAT- SPREP | WRP | Ring-Fenced |  | 64228.48 |  |  |  |  | 64228.48
|  |  | Governance framework for RTC and RIC | ADB | ADB | Other Support |  | 75000 |  |  |  |  | 75000 | 2000000 | implementation of roadmap
|  |  | Business model review for RTC and RIC | MFAT- SPREP | WRP | Ring-Fenced |  |  | 50000 |  |  |  | 50000
|  |  | PIETR panel Training and capacity development roadmap development and implementation | DFAT | WRP | Ring-Fenced |  |  | 35000 |  |  |  | 35000 | 500000
| 2.2.1 | Training of forecasters to BIP-M standard | Meteorologists Training in 2025 | MFAT-NZ | NZ Met Services | Other Support | 7195 | 202272 | 9773 |  |  |  | 219240
|  |  | Meteorologists Training | DFAT | BOM | Ring-Fenced |  |  | 180000 | 180000 |  |  | 360000
|  |  | Meteorologists Training in 2024 | DFAT | BOM | Ring-Fenced |  | 76226.37 | 63152.63 |  |  |  | 139379 | 240000
|  |  | Development of bridging and/or support for BIP-M in collaboration with RTC, USP and PIETR. | [5 empty] | 92973.75 |  |  |  | 92973.75 | 443478
| 2.2.2 | Training on specialised forecasting services, and assessment of competencies (e.g. marine, aviation, hydrology/ hydrography) | Hydrologists Training | DFAT | PAGASA | Ring-Fenced |  |  | 30000 | 80000 |  |  | 110000
| 2.2.3 | Training of observers, technicians and ICT specialists, and assessment of competencies | BIP MT Training | DFAT | WRP | Ring-Fenced |  |  | 147826.087 |  |  |  | 147826.087 | 405000
|  |  |  | MFAT- SPREP | WRP | Ring-Fenced |  | 124020.19 |  |  |  |  | 124020.19
| 2.2.4 | Establish and deliver a Pacific Meteorology Leadership Programme for mid and senior level staff | Liaison with regional institutions for the development of a Leadership Program for mid-level to senior staff level and deliver the course | MFAT- SPREP | WRP | Ring-Fenced |  |  | 135133.073 |  |  |  | 135133.073
| 2.2.5 | Specialised regional workshops and training courses | Installation and training in the common alerting protocol and Regional workshop | [5 empty] | 109824.0996 |  |  |  | 109824.0996
|  |  | ISO 9001 / QMS Training delivered at Fiji Met in partnership with Fiji National University | MFAT- SPREP | WRP | Ring-Fenced |  |  | 54069.5652 |  |  |  | 54069.5652
| 2.2.6 | Provide additional staff for training and capacity development | Staff: Support to WRP PMU Human Resource | UK WISER | WRP | Ring-Fenced |  | 17405.06 | 111947 |  |  |  | 129352.06
|  |  | Staff: Technical Adviser Capability Training | DFAT | WRP | Ring-Fenced |  |  | 95236.1667 | 163262 | 163262 | 163262 | 585022.1667
| 2.3.1 | Twinning programme, ongoing mentoring and communities of practices | Severe Weather Pilot (3 countries) - twinning and community of practice | MFAT-NZ | NZ Met Services | Other Support | 220742 | 177689 |  |  |  |  | 398431 | 1000000 | competency training at Fiji
|  |  | HydroMet Technician Training and Peer Network | MFAT-NZ | ESNZ | Other Support |  | 29488 | 45000 | 17152 |  |  | 91640
|  |  | Strengthen public weather forecasting practices, community of practice and twinning | DFAT | WRP | Ring-Fenced | [6 empty] | 0
3 | 3.1.1 | Implement observation network plans, asset management, standardised infrastructure, data management and maintenance practices | AWS and Manual Stations Observing Network Sustainability Planning and Refurbishment (part 1 - plans) | MFAT-NZ | ESNZ | Other Support |  | 255029 |  |  |  |  | 255029
|  |  | Guidance Document for Standardisation and Maintenance of Meteorological Equipment | MFAT-NZ | ESNZ | Other Support |  | 62070 | 40300 |  |  |  | 102370
|  |  | Radar Network Plan/Strategy | MFAT-NZ | NZ Met Services | Other Support | 290 | 37063 | 11947 |  |  |  | 49300
|  |  | Upper Air network plan | DFAT | WRP | Ring-Fenced |  |  |  | 10000 |  |  | 10000
|  |  | Ocean and tides network plan | DFAT | WRP | Ring-Fenced |  |  |  | 20000 |  |  | 20000
|  |  | Flood and hydrology network plan | DFAT | WRP | Ring-Fenced |  |  |  | 20000 |  |  | 20000
|  |  | ICT Network plan | DFAT | WRP | Ring-Fenced |  |  |  | 10000 |  |  | 10000
|  |  | Asset Management Information System Implementation (software & training) | DFAT | WRP | Ring-Fenced |  |  | 75000 | 125000 | 20000 | 10000 | 230000
|  |  | Establish pacific Asset Management Capability, Plans and Lifecycle Cost Forecast | DFAT | WRP | Ring-Fenced |  |  | 50000 | 150000 |  |  | 200000 | 2489000 | incl new oceans infrastrucure (wave buoys and tide gauge)
|  |  | Geohazard Network Plan | DFAT | WRP | Ring-Fenced |  |  |  | 20000 |  |  | 20000 | 126592
| 3.1.2 | Provide asset management and maintenance staff to expand capacity (e.g. SPREP, SPC, NMHS) | Staff: Technical Adviser Infrastructure & ICT | DFAT Inception | WRP | Ring-Fenced |  | 45055.95 | 163262 | 163262 | 163262 | 163262 | 698103.95
|  |  | Staff: SPC resource to coordinate oceans infrastructure and asset management | DFAT | SPC | Ring-Fenced | [6 empty] | 0
|  |  | Staff: Asset Manager | DFAT | WRP | Ring-Fenced |  |  |  | 126592 | 126592 | 126592 | 379776 | 4500000 | or another priority country
| 3.1.3 | Revitalise and expand automatic and manual weather stations | AWS and Manual Stations Observing Network Sustainability Planning and Refurbishment (part 2 - refurbishment) | MFAT-NZ | ESNZ | Other Support |  | 8975 | 940769 | 535227 |  |  | 1484971
| 3.1.5 | Establish weather watch radars | FSM Radar | DFAT | WRP | (blank) | [6 empty] | 0
|  |  | Kiribati Radar | DFAT | WRP | (blank) | [6 empty] | 0 | 2500000
|  |  | Solomon Islands Radar | MFAT-NZ | NZ Met Services | Other Support |  | 764160 | 1816614 |  |  |  | 2580774 | 1000000 | RIC and maintenance centre support and warehousing and workshop facilities at regional and national level
|  |  | Tonga Radar | MFAT-NZ | NZ Met Services | Other Support | 1906045 | 208211 | 121061 | 121061 |  |  | 2356378
|  |  | Samoa Radar | DFAT | WRP, BOM, NZMetServices | Ring-Fenced |  |  | 1995000 | 1360000 | 10000 | 10000 | 3375000 | 1000000
| 3.2.1 | Establish and operate a Regional Instrument Centre (RIC) | Training of FMS Staff to support ISO/IEC 17025 certification of RIC | MFAT- SPREP | WRP | Ring-Fenced |  |  | 50504.3478 |  |  |  | 50504.3478
| 3.1.6 | Revitalise and expand wave buoys | Wave Buoys | (blank) | (blank) | (blank) | [6 empty] | 0
4 | 4.1.1 | Develop an Integrated Forecasting Platform and strengthen RSMCs (incl WIS, CAP) | Technical partners Integrated Forecast System Workshop | MFAT- SPREP | WRP | Ring-Fenced |  |  | 26956.5217 |  |  |  | 26956.5217
|  |  | IFP Implementation and Roll Out - Progressively by country | DFAT | BOM, NZ MetServices | Ring-Fenced |  |  | 750000 | 800000 |  |  | 1550000
|  |  | Initial consultation and workshop on an integrated forecast platform and other workshops | UK WISER | WRP | Ring-Fenced | 55234.94 | [5 empty] | 55234.94
|  |  | IFP Design and ICT Architecture | DFAT | BOM, NZ MetServices | Ring-Fenced |  |  | 75000 |  |  |  | 75000 | 5000000 | Sector specific work - subject to conversations with DFAT BOM Partnership for Aviation project scope on certification of the NMHSs, additional funding for marine, tourism, energy sector engagement and warnings for both safety and economic prosperity as part of KRA5
|  |  | AI-ML Weather Models | DFAT | WRP | Ring-Fenced |  |  | 20000 |  |  |  | 20000
|  |  | Secondment of Forecasting Specialist to progress IFP, KRA 2 and 3. | DFAT | WRP | (blank) | [6 empty] | 0 | 1000000
|  |  | Peer review of IFP | DFAT | BOM, UK Met Office | Ring-Fenced |  |  | 30000 |  |  |  | 30000
| 4.2.1 | Strengthen aviation forecasting | Aviation industry workshop | DFAT | WRP | Ring-Fenced |  |  | 30000 |  |  |  | 30000
|  |  | Quality management systems and Part 174 compliance uplift | (blank) | (blank) | (blank) | [6 empty] | 0 | 680000
| 4.2.4 | Strengthen coastal inundation forecasting | Complete Lidar surveys for the Marshall Islands | DFAT | SPC | Ring-Fenced |  | 279417.63 | 478112.83 |  |  |  | 757530.46 | 520653 | additional ICT capability to support the region
|  |  | Develop Lidar strategy for the Pacific | DFAT | SPC | Ring-Fenced |  |  | 12396.5 |  |  |  | 12396.5
|  |  | Tokelau Data Collection and Inundation Forecasting | MFAT-NZ | ESNZ | Other Support |  | 21387 | 306806 | 106807 |  |  | 435000 | 675000 | including bringing in specialists to support work
| 4.2.5 | Strengthen hydrological services and riverine flood forecasting | Development of a regional strategy for hydrology | DFAT | SPC | Ring-Fenced |  | 0 | 92973.75 | 0 |  |  | 92973.75 | 100000
| 4.2.6 | Provide additional ICT and other technical staff to expand capacity | Hiring ICT staff for Pacific Island Country NMHSs | DFAT | Cook Islands, Fiji, Niue, Samoa, Solomon Islands, Tonga, Tuvalu | Ring-Fenced |  | 13263.1 | 170000 | 170000 | 170000 | 170000 | 693263.1 | 900000
|  |  | Secondment of ICT Specialist to progress IFP, KRA 2 and 3. | DFAT | BOM | Ring-Fenced |  |  | 216938.75 |  |  |  | 216938.75
| 4.2.2 | Strengthen public forecasting | Severe Weather Pilot (3 countries) - strengthen public forecasting | MFAT-NZ | NZ Met Services | Other Support | 331114 | 159336 | 107197 |  |  |  | 597647
5 | 5.1.1 | Planning for delivery of impact-based messages and warnings to end-users, considering persons with disabilities and vulnerable groups. | National consultation workshops with selected countries to review existing messages and warnings | MFAT- SPREP | WRP | Ring-Fenced |  |  |  | 20000.0007 |  |  | 20000.0007 | 500000
|  |  | Regional workshop with NDMOs, NMHS, EW4All to review existing messaging and develop plan for preparation and delivery of response-based messaging and warnings to end users | MFAT- SPREP | WRP | Ring-Fenced |  |  |  | 50000.0002 |  |  | 50000.0002
| 5.1.4 | Inclusive Community Education and Information-Exchange collectives | Translation and printing of COPE books | UK WISER | WRP | Ring-Fenced |  |  | 107587.375 |  |  |  | 107587.375 | 489786
|  |  |  | MFAT- SPREP | WRP | Ring-Fenced |  |  | 86956.5217 |  |  |  | 86956.5217
| 5.1.5 | Develop innovative approaches for dissemination of forecasts and warnings to end-users (e.g. cell broadcasting, mobile apps, social media) | GSMA cell broadcasting workshop and training | MFAT- SPREP | WRP | Ring-Fenced |  | 22530.7 |  |  |  |  | 22530.7
|  |  | Radio system implementation for early warning dissemination | (blank) | WRP | (blank) | [6 empty] | 0
|  |  | Cell Broadcasting Strategy Implementation | (blank) | (blank) | (blank) | [6 empty] | 0
| 5.1.6 | Install communication internet access equipment and operational costs | Plan for roll out of satellite communication, capacity development with the community, with units for selected countries | DFAT | Tonga, Solomon Islands, Kiribati | Ring-Fenced |  |  | 40931.14 |  |  |  | 40931.14
|  |  |  | MFAT- SPREP | WRP | Ring-Fenced |  | 16793.99 | 100000.0004 |  |  |  | 116793.9904
| 5.1.7 | Provide additional staff for warning communication and engagement to expand capacity | Staff: Technical Adviser Forecasting | DFAT | WRP | Ring-Fenced | [5 empty] | 163262 | 163262
0 | 0 | Contingency and Other | MHEWS Readiness Fund (flexi-fund) | DFAT | NMHS | Ring-Fenced |  | 11540.85 | 150000 | 150000 | 150000 | 150000 | 611540.85
#N/A | #N/A | (blank) | (blank) | (blank) | (blank) | (blank) | [6 empty] | 0
Sub Total | [6 empty] | 3743228.32 | 3939975.97 | 10901933.2902 | 5768245.3009 | 2056673 | 2049935 | 28459990.8811
0

## Change Adaptation Register
#VALUE! |  |  |  | Adaptations and Change Register
Adaptations - is when one goes beyond a receiver of knowledge and skills to be willing to apply and share (ie. transform and adapt)
Changes and adaptations across WRP will be sourced from: lessons learned, reflection sessions (PMU and executing agency led (See 10.1 MERL Plan)); executing agencies reports; WRP implementation plan and work plan)
Strategic adaptations/changes across WRP to the changing environment, context and sector are to be approved by the Steering Committee. Managerial adaptations/changes across WRP are to be approved by the WRP PMU. Operational adaptations/changes can be approved by either WRP PMU or the executing agency, depending on the change.
Please allocate one change # per adaptation/change
Change No. | Activity No. | Activity Name | Work Plan Funding New (USD '000) | Work Plan Funding Previous (USD '000) | Proposed Adaptation/ Changes (detail the proposed adaptation/change required, including what, how, who and when to achieve a more successful outcome) | Approved by | Date Approved | Date Completed | Type (Strategic; Managerial; Operational) | Priority | Status | Responsible | Adaptation Review (6-12 months after adaptation completion, Senior MERLA Officer to review and collect impact data) | Impact of Adaptation
EXPAND FOR CHANGES FROM SEP 2025.
1 | 1.1.1 | Establish the PMU, Operational Processes and WRP pooled fund | 356.0261 | no change | Simplified activity title from "Preparatory start-up work in 2024 to prepare: i. “Programme of Work” for the WRP to include revision of 2021 Decadal Programme of Investment document; ii. Implementation plan (V2) and a full risk matrix; iii. legal agreement with SPREP to host the WRP and a legal and financial framework for the WRP pooled investment fund; iv. strategy for environmental and social safeguards for the WRP (including GEDSI); and v. interim project coordination while core PMU staff are recruited." | SC | 26/9/25 |  |  |  |  | PMU
2 | 1.1.2 | Operational Phase of PMU and coordination activities | 2621.845 | 1154.2492 | Re-titled activity from "Support for PMU, travel for PMU, consultations with NMHS, PMC Panels, Liaison Committee and partners, communication activities, WRP annual steering committee meetings and support for attendance at PMC Biennial Meetings". Budget reduced and re-phased. Reallocation of funds to MERL 1.1.3 activities. Insufficient budget allocation in future years 2028 and 2029, which will need to draw on contingency or new funding. | SC | 26/9/25 |  |  |  |  | PMU
3 | 1.1.3 | MERL framework establishment and operationalisation | 132.948 | 27.0348 | New activity and cost, gap in previous implementation plan. | SC | 26/9/25 |  |  |  |  | PMU
4 | 1.1.4 | PMU Staff (Management and Delivery Support roles) | 4725.1276 | 6576 | New activity, separated to improve oversight of PMU staff costs. Reduced budget as a result of delayed recruitment of several roles and planned deferral of recruitment of Resource Mobilsation Officer and ICT Officer as a budget management initiative. | SC | 26/9/25 |  |  |  |  | PMU
5 | 1.1.5 | NMHS Staff to expand capacity to support programme delivery | 0 |  | New activity, gap in previous implementation plan | SC | 26/9/25 |  |  |  |  | PMU
6 | 1.2.1 | Sustainable hydrometeorological financing investment facility | 0 |  | New activity, introduced through approved Roadmap for sustainable financing and asset management | SC | 26/9/25 |  |  |  |  | PMU
7 | 1.3.1 | GEDSI and social safeguards mainstreamed into WRP | 220.9974 | no change | New activity, separated to improve oversight of these activities. Budgeted work plan previously approved from UK WISER and UNDRR TA. | SC | 26/9/25 |  |  |  |  | PMU
8 | 1.3.2 | Cultivating a diverse and GEDSI responsive hydrometeorological service and warning institutions | 0 |  | New activity, introduced through GESDI strategy (pending SC approval) | SC | 26/9/25 |  |  |  |  | PMU
9 | 4.1.1 | Develop an Integrated Forecasting Platform and strengthen RSMCs (incl WIS, CAP) | 2557.1915 | 330.1915 | Previously approved budget was only for 2025/26. Extended budgeted work plan out to 2028 for implementation of IFP based on Peer Review report recommendations phase 1 and 2 (US$2.425M), and to also start exploring AI ML opportunities. There is currently insufficient budget for Phase 3 and would need to look for co-funding opportunities. Previous IFP melbourne workshop funded by UK WISER is also allocated to this activity. | SC | 26/9/25 |  |  |  |  | PMU
10 | 4.2.1 | Strengthen aviation forecasting | 30 | 0 | Re-titled activity from "Strengthen aviation forecasting in aerodrome meteorological offices and meteorological watch offices, as designated in relevant International Civil Aviation Organisation regional air navigation plans." Budgeted work plan added to convene a regional aviation stakeholders workshop to improve coordination and discuss shared challenges. | SC | 26/9/25 |  |  |  |  | PMU
11 | 4.2.2 | Strengthen public forecasting | 597.647 | no change | Retitled activity from "Strengthen NMHS public forecasting and marine forecasting (recognising that marine forecasts are targeted at specific stakeholders) and establish two-way WMO information system (WIS) allowing NMHS to share their information world wide." NZ Severe Weather Forecasting Pilot project is contributes to this activity. | SC | 26/9/25 |  |  |  |  | PMU
12 | 4.2.3 | Strengthen marine forecasting | 0 |  | New activity , previously combined with 4.2.2 public forecasting | SC | 26/9/25 |  |  |  |  | PMU
13 | 4.2.4 | Strengthen coastal inundation forecasting | 1191.1865 | no change | Re-titled activity from "Implementation of coastal inundation forecasting in 5 countries including riverine flood forecasting". Previously approved Lidar strategy, Marshall Island lidar survey and Tokelau coastal inundation forecasting projects is allocated to this activity. | SC | 26/9/25 |  |  |  |  | PMU
14 | 4.2.5 | Strengthen hydrological services and riverine flood forecasting | 92.9737 | no change | New activity, previously combined with 4.2.4 coastal inundation forecasting | SC | 26/9/25 |  |  |  |  | PMU
15 | 4.2.6 | Provide additional ICT and other technical staff to expand capacity | 1066.9388 | 124 | Moved under new KRA. Re-titled activity from "Provision of additional ICT staff in each of the 14 NMHS not aligned with USA National Weather Services or Meteo France, and 2 additional ICT staff in Fiji". Increased 2025 budget from USD124k (AUD200k) to USD170k based on improved country salary estimates. Extended budgeted work plan out to 2029. | SC | 26/9/25 |  |  |  |  | PMU
16 | 5.1.1 | Planning for delivery of impact-based messages and warnings to end-users, considering persons with disabilities and vulnerable groups. | 74.5322 | no change | Simplified activity title from "Development of a detailed plan and costs for development and delivery of response based messages and warnings to end-users based on: (1) National Workshops with NMHS, NDMO, vulnerable groups and socio-economic sectors to review existing messages and warnings to end-users; and (2) Regional workshop with NDMOs, NMHS, EW4All". | SC | 26/9/25 |  |  |  |  | PMU
17 | 5.1.2 | Prepare impact-based, location specific warnings, based on assessments and modelling, and incorporating traditional knowledge | 0 | no change | Simplified activity title from "Preparation of impact-based, location specific warnings, based on assessments and modelling, and incorporating traditional knowledge and GEDSI considerations especially for the most vulnerable groups such as persons with disabilities, children in collaboration with EW4All (pillar 3) partners." | SC | 26/9/25 |  |  |  |  | PMU
18 | 5.1.3 | Deliver and continuously review impact based messaging including translation into local languages | 0 | no change | Re-titled activity from "Delivery of the impact-based messaging, translation into local languages, community engagement, mobile apps, public awareness activities including those end users with no internet. | SC | 26/9/25 |  |  |  |  | PMU
19 | 5.1.4 | Inclusive Community Education and Information-Exchange collectives | 206.7205 | no change | New activity, previously combined with 5.1.3. This provides greater visibility of community engagement and aligns with GESDI strategy. Budgeted work plan currently related to COPE book translation. | SC | 26/9/25 |  |  |  |  | PMU
20 | 5.1.5 | Develop innovative approaches for dissemination of forecasts and warnings to end-users (e.g. cell broadcasting, mobile apps, social media) | 24 |  | New activity, previously combined with 5.1.3. Budget provided to unplanned NMHS attendance of the GSMA Cell Broadcasting workshop. | SC | 26/9/25 |  |  |  |  | PMU
21 | 5.1.6 | Install communication internet access equipment and operational costs | 157.7251 | no change | Re-titled activity from "Installation of internet access equipment and operational costs of selected NMHSs and NDMO e.g. starlink" | SC | 26/9/25 |  |  |  |  | PMU
22 | 5.1.7 | Provide additional staff for warning communication and engagement to expand capacity | 163.262 | 1072 | New activity to improve visibility of investment into expanding staff capacity in the pacific. This budgeted work plan is currently for WRP Forecasting and Communications Advisor. The role was originally planned to be recruited in 2026. It is now deferred until 2029 unless additional funding becomes available to enable focus on KRA 5 and impact based forecasting. | SC | 26/9/25 |  |  |  |  | PMU
23 | 3.2.1 | Establish and operate a Regional Instrument Centre (RIC) | 50.5043 | no change | Re-phasing of planned expenditure from 2025 to 2026. | SC | 26/9/25 |  |  |  |  | PMU
24 | 3.1.1 | Implement observation network plans, asset management, standardised infrastructure, data management and maintenance practices | 976.67 | 623.699 | Re-titled activity from "Preparation of national observations network plans for country automatic weather stations; and revitalisations, upgrade and expansion of existing network of automatic weather stations in collaboration with the Systematic Observations Financing Facility". Activity has been broadened to cover all observation networks and incorporates development of regionally defined standards for all technologies (not just AWS) and implementation of the approved Sustainable Financing and Asset Management Roadmap. Extended budgeted work plan out to 2029 as a result. Previously approved only for 2025/26 was USD217k (AUD300k). Approved NZ Met Services and Earth Science project on equipment standards, radar strategy and AWS network plan has been allocated under this activity. | SC | 26/9/25 |  |  |  |  | PMU
25 | 3.1.2 | Provide asset management and maintenance staff to expand capacity (e.g. SPREP, SPC, NMHS) | 1073.6395 | 1099 | New activity to improve visbility of investment into expanding staff capacity in the pacific. Delayed recruitment of WRP Infrastructure and ICT Advisor has reduced budgeted work plan costs. New Asset Manager role added to staff plan and work plan, as part of the asset management roadmap implementation. | SC | 26/9/25 |  |  |  |  | PMU
26 | 3.1.3 | Revitalise and expand automatic and manual weather stations | 1500 | no change | New activity, previously combined with 3.1.1 | SC | 26/9/25 |  |  |  |  | PMU
27 | 3.1.4 | Revitalise and expand river gauges and rain gauges | 0 | no change | Simplified activity title from "Revitalise, upgrade and expand existing network of river gauges and rain gauges" | SC | 26/9/25 |  |  |  |  | PMU
28 | 3.1.5 | Establish weather watch radars | 6962.152 | 6406.552 | Re-titled from "Preparation of radar network plan and establishment of weather watch radar in 5 countries". Extended budgeted work plan out to complete implementation of Samoa radar. Previously approved samoa radar budget was for commencing the project only with USD 1.47M (AUD 2.37M). | SC | 26/9/25 |  |  |  |  | PMU
29 | 3.1.6 | Revitalise and expand wave buoys | 0 | no change | Simplified activity title from "Establishment of wave ride buoys and establishment of standard operating procedures" | SC | 26/9/25 |  |  |  |  | PMU
30 | 3.1.7 | Revitalise and expand tide gauges | 0 | no change | Simplified activity title from "Establishment of fixed and relocatable tide gauges" | SC | 26/9/25 |  |  |  |  | PMU
31 | 3.1.8 | Revitalise and expand Meteorological balloon launching systems | 0 | no change | Simplified activity title from "Establishment of automated meteorological ballon launching systems in 7 countries not covered by the Green Climate Fund Project" | SC | 26/9/25 |  |  |  |  | PMU
32 | 3.1.9 | Data capture from aircraft observation using the aircraft meteorological data relay system | 0 | no change |  | SC | 26/9/25 |  |  |  |  | PMU
33 | 2.1.1 | Establish and operate a Regional Training Centre (RTC) | 237.9826 | 81.0261 | Re-titled from "Establishment of a Regional Training Centre and the training of observers, technicians and IT specialists" and separated to new activity 2.2.3. Budgeted work plan increased to enable PIETR RTC task team and WRP to progress critical activities, such as development of RTC business model and capacity development roadmap. | SC | 26/9/25 |  |  |  |  | PMU
34 | 2.2.1 | Training of forecasters to BIP-M standard | 811.5928 | 510.64 | Increased budget based on improved cost estimates for BIP-M training, living costs, tutoring and support. Extended budgeted work plan an additional year to 2027. No further budget allocated yet beyond 2027. | SC | 26/9/25 |  |  |  |  | PMU
35 | 2.2.2 | Training on specialised forecasting services, and assessment of competencies (e.g. marine, aviation, hydrology/ hydrography) | 160 | 124 | Re-titled and expanded activity from "Provision of diploma and postgraduate certificate training in hydrography and hydrology, and training course on marine meteorological services and assessment of marine competencies". This is to recognise the need for specialised competency based training across all services and disciplines, not only hydrology and marine. This is in addition to BIP-M basic training. Budgeted work plan has been increased for hydrology training for 2025 and 2027. | SC | 26/9/25 |  |  |  |  | PMU
36 | 2.2.3 | Training of observers, technicians and ICT specialists, and assessment of competencies | 295.6522 | 124.0202 | New activity, previously combined with 2.1.1 Establishment of RTC. Budgeted work plan extended for BIP-MT training to 2027. No further budget allocated yet beyond 2027. | SC | 26/9/25 |  |  |  |  | PMU
37 | 2.2.4 | Establish and deliver a Pacific Meteorology Leadership Programme for mid and senior level staff | 135.1739 | no change |  | SC | 26/9/25 |  |  |  |  | PMU
38 | 2.2.5 | Specialised regional workshops and training courses | 207.4552 | no change |  | SC | 26/9/25 |  |  |  |  | PMU
39 | 2.2.6 | Provide additional staff for training and capacity development | 741.5939 | no change | New activity to improve visibility of investment into expanding staff capacity in the pacific. Delayed recruitment of WRP Training and Capacity Development Advisor may require re-phasing or reallocation of budget from UK WISER. | SC | 26/9/25 |  |  |  |  | PMU
40 | 2.3.1 | Twinning programme, ongoing mentoring and communities of practices | 490.071 | no change | Re-titled activity from "Twinning programme with BOM, NZ Met Services, NIWA and NOAA to provide ongoing mentoring to NMHS" | SC | 26/9/25 |  |  |  |  | PMU
41 | NA | Contingency and Other | 750 | 93 | MHEWS Readiness Fund (flexi-fund) allocated here under "Contingency and Other" until concepts are finalised and budget will be reallocated to appropriate KRA. Increased 2025 budget of USD10k per country. Extended budgets out to 2029. | SC | 26/9/25 |  |  |  |  | PMU
42 | 1.1.1 | Establish the PMU, Operational Processes and WRP pooled fund | 338.8278 | 356.0261 | Unused funds from 2025 redistributed. Communication strategy done in-house so $50k funding was reallocated. Including additional $27k funds allocated to Branding and Advertising to support implementation of communication strategy. Corrections in actual budgets from ESNZ cause of the main decrease. | SC | 2026-02-06 |  |  |  |  | PMU
43 | 1.1.2 | Operational Phase of PMU and coordination activities | 2595.6739 | 2621.845 | Unused funds from 2025 redistributed. Addtiional $112k funding allocated to WRP SC and Liaison Platform to cover expected costs. $45k added to staff start up costs. | SC | 2026-02-06 |  |  |  |  | PMU
44 | 1.1.3 | MERL framework establishment and operationalisation | 153.434 | 132.948 | MFAT provided additional $20k in 2026 towards MERL implemenation. | SC | 2026-02-06 |  |  |  |  | PMU
45 | 1.1.4 | PMU Staff (Management and Delivery Support roles) | 4404.4213 | 4725.1276 | Savings made as a result of delayed/deferred recruitment. PMU roles are budgeted higher which acts as a contingency for the program - unused funds from 2025 redistributed. | SC | 2026-02-06 |  |  |  |  | PMU
46 | 1.1.5 | NMHS Staff to expand capacity to support programme delivery | 0 | 0 |  | SC | 2026-02-06 |  |  |  |  | PMU
48 | 1.2.1 | Sustainable hydrometeorological financing investment facility | 100 | 0 | Allocation of $100k funding to start investigation on a financing facility (if world bank is not able to provide TA support). | SC | 2026-02-06 |  |  |  |  | PMU
50 | 1.3.1 | GEDSI and social safeguards mainstreamed into WRP | 291.7445 | 220.9974 | Additional $71k budget allocated to support mainstreaming GEDSI into WRP implementation from 2026 out to 2029. This is to help cover disability accomodations in events and workshops venues per feedback from DFAT in IDS. | SC | 2026-02-06 |  |  |  |  | PMU
51 | 1.3.2 | Cultivating a diverse and GEDSI responsive hydrometeorological service and warning institutions | 0 | 0 |  | SC | 2026-02-06 |  |  |  |  | PMU
54 | 4.1.1 | Develop an Integrated Forecasting Platform and strengthen RSMCs (incl WIS, CAP) | 1757.1915 | 2557.1915 | $800k funds originally provisioned for 2028 has been reallocated to Samoa radar in order to fully fund the radar activities in 2026 and 2027 (SC approved out-of-session). Required for IFP in future will be determined as the IFP design is completed and ICT gaps confirmed. | SC | 2026-02-06 |  |  |  |  | PMU
56 | 4.2.1 | Strengthen aviation forecasting | 30 | 30 |  | SC | 2026-02-06 |  |  |  |  | PMU
57 | 4.2.2 | Strengthen public forecasting | 597.647 | 597.647 |  | SC | 2026-02-06 |  |  |  |  | PMU
58 | 4.2.3 | Strengthen marine forecasting | 0 | 0 |  | SC | 2026-02-06 |  |  |  |  | PMU
59 | 4.2.4 | Strengthen coastal inundation forecasting | 1204.927 | 1191.1865 | Minor budget adjustments to cover cost of Lidar surveys for Marshall Islands. | SC | 2026-02-06 |  |  |  |  | PMU
60 | 4.2.5 | Strengthen hydrological services and riverine flood forecasting | 92.9737 | 92.9737 |  | SC | 2026-02-06 |  |  |  |  | PMU
61 | 4.2.6 | Provide additional ICT and other technical staff to expand capacity | 910.2018 | 1066.9388 | Budget savings/reduction due to delayed recruitment by countries on ICT staff. | SC | 2026-02-06 |  |  |  |  | PMU
64 | 5.1.1 | Planning for delivery of impact-based messages and warnings to end-users, considering persons with disabilities and vulnerable groups. | 70 | 74.5322 | Minor budget adjustments for rounding. | SC | 2026-02-06 |  |  |  |  | PMU
65 | 5.1.2 | Prepare impact-based, location specific warnings, based on assessments and modelling, and incorporating traditional knowledge | 0 | 0 |  | SC | 2026-02-06 |  |  |  |  | PMU
66 | 5.1.3 | Deliver and continuously review impact based messaging including translation into local languages | 0 | 0 |  | SC | 2026-02-06 |  |  |  |  | PMU
67 | 5.1.4 | Inclusive Community Education and Information-Exchange collectives | 194.5439 | 206.7205 | Minor budget adjustments to reflect actual cost of COPE book translation and launch for Niue and Tokelau. | SC | 2026-02-06 |  |  |  |  | PMU
68 | 5.1.5 | Develop innovative approaches for dissemination of forecasts and warnings to end-users (e.g. cell broadcasting, mobile apps, social media) | 22.5307 | 24 | Minor budget adjustments for rounding. | SC | 2026-02-06 |  |  |  |  | PMU
69 | 5.1.6 | Install communication internet access equipment and operational costs | 157.7251 | 157.7251 | No change to total. Redistribution of cost to later years due to underspend in 2025. | SC | 2026-02-06 |  |  |  |  | PMU
70 | 5.1.7 | Provide additional staff for warning communication and engagement to expand capacity | 163.262 | 163.262 |  | SC | 2026-02-06 |  |  |  |  | PMU
73 | 3.2.1 | Establish and operate a Regional Instrument Centre (RIC) | 50.5043 | 50.5043 |  | SC | 2026-02-06 |  |  |  |  | PMU
75 | 3.1.1 | Implement observation network plans, asset management, standardised infrastructure, data management and maintenance practices | 916.699 | 976.67 | $100k fund reallocated from here to 1.3.1 sustainable financing investment facility (in the event that World Bank is not able to provide TA support). Reforecasted expenditure for 2026 to 2027 for development of asset plans, network plans and asset information system. $20k budget allocated towards development of Geohazard network asset plan/strategy. | SC | 2026-02-06 |  |  |  |  | PMU
77 | 3.1.2 | Provide asset management and maintenance staff to expand capacity (e.g. SPREP, SPC, NMHS) | 1077.88 | 1073.6395 | Minor budget adjustments for rounding. | SC | 2026-02-06 |  |  |  |  | PMU
78 | 3.1.3 | Revitalise and expand automatic and manual weather stations | 1484.971 | 1500 |  | SC | 2026-02-06 |  |  |  |  | PMU
79 | 3.1.4 | Revitalise and expand river gauges and rain gauges | 0 | 0 |  | SC | 2026-02-06 |  |  |  |  | PMU
80 | 3.1.5 | Establish weather watch radars | 8312.152 | 6962.152 | Increased budget by $1350k to cover cost of the Samoa radar in 2027 capital cost. | SC | 2026-02-06 |  |  |  |  | PMU
81 | 3.1.6 | Revitalise and expand wave buoys | 0 | 0 |  | SC | 2026-02-06 |  |  |  |  | PMU
82 | 3.1.7 | Revitalise and expand tide gauges | 0 | 0 |  | SC | 2026-02-06 |  |  |  |  | PMU
83 | 3.1.8 | Revitalise and expand Meteorological balloon launching systems | 0 | 0 |  | SC | 2026-02-06 |  |  |  |  | PMU
84 | 3.1.9 | Data capture from aircraft observation using the aircraft meteorological data relay system | 0 | 0 |  | SC | 2026-02-06 |  |  |  |  | PMU
87 | 2.1.1 | Establish and operate a Regional Training Centre (RTC) | 224.2285 | 237.9826 | Minor budget adjustments to reflect actual cost of regional workshop and business model review for RTC and RIC. | SC | 2026-02-06 |  |  |  |  | PMU
89 | 2.2.1 | Training of forecasters to BIP-M standard | 811.5928 | 811.5928 |  | SC | 2026-02-06 |  |  |  |  | PMU
90 | 2.2.2 | Training on specialised forecasting services, and assessment of competencies (e.g. marine, aviation, hydrology/ hydrography) | 110 | 160 | Cost of Hydrologist training (BIP-H) in Pagasa lower than forecasted. Budget reduction by $50k. | SC | 2026-02-06 |  |  |  |  | PMU
91 | 2.2.3 | Training of observers, technicians and ICT specialists, and assessment of competencies | 271.8463 | 295.6522 | Unused funds from 2025 redistributed. Cost of BIP MT training $24k lower than forecasted. | SC | 2026-02-06 |  |  |  |  | PMU
92 | 2.2.4 | Establish and deliver a Pacific Meteorology Leadership Programme for mid and senior level staff | 135.1331 | 135.1739 |  | SC | 2026-02-06 |  |  |  |  | PMU
93 | 2.2.5 | Specialised regional workshops and training courses | 163.8937 | 207.4552 | Unused funds from 2025 redistributed. Cost of CAP training $43k lower than forecasted. | SC | 2026-02-06 |  |  |  |  | PMU
94 | 2.2.6 | Provide additional staff for training and capacity development | 714.3742 | 741.5939 | Budget savings/reduction due to delayed recruitment of PMU Training and Capacity Development Advisor. | SC | 2026-02-06 |  |  |  |  | PMU
96 | 2.3.1 | Twinning programme, ongoing mentoring and communities of practices | 490.071 | 490.071 |  | SC | 2026-02-06 |  |  |  |  | PMU
103 | 0 | Contingency and Other | 611.5408 | 750 | Underspend by countries Readiness Fund/Flexi-fund in 2025 has been reallocated. Resulting in overall reduction in funding by $138k. | SC | 2026-02-06 |  |  |  |  | PMU
104 | 0 | GRAND TOTAL (excl. SPREP program fees) | 28459.9909 | 28611.6087 | Minor increase in total committed funding from MFAT to cover consultant cost for MERL implementation in 2026. Corrections in actual budgets from ESNZ cause of main decrease. | SC | 2026-02-06 |  |  |  |  | PMU

## Implementation Plan V2 Sep25 (hidden)
KRA |  |  |  |  | Activity | Inception USD 2024 - 2025 | Phase 1 USD 2024 - 2029 | Indicative Cost USD '000 2024 - 2033 | Funds Raised | Total Funding Raised USD | Work Plan Funding USD '000 2024 - 2029 |  | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | COSPPac | Adele | NIWA Earth Science
KRA 1 GOVERNANCE, MANAGEMENT AND COORDINATION | [5 empty] | 2340000 | 10150000 | 20310 |  |  | 8056.9441 |  | 1523.4842 | 1307.3734 | 1537.3846 | 1351.588 | 1198.557 | 1138.557
Output 1.1 WRP governance, management and financing mechanisms established, mandated and equipped to coordinate a Pacific-led, integrated, and sustainable programme
1 |  | Output 1.1 WRP governance, management and financing mechanisms established, mandated and equipped to coordinate a Pacific-led, integrated, and sustainable programme | 11 | 1.1.1 | Establish the PMU, Operational Processes and WRP pooled fund | 550000 | 550000 | 550 |  |  | 356.0261 |  | 0 | 256.0261 | 100 | 0 | 0 | 0 | **ESS??
1 |  | Output 1.1 WRP governance, management and financing mechanisms established, mandated and equipped to coordinate a Pacific-led, integrated, and sustainable programme | 12 | 1.1.2 | Operational Phase of PMU and coordination activities | 300000 | 880000 | 1470 |  |  | 2621.845 |  | 1441.448 | 344.0985 | 379.0675 | 224.431 | 146.4 | 86.4 | COSPPac - shared travel cost for meetings and coordination
1 |  | Output 1.1 WRP governance, management and financing mechanisms established, mandated and equipped to coordinate a Pacific-led, integrated, and sustainable programme | 13 | 1.1.3 | MERL framework establishment and operationalisation | incl above | incl above | incl above |  |  | 132.948 |  | 0 | 57.948 | 0 | 75 | 0 | 0 | COSPPac - overlap in the MERL reporting and indicators, coordination efficiency for sustainability and broader alignment with other pacific and national reporting of the NMHSs
1 |  | Output 1.1 WRP governance, management and financing mechanisms established, mandated and equipped to coordinate a Pacific-led, integrated, and sustainable programme | 14 | 1.1.4 | PMU Staff (Management and Delivery Support roles) | 1490000 | 8720000 | 18290 |  |  | 4725.1276 |  | 82.0362 | 434.4634 | 1052.157 | 1052.157 | 1052.157 | 1052.157 | COSPPac - shared resources in GEDSI, MERL, communications
1 |  | Output 1.1 WRP governance, management and financing mechanisms established, mandated and equipped to coordinate a Pacific-led, integrated, and sustainable programme | 16 | 1.1.5 | NMHS Staff to expand capacity to support programme delivery | new | new | new |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | COSPPac - shared resources in GEDSI, overlap in stakeholder engagement, develoment of tools and frameworks for executing staff
1 | Output 1.2 Sustainable hydrometerological financing facility and resource mobilisation approach established and operational
1 |  | Output 1.2 Sustainable hydrometerological financing facility and resource mobilisation approach established and operational | 17 | 1.2.1 | Sustainable hydrometeorological financing investment facility | new | new | new |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
1 | Output 1.3 Transformative GEDSI strategy adopted and integrated across governance, management and partner programming
1 |  | Output 1.3 Transformative GEDSI strategy adopted and integrated across governance, management and partner programming | 81 | 1.3.1 | GEDSI and social safeguards mainstreamed into WRP | incl above | incl above | incl above |  |  | 220.9974 |  | 0 | 214.8374 | 6.1601 | 0 | 0 | 0 | COSPPac - shared resources in GEDSI, overlap in stakeholder engagement, develoment of tools and frameworks for executing staff
1 |  | Output 1.3 Transformative GEDSI strategy adopted and integrated across governance, management and partner programming | 82 | 1.3.2 | Cultivating a diverse and GEDSI responsive hydrometeorological service and warning institutions | new | new | new |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
KRA 4 FORECAST AND WARNING PRODUCTION (previously KRA 2) | [5 empty] | 300000 | 9000000 | 45760 |  |  | 5535.9375 |  | 386.3489 | 1550.4873 | 1416.8913 | 1042.21 | 970 | 170
Output 4.1 An integrated Pacific forecasting platform established and operating sustainably to global standards
4 |  | Output 4.1 An integrated Pacific forecasting platform established and operating sustainably to global standards | 41 | 4.1.1 | Develop an Integrated Forecasting Platform and strengthen RSMCs (incl WIS, CAP) | 100000 | 1000000 | 18220 |  |  | 2557.1915 |  | 55.2349 | 105 | 796.9565 | 800 | 800 | 0 | **check where NZ met obs are coming from. COSPPac - CLiDE database to automatically transfer data to WIS2 (but only hourly obs). Maybe a small subset of AWS not feeding into CLiDE yet (e.g. aviation)
1 | OP4.2 Pacific forecasting capacity expanded and maintained
4 |  | OP4.2 Pacific forecasting capacity expanded and maintained | 42 | 4.2.1 | Strengthen aviation forecasting |  |  | 1980 |  |  | 30 |  | 0 | 0 | 30 | 0 | 0 | 0 | COSPPac- CLiDE have the ability to support METAR and SPECI. Some met services use it to enter manual data and produce the message automatically and provides first pass QC. This is beneficial before going into WIS2.
4 |  | OP4.2 Pacific forecasting capacity expanded and maintained | 43 | 4.2.2 | Strengthen public forecasting |  |  | 6930 |  |  | 597.647 |  | 331.114 | 266.533 | 0 | 0 | 0 | 0
4 |  | OP4.2 Pacific forecasting capacity expanded and maintained | 44 | 4.2.3 | Strengthen marine forecasting |  |  | incl above |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | COSPPac - expanding fixed marine obs (ingesting ocean buoys and tide guages). Some tide gauge data but issues with ingesting near real-time currently and working to resolve with the tidal centre.
4 |  | OP4.2 Pacific forecasting capacity expanded and maintained | 45 | 4.2.4 | Strengthen coastal inundation forecasting | 200000 | 4900000 | 12250 |  |  | 1191.1865 |  | 0 | 965.5665 | 153.41 | 72.21 | 0 | 0 | COSPPac - SPC oceans portal has weather usages with 7 days forecast (based on bureau dataset), tide predictions from Bureau and calendar production and distribution. Conversations of potential transition to SPC on tide prediction and Andy Taylor. Tokelau 3 tide gauges. |  | Output 1. Coastal Datal Collection and Inundation Forecasting in Tokelau
4 |  | OP4.2 Pacific forecasting capacity expanded and maintained | 46 | 4.2.5 | Strengthen hydrological services and riverine flood forecasting |  | incl above | incl above |  |  | 92.9737 |  | 0 | 0 | 92.9737 | 0 | 0 | 0 | COSPPac - rainfall data from NMHSs going into CLiDE and there is an API. It would be valuable to ingest historical data as data rescue activity. No ability to ingest water level station data. Need to think how to better safeguard CLiDE.
4 |  | OP4.2 Pacific forecasting capacity expanded and maintained | 47 | 4.2.6 | Provide additional ICT and other technical staff to expand capacity | - | 3100000 | 6380 |  |  | 1066.9388 |  | 0 | 213.3878 | 343.551 | 170 | 170 | 170 | COSPPac - funding SPREP IT staff (1FTE), SPC (1FTE), NIWA and Bureau to build ICT capability within NMHSs. There is also allocated additional funding for ICT services focussed on climate and ocean products and services (not directly met).
KRA 5 COMMUNICATION AND DELIVERY OF FORECASTS AND WARNINGS TO END USERS (previously KRA 3) | [5 empty] | 860000 | 2560000 | 9520 |  |  | 626.2398 |  | 0 | 178.5658 | 209.8798 | 74.5322 | 0 | 163.262
Output 5.1 Pacific capacity and collaborative approaches to deliver locally-relevant, impact-based, inclusive and accessible forecasts and warnings for end users strengthened and sustained
5 |  | Output 5.1 Pacific capacity and collaborative approaches to deliver locally-relevant, impact-based, inclusive and accessible forecasts and warnings for end users strengthened and sustained | 51 | 5.1.1 | Planning for delivery of impact-based messages and warnings to end-users, considering persons with disabilities and vulnerable groups. | 710000 | 660000 | 660 |  |  | 74.5322 |  | 0 | 0 | 0 | 74.5322 | 0 | 0 | COSPPac - climate time scale impact based forecasting for climate sensitive sectors. UNEP - additionally funding for 2 countries further focussed at national level (cook is, tuvalu)
5 |  | Output 5.1 Pacific capacity and collaborative approaches to deliver locally-relevant, impact-based, inclusive and accessible forecasts and warnings for end users strengthened and sustained | 52 | 5.1.2 | Prepare impact-based, location specific warnings, based on assessments and modelling, and incorporating traditional knowledge |  | 1000000 | 3930 |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | COSPPac - collating traditional knowedge and data rescue mangement and a database and procedures in SPREP. Most of the data is weather TK. Funding SPREP TK advisor who runs workshops in country assisting the NMHSs to collect data. SPREP IT funded to maintain database (built by Bureau and transitioned)
5 |  | Output 5.1 Pacific capacity and collaborative approaches to deliver locally-relevant, impact-based, inclusive and accessible forecasts and warnings for end users strengthened and sustained | 53 | 5.1.3 | Deliver and continuously review impact based messaging including translation into local languages |  | 400000 | 4430 |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | COSPPac - support NMHSs for translation framework of climate bulletins into local languages where possible.
5 |  | Output 5.1 Pacific capacity and collaborative approaches to deliver locally-relevant, impact-based, inclusive and accessible forecasts and warnings for end users strengthened and sustained | 54 | 5.1.4 | Inclusive Community Education and Information-Exchange collectives | 50000 | incl above | incl above |  |  | 206.7205 |  | 0 | 104.9798 | 101.7407 | 0 | 0 | 0 | COSPPac - supports NCOF. Bureau, SPC, SPREP funded staff is supporting NMHSs promote climate bulletins/products and services at a community level. COSPPac also actively developing that two-way network, referred to as knowledge brokering. Significant improvement needed in this space. Questions often arise from comunity on weather servies which can't be addressed by COSPPac. e.g. National climate outlook forum along side a National Weather outlook forum.
5 |  | Output 5.1 Pacific capacity and collaborative approaches to deliver locally-relevant, impact-based, inclusive and accessible forecasts and warnings for end users strengthened and sustained | 55 | 5.1.5 | Develop innovative approaches for dissemination of forecasts and warnings to end-users (e.g. cell broadcasting, mobile apps, social media) |  | incl above | incl above |  |  | 24 |  | 0 | 24 | 0 | 0 | 0 | 0 | COSPPac - supports NMHSs in communicating via social media, radio, and traditional media. SPC has a tide's app for the region with national level info and tide predictions at national level. It has sunrise, sunset etc.
5 |  | Output 5.1 Pacific capacity and collaborative approaches to deliver locally-relevant, impact-based, inclusive and accessible forecasts and warnings for end users strengthened and sustained | 56 | 5.1.6 | Install communication internet access equipment and operational costs | 100000 | 500000 | 500 |  |  | 157.7251 |  | 0 | 49.586 | 108.1391 | 0 | 0 | 0 | COSPPac - Flexi-fund is contributing to this with comms/starlink. Celine? Used to pay tuvalu internet services. Gap infrastructure to connect to government communication link, which may negate the need for ongoing satellite communication cost. (WRP could contribute??)
5 |  | Output 5.1 Pacific capacity and collaborative approaches to deliver locally-relevant, impact-based, inclusive and accessible forecasts and warnings for end users strengthened and sustained | 57 | 5.1.7 | Provide additional staff for warning communication and engagement to expand capacity | new | new | new |  |  | 163.262 |  | 0 | 0 | 0 | 0 | 0 | 163.262 | COSPPac - approx. 10 officers in NMHSs for science communications 2 years $1.2Mill and flexi-fund may also contribute. They develop communication plans and map stakeholders, to tailor and improve operatinoal products to community. Implement engagement activities with the community. These roles may be supporting weather information delivery.
KRA 3 OBSERVATION NETWORK INFRASTRUCTURE (previously KRA 4) | [5 empty] | 3550000 | 9880000 | 89160 |  |  | 10562.9658 |  | 1906.335 | 766.5455 | 6142.4883 | 1127.889 | 309.854 | 309.854
Output 3.2 WMO-designated Pacific Regional Instrument Centre established and sustainably managed
3 |  | Output 3.2 WMO-designated Pacific Regional Instrument Centre established and sustainably managed | 31 | 3.2.1 | Establish and operate a Regional Instrument Centre (RIC) |  | 1860000 | 1860 |  |  | 50.5043 |  | 0 | 0 | 50.5043 | 0 | 0 | 0 | COPPac - SPC barometers sent to fiji met. Sea level calibration is dependent on Bureau metrology lab. Jeff is trying to test if longer calibration time can be acceptable. Lots of import duties.
Output 3.1 Interoperable, affordable and resilient observation network progressively remediated, expanded and sustained
3 |  | Output 3.1 Interoperable, affordable and resilient observation network progressively remediated, expanded and sustained | 32 | 3.1.1 | Implement observation network plans, asset management, standardised infrastructure, data management and maintenance practices | 1050000 | 1000000 | 1000 |  |  | 976.67 |  | 0.29 | 385.669 | 460.711 | 110 | 10 | 10 | COSPPac - $120k asset managemen system for sea leve assets from asset miantenance perspective only. Metadata needs to be consistent in CLiDE. Contributed to PMC paper to identify priority stations for high quality surface network stations. Pacific sea level stations are captured in the Bureau asset mangaement plan for sea level. SPC may not have costs, as Bureau procurement. COSPPac will work with NIWA and WRP to standard maintenance regimes. |  | Output 3. Development of a Guidance Document for Standardisation and Maintenance of Meteorological Equipment
|  | Output 3.1 Interoperable, affordable and resilient observation network progressively remediated, expanded and sustained | [18 empty] | Output 2. AWS and Manual Station Observation Network Sustainability Planning and Refurbishment (Network Plan)
3 |  | Output 3.1 Interoperable, affordable and resilient observation network progressively remediated, expanded and sustained | 33 | 3.1.2 | Provide asset management and maintenance staff to expand capacity (e.g. SPREP, SPC, NMHS) |  | 220000 | 470 |  |  | 1073.6395 |  | 0 | 40.8155 | 163.262 | 289.854 | 289.854 | 289.854 | COSPPac - funding staff in BOM (2 FTE), SPC (2 FTE). SPC coordinates 6 monthly maintenance plan for the sea level. Bureau purchases directly any consumables for NMHSs and Land survey departments for repairs and maintenance purposes (e.g. tools, safety equipment etc). |  | Output Support. Technical Assistance
3 |  | Output 3.1 Interoperable, affordable and resilient observation network progressively remediated, expanded and sustained | 71 | 3.1.3 | Revitalise and expand automatic and manual weather stations |  | 2000000 | 11340 |  |  | 1500 |  | 0 | 0 | 1000 | 500 | 0 | 0 |  |  | Output 2. AWS and Manual Station Observation Network Sustainability Planning and Refurbishment (Refurbishment AWS MWS)
3 |  | Output 3.1 Interoperable, affordable and resilient observation network progressively remediated, expanded and sustained | 72 | 3.1.4 | Revitalise and expand river gauges and rain gauges |  |  | 8050 |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | COSPPac - no river guages data stored in CLiDE, but rain is and in theory can ingest other rainfall data from other pacific agencies. |  | Output 2. Station Observation Network Sustainability Planning and Refurbishment
3 |  | Output 3.1 Interoperable, affordable and resilient observation network progressively remediated, expanded and sustained | 73 | 3.1.5 | Establish weather watch radars | 2500000 | 2500000 | 11650 |  |  | 6962.152 |  | 1906.045 | 340.061 | 4468.011 | 228.035 | 10 | 10 | COSPPac - no radar data stored in CLiDE
3 |  | Output 3.1 Interoperable, affordable and resilient observation network progressively remediated, expanded and sustained | 74 | 3.1.6 | Revitalise and expand wave buoys |  | 2300000 | 19750 |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | COSPPac - no formal deliverables other than SPC technical resources funded
3 |  | Output 3.1 Interoperable, affordable and resilient observation network progressively remediated, expanded and sustained | 75 | 3.1.7 | Revitalise and expand tide gauges |  |  | 13930 |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | COSPPac - 14 guages maintains, SPC planning to deploy 2 more. Tokelau tide gauges.
3 |  | Output 3.1 Interoperable, affordable and resilient observation network progressively remediated, expanded and sustained | 76 | 3.1.8 | Revitalise and expand Meteorological balloon launching systems |  |  | 20520 |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | COSPPac - ability to store in CLiDE, but not done for a long time. There historical data in various places not archived in CLiDE. Unclear where the Fiji stores/archives and sends this data.
3 |  | Output 3.1 Interoperable, affordable and resilient observation network progressively remediated, expanded and sustained | 77 | 3.1.9 | Data capture from aircraft observation using the aircraft meteorological data relay system |  |  | 590 |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | COSPPac - no AMDAR data stored in CLiDE
KRA 2 PEOPLE CAPABILITY (previously KRA 5 Training and Capacity) | [5 empty] | 330000 | 5480000 | 20640 |  |  | 3079.5215 |  | 227.937 | 1288.1082 | 813.6903 | 423.262 | 163.262 | 163.262
OP2.1 WMO-designated Pacific Regional Training Centre established and sustainably managed
2 |  | OP2.1 WMO-designated Pacific Regional Training Centre established and sustainably managed | 21 | 2.1.1 | Establish and operate a Regional Training Centre (RTC) | 20000 | 920000 | 920 |  |  | 237.9826 |  | 0 | 202.9826 | 35 | 0 | 0 | 0 | COSPPac - training content to contribute (data mangement CLiDE, tide gauge maintenance, SPC ocean science, climate science) |  | Output 4. HydroMet Training, Resources and Community of Practice
OP2.2 Inclusive leadership and technical capability strengthening programmes established and delivering ongoing training to industry standards
2 |  | OP2.2 Inclusive leadership and technical capability strengthening programmes established and delivering ongoing training to industry standards | 22 | 2.2.1 | Training of forecasters to BIP-M standard | 110000 | 1350000 | 2700 |  |  | 811.5928 |  | 7.195 | 351.424 | 272.9737 | 180 | 0 | 0
2 |  | OP2.2 Inclusive leadership and technical capability strengthening programmes established and delivering ongoing training to industry standards | 23 | 2.2.2 | Training on specialised forecasting services, and assessment of competencies (e.g. marine, aviation, hydrology/ hydrography) |  |  | 2440 |  |  | 160 |  | 0 | 80 | 0 | 80 | 0 | 0
2 |  | OP2.2 Inclusive leadership and technical capability strengthening programmes established and delivering ongoing training to industry standards | 24 | 2.2.3 | Training of observers, technicians and ICT specialists, and assessment of competencies |  | 480000 | 3240 |  |  | 295.6522 |  | 0 | 147.8261 | 147.8261 | 0 | 0 | 0 |  |  | Output 4. HydroMet Community of Practice
2 |  | OP2.2 Inclusive leadership and technical capability strengthening programmes established and delivering ongoing training to industry standards | 25 | 2.2.4 | Establish and deliver a Pacific Meteorology Leadership Programme for mid and senior level staff |  | 600000 | 1040 |  |  | 135.1739 |  | 0 | 0 | 135.1739 | 0 | 0 | 0
2 |  | OP2.2 Inclusive leadership and technical capability strengthening programmes established and delivering ongoing training to industry standards | 26 | 2.2.5 | Specialised regional workshops and training courses | 200000 | 2130000 | 9330 |  |  | 207.4552 |  | 0 | 150.3056 | 57.1496 | 0 | 0 | 0 | COSPPac - partnership with SPC and SPREP in communication capacity development of NMHSs (forecast communication, climate drivers, social media, channels, talking points). Traditional knowledge training.
2 |  | OP2.2 Inclusive leadership and technical capability strengthening programmes established and delivering ongoing training to industry standards | 27 | 2.2.6 | Provide additional staff for training and capacity development | new | new | new |  |  | 741.5939 |  | 0 | 86.2409 | 165.567 | 163.262 | 163.262 | 163.262 | COSPPac - capacity development role contribute to PIETR panel and the RTC task team.
OP2.3 Continuous learning and mentoring opportunities provided
2 |  | OP2.3 Continuous learning and mentoring opportunities provided | 28 | 2.3.1 | Twinning programme, ongoing mentoring and communities of practices |  |  | 970 |  |  | 490.071 |  | 220.742 | 269.329 | 0 | 0 | 0 | 0 | COSPPac - on the job training NMHSs and LSDs for tide gauge network (GNSS network). Trained to C1 for NMHSs and C2 for SPC technicians, based on Bureau competency framework. |  | Output 4. HydroMet Community of Practice
KRA6 RISK INFORMATION AND PREPAREDNESS (new) | [5 empty] | 0 | 0 | TBD |  |  | TBD |  | TBD | TBD | TBD | TBD | TBD | TBD
OP6.1 Standardised, interoperable and inclusive multi-hazard data produced, stored and shared with resilience partners
6 |  | OP6.1 Standardised, interoperable and inclusive multi-hazard data produced, stored and shared with resilience partners |  |  | TBD by decadal investment plan to align with EW4All
OP6.2 Roles and responsibilities established for coordinating, updating, and reviewing hazard inputs into risk knowledge products, preparedness and response plans and procedures
6 |  | OP6.2 Roles and responsibilities established for coordinating, updating, and reviewing hazard inputs into risk knowledge products, preparedness and response plans and procedures |  |  | TBD by decadal investment plan to align with EW4All
CONTINGENCY AND OTHER | [5 empty] | 330000 | 3000000 | 5560 |  |  | 750 |  | 0 | 150 | 150 | 150 | 150 | 150
0 |  | Contingency and Other | 00 |  | Contingency and Other |  |  |  |  | 611540.85 | 750 |  | 0 | 150 | 150 | 150 | 150 | 150
[5 empty] | GRAND TOTAL (excl. SPREP program fees) | 7710000 | 40070000 | 190950 |  | 0 | 28611.6087 | #REF! | 4044.1051 | 5241.0801 | 10270.3343 | 4169.4812 | 2791.673 | 2094.935
Note on H14: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Added ICT infrastructure with cybersecurity from KRA4 $700k
Note on I14: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Added ICT infrastructure and cybersecurity and forecaster workstations $7.22M
Note on H16: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: IFP - $100k WIS - $200k High accessibility ICT infrastructure with cybersecurity $700k from KRA4
Note on I16: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: IFP $11M ICT infrastructure with cybersecurity, standalone forecaster work stations and technical workshops $7.22M transferred from KRA4
Note on G24: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Moved CAP training $100k to KRA2 people capability, so total reduced
Note on H24: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Moved CAP training $100k to KRA5, so total reduced by $100k
Note on I24: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Moved CAP training $200k to KRA5, so total reduced by $200k
Note on G26: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: National workshops 500k Regional workshop 160k Engagement strategy vulnerable groups 50k
Note on H26: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: National workshops 500k Regional workshop 160k
Note on I26: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: National workshops 500k Regional workshop 160k
Note on I28: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: combined delivery of impact based message $3.93M review of end user response $500k
Note on F30: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: tools, channels? instead of approaches
Note on H33: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Total reduced by Moved ICT infrastructure with cybersecurity to KRA4 $700k
Note on I33: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Reduced by ICT infrastructure, cybersecurity, forecaster workstations to KRA4 $7.22M
Note on G37: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: $1M network plans 50k regional principles and standards
Note on H39: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: cost of SPC staff only. Asset management and maintenance staff not budgeted originally.
Note on I39: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: cost of SPC staff only. Asset management and maintenance staff not budgeted originally.
Note on I40: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Reduced by $1M and move to network plans above
Note on F43: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Check with SPC if they prefer this terminology of ocean monitoring rather than be specific to wave buoys, as there is a lot of technology options
Note on G47: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Increased $100k as CAP training moved from KRA3 to 5
Note on H47: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Total increased CAP training $100k moved from KRA3 to KRA5
Note on I47: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Total increased by CAP training $200k from KRA2 to 5
Note on G55: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Short term capacity development workshop $100k CAP training - $100k moved from KRA3 to KRA5
Note on H55: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: CAP training - $100k moved from KRA3 to KRA5
Note on I55: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: CAP training - $200k moved from KRA3 to KRA5 Merged with QMS training 980k