## Slide 1: FY2025 Annual Report 01 January 2025 – December 2025
Steering Committee Paper 4.1 Presentation
1-2 June 2026
Honiara, Solomon Islands

## Slide 2
Human and economic cost of extreme events and climate change in the Pacific reduced
_____________
Pacific economies and livelihoods are climate and disaster resilient
_____________
Pacific security is stronger
_____________
Pacific peoples have access to safe and reliable transport and communications systems
_____________
Pacific hydrometeorological and multi-hazard early warning services are more integrated, impactful, sustainable and resilient
O1 - Pacific hydrometeorological services collectively securing ongoing, reliable and diverse finance and technical expertise
O5 - Pacific communities, governments, industries and travellers increasingly trust, understand forecasts and warnings
O6 – More informed and targeted disaster preparedness and responses inclusive of all genders, abilities, cultures and socio-economic groups
O4 – All Pacific end users assured access to relevant, timely, reliable, accessible and actionable forecasts and warnings
O3 - Pacific hydrometeorological services using and sustaining a growing Pacific-owned and controlled asset, data and knowledge base for public benefit
O2 - Pacific hydrometeorological services have increasing influence in national, regional and multilateral settings
KRA 2
People capability
KRA 3
Observation
network
infrastructure
KRA 5
Communication and
delivery of forecasts
and warnings to end
users
KRA 4
Forecast and
warning
production
KRA 1
Governance,
management and
coordination
OP1.1 WRP governance, management and pooled financing mechanisms established, mandated and equipped to coordinate a sustainable Pacific-led programme
OP1.2 Sustainable hydrometeorological financing facility and resource mobilisation approach established
OP1.3 Transformative GEDSI strategy adopted and integrated across governance, management and partner programming
OP3.1 Interoperable, affordable and resilient observation network infrastructure progressively remediated, expanded and sustained
OP3.2 WMO-designated Pacific Regional Instrument Centre established and sustainably managed
IO1.1 WRP governance, management, financing and coordination mechanisms are collaborative, inclusive, equitable, mutually accountable and value maximising
IO1.2 Pacific hydrometeorological services generating regular and sustainable returns on investment
IO1.3 Investor confidence in Pacific-led development and management of hydrometeorological services increased
IO2.1 Training services increasingly Pacific-based and integrating Pacific learning methods
IO2.2 Skills, knowledge and confidence of NMHS personnel increased
IO2.3 Retention of staff and capacity within the sector improved
Enablers
OVERALL OBJECTIVE: Climate and disaster resilient Pacific Island communities have improved safety, security, socio-economic well-being and prosperity
SPECIFIC OBJECTIVE: Pacific communities, governments and industries have inclusive multi-hazard early warning systems, forecasts, and information to reduce the impacts of extreme weather and other natural hazard events, including those exacerbated by climate change
Service value chain expansion
OP4.1 An integrated Pacific forecasting platform established and operating sustainably to global standards
OP4.2 Pacific forecasting capacity expanded and maintained
OP5.1 Pacific capacity and collaborative approaches to deliver locally-relevant, impact-based, inclusive and accessible forecasts and warnings for end users strengthened and sustained
OP2.1 WMO-designated Pacific Regional Training Centre established and sustainably managed
OP2.2 Inclusive leadership and technical capability strengthening programmes established and delivering ongoing training to industry standards
OP2.3 Continuous learning and mentoring opportunities provided
OUTPUTS - We will deliver:
IO3.1 Observation, monitoring and detection systems and real-time data supply expanded and enhanced
IO3.2 Pacific NMHS increasingly have robust, fit-for-purpose and well- maintained observation infrastructure
IO5.1 PRP members and communities collaborating effectively to communicate impact-based forecasts and warnings (inclusive of traditional knowledge) to all Pacific end users
IO5.2 Skills, knowledge and confidence of community members increased
INTERMEDIATE OUTCOMES – We will seek to achieve:
IO4.1 Quality forecasting data increasingly collected, integrated, analysed, monitored and maintained in the Pacific and integrated into the global meteorological system
IO4.2 Pacific forecasting and warnings increasing in accuracy
OUTCOMES – We will influence:
IMPACTS – We will contribute to:
KEY RESULT AREAS
IMPACT PATHWAY
ASSUMPTIONS: We can build momentum to attract sufficient investment | Political will remains | Organisational contexts remain favourable | External shocks can be accommodated | Services are more relevant if include modern and traditional knowledge
KRA 6 Risk
Information and
preparedness
OP6.1 Standardised, interoperable and inclusive multi-hazard data produced, stored and shared with resilience partners
OP6.2 Roles and responsibilities established for coordinating, updating, and reviewing hazard inputs into risk knowledge products, preparedness and response plans/procedures
IO6.1 Multi-hazard and multi-agency approach increasingly reflected in risk products, preparedness and response plans/procedures
IO6.2 Multi-hazard early warnings include traditional knowledge and are accessible to diverse and vulnerable communities
PRINCIPLES:
Pacific-led and owned
Driven by Pacific peoples | Responsive to local needs, cultural contexts |
Integrating traditional knowledge | Harmonised (local, national, regional, global)
Inclusive, equitable and empowering
Rights-based | GEDSI-responsive | Active, meaningful participation | Precautionary
Collaborative
Mutually accountable and transparent | Coordinated | Partnership-based
Transformative and sustained
Visionary | Structural and systemic | Agile | Enduring

## Slide 3
Evidence Base & Methodology
Consolidated from executing agency reports
All data and information are sourced directly from executing agency reports. Consolidated, synthesised, quality-checked for reasonable assurance
Assessed against the MERL Framework
Progress assessment is grounded in the MERL Framework endorsed by the Steering Committee in September 2025 — the first time a formal evidence framework has been applied to WRP reporting.
Progress measured from baselines to targets, where possible
Where baselines exist, progress has been tracked against Phase 1 targets. Some placeholder targets have not yet been reviewed or realigned to reflect the current programme context and dynamics.
Authored by the MERL and GEDSI team
Primarily written by WRP MERLA Officer, MERL Consultants Kat and Nicole, GEDSI Consultant Susan, with contributions from the Programme Manager, Programme Advisor and WRP PMU
On the RAG Status Ratings
Ratings are deliberately conservative
Some RAG ratings may appear contestable. They have been kept conservative by design — to avoid inflating early progress and to preserve the ability to demonstrate meaningful, incremental improvement from one reporting period to the next.
Ratings are evidence-informed, not evidence-derived
In the absence of a formal analytical framework, ratings reflect the PMU's best professional judgement applied consistently across KRAs, informed by available MERL data.
A formal analytical framework is being developed
To ensure consistent interpretation of progress year-on-year — using the same lens across all reporting periods — the PMU is developing a formal analytical framework for SC endorsement, following internal consultation and external review.
Things to Note

## Slide 4
Things to Note – cont.
This report is evidence that our MERL is working.
01
Phase 1 targets are provisional and will undergo a thorough review
Implementation targets were set as placeholders during programme design. Some are yet to be formally reviewed, validated, and agreed with EA/WRP PMU to reflect current programme realities.
02
MERL indicators are being strengthened
The MERL Framework — endorsed in September 2025 — is a first iteration. Review to take place post SC4 with amendments proposed to be tabled for SC5 deliberation/endorsement.
03
Developing a LENS to guide progress assessment
To ensure consistent, evidence-derived interpretation of progress across reporting periods, a formal analytical framework will be developed for deliberation/endorsement by SC5 following internal and external reviews.
Identifying these gaps IS the MERL working.
A credible programme knows what it doesn't yet know — and commits to fixing it.

## Slide 5
Things to Note – cont.
Also included are 10 Stories (Qualitative Signals) in slide 15-16:
  Six Performance Stories - KRA 2-4, GEDSI (BIP-M, GEDSI/MERL, regional workshop, SWP–Niue’s experience, GSMA cell broadcasting, SPREP-PDF MoU)
  Three Learning Stories - KRA 1 (PMC/SC, SWP – Feedback/AM, IFP)
  One Impact Story - KRA 3 (Tonga Radar)
Appendix 1 – Summarized MERL Table
Appendix 2 – FY2025 Budget Tracking
Appendix 3 – Summarized Program Risk Register

## Slide 6
Outline
1
01
Programme at a Glance & Status
02
Progress by Key Result Area
(KRAs 1–6)
03
Effectiveness, GEDSI, Sustainability & ESS
04
Programme Management & Governance
Purpose:
To report on FY2025 programme performance and seek Steering Committee notation, acceptance and endorsement of paper 4.1— with a forward look at 2026 priorities.

## Slide 7
1.0 Overall Programme Status – Indicative Output-Based Assessment
Strong foundations built in 2025 — implementation must accelerate decisively in 2026
OVERALL STATUS AMBER
Progress underway; path forward
clear. Acceleration needed in 2026.
Status by Key Result Area
KRA 1
Governance
AMBER
KRA 2
People Capability
GREEN
KRA 3
Observation Net. Infra
GREEN
KRA 4
Forecast & Warning Prod
AMBER
KRA 5
Comm. & Delivery to End Users
AMBER
KRA 6
Risk Info. & Preparedness
AMBER-RED
Key Numbers — FY2025
USD 28.5M
Total Committed
Funding up to 2025
USD 3.9M
Actual
Expenditure 2025
15
Active
Partners
9
BIP-M/MT
Graduates
Evidence from the field — see full stories in the deck:
LEARNING STORY
Governance & IFP
When country engagement was missing — and what we changed
PERFORMANCE STORY
9 BIP-M/MT Graduates
Permanent national capacity uplift across 7 Pacific countries
IMPACT STORY
Tonga Weather Radar
Earlier, more specific, more actionable warnings — first time ever

## Slide 8
Summary – Money Matters
Chart: USD Million
| Total Committed (excl. SPREP fees) | SPREP Managed | EA Managed (MetService, ESNZ, ADB, UNDRR) | SPREP Received 2025 | Actual Spend 2025 | Budget 2025
USD Million | 28.5 | 18.1 | 10.5 | 7.92 | 3.9 | 5.2
3 Active Donors
DFAT (Australia), NZ MFAT, UK WISER
USD 18.1M
Managed directly by SPREP
USD 10.4M
Managed by executing agencies
14%
Of committed funding spent in 2025
25% below budget
Due to recruitment delays, procurement establishment, EA invoice timing

## Slide 9
KRA 1: Governance, Management & Coordination
AMBER
Building the institutional foundation for a Pacific-led,
decade-long programme
8
Governance &
Partnership Mechanisms
3 ✓
Governance Studies
Completed
5
Frameworks
Fully Adopted
6 FTE
+3
PMU Staff
in Post
15
Active WRP
Partners
KEY ACHIEVEMENTS
GEDSI Strategy 2025–2033 approved 6 months ahead of schedule
MERL Framework, Sustainability Framework & Governance Review finalised
All 3 governance studies complete (Alignment Review, Risk Matrix, Asset Register)
PFIF Phase 1 legal framework completed
10-year BoM–SPREP Strategic Relationship Arrangement signed
MHEWS Readiness Fund operational — first 2 Concept Notes approved
KEY CHALLENGES
3 critical PMU roles vacant: MERLA, ESS/GEDSI, Communications Officers
Output 1.2 financing facility not yet commenced
Operations Manual still in development (due May 2026)
~50% of projects with GEDSI actions identified; only ~25% implementing
Pacific-led activities estimated at ~20–25% only
Pooled fund operationalisation delayed — affects programme efficiency
Notes: Output 1.2
Sustainable hydrometeorological financing facility and resource mobilisation approach established

## Slide 10
KRA 2: People Capability
GREEN
Investing in the people who stand between a
weather event and a community's response
4
Training Programmes
Established & Delivering
72
Training Sessions
Delivered
>100
People Trained
across 15 PICs
74
Active CoP
Members
61
Peer Exchanges
& Webinars
9
BIP-M/MT
Graduates
Severe Weather Pilot — Standout Results (MetService / Fiji / Tonga / Niue)
100%
reported increased confidence
+39%
accuracy confidence gains
+45%
timeliness confidence gains
+42%
collaboration confidence
100%
applying skills in their work
Notes: Achievements:
4 training programmes established and delivering — BIP-M Wellington and BoM Melbourne (both WMO-accredited), BIP-MT Nadi, and HydroMet Technician CoP. A13 = 4
72 training sessions delivered across all programmes — 3 formal accredited, 44 weekly online Severe Weather Pilot collaboration meetings, 25 workshops and other sessions. A14 = 72
9 BIP-M and BIP-MT graduates in 2025 — 3 from Tonga and Kiribati (Wellington), 3 from Samoa (Melbourne), 3 from Cook Islands, PNG, Tuvalu and Vanuatu (Nadi BIP-MT). Each is a permanent uplift in national forecasting capacity. A15 → 9 graduates
Severe Weather Pilot: 100% of participants reported increased confidence; +39% accuracy, +45% timeliness, +42% collaboration confidence gains. 100% applying skills in their work. B9 = 100%; B10 = 100%; B11 = 100% — MetService only
2 Communities of Practice operating: HydroMet Technician CoP (74 members, 15 PICs, Pacific-led convener); Severe Weather Outlook CoP (44 weekly meetings, Fiji Met increasingly leading). A16 = 74; A18 = 61
61 peer exchanges and webinars delivered — far exceeding the Phase 1 target of 5 sessions by December 2026. A18 = 61
JICA contract signed November 2025 for RTC construction at Fiji Met Service — WRP-supported FMS participation in contract signing. Construction target December 2027. A11 → 2027
Challenges:
Pacific Meteorology Leadership Programme (PMLP) not yet established — at concept stage only. Target: September 2026. A13 → PMLP pending
0 formal twinning partnerships established. Informal mentoring is active through the Severe Weather Pilot (MetService ↔ Fiji/Tonga/Niue) but does not meet the A17 formal definition. A17 = 0; target 5 by Dec 2028
Post-training survey data available for MetService programmes only — ESNZ, BoM and SPREP PMU survey data not yet collected, limiting programme-wide evidence of impact. Standardised survey tools to be rolled out to all EAs in 2026. B8, B9, B10, B11 → partial
RTC Governance and Business Model not yet formally adopted (ADB activity at 30% progress). Business Model Review deferred to 2026. WMO designation and JICA construction both targeted for 2027. A1 RTC = 0 adopted; A12 = 0
No staff retention or career progression baseline data collected — attrition rates not systematically tracked across Pacific NMHS. Baseline collection to be progressed through PIMS review and annual NMHS survey in 2026. B12, B13, B14 → no data

## Slide 11
KRA 3: Observation Network
Infrastructure
GREEN
You cannot forecast what you cannot observe
National Stocktake
~700 stations
across 15 PICs
Tonga Radar
Operational
First WRP-funded
infrastructure in use
Regional Obs
Workshop
65 reps from
14 PICs, Nov 2025
Solomon Islands
Radar Pre-Con
Contracts signed;
UXO assessment done
Samoa Radar
Procurement
RFQ issued Dec 2025;
closes Feb 2026
ACHIEVEMENTS
3 observation studies completed (stocktake, NAMP templates, WMO procurement standards)
Regional Radar Strategy in draft — to be formally endorsed SC4 (June 2026)
WRP Infrastructure & ICT Adviser joined PMU October 2025
JICA contract signed for RIC construction at Fiji Met Service (target Dec 2027)
CHALLENGES
Only ~40% of ~700 stations (~280) registered in OSCAR global database
All 5 regional network plans still in draft; 4 plans not yet started (ocean, hydrology, ICT, upper air)
AMIS (Asset Management Info System) at concept stage only — critical dependency
7 of 8 NMHS ICT staffing LOAs delayed — significant delivery gap

## Slide 12
KRA 4: Forecast & Warning Production
AMBER
Building the technical and operational foundation
for a Pacific-owned integrated forecasting system
Integrated Forecasting Platform (IFP) Journey
Peer Review
Complete
Sep 2025
14/15 Met
Director 1:1s
Dec 2025
Phase 1 SC
Endorsement
Sep 2025
Design
Workshop
Apr/May 2026
IFP Phase 1
Deployment
2027–2029
KEY ACHIEVEMENTS
IFP Peer Review: 5 options assessed; SC endorsed Phase 1 (Fiji Met as regional hub)
6 studies completed incl. ICT baseline (11 PICs), IFP Survey (11 countries)
5 Severe Weather Pilot tools operational in Fiji, Tonga & Niue — extended 12 months
15 forecasting SOPs developed across 3 countries through Severe Weather Pilot
KEY CHALLENGES
IFP Phases 2 & 3 not approved — insufficient country engagement was the key governance learning of 2025
0 IFP platforms installed — first deployments not expected before 2027–2029
7 of 8 ICT staffing LOAs still pending (LOA finalisation delays)
Aviation, marine & community SOPs not yet initiated

## Slide 13
KRA 5: Communication & Delivery
to End Users
AMBER
A warning that does not reach the right person, in the right
language, at the right moment, is not a warning
Status Note: KRA 5 is the KRA with the highest volume of planned 2026 activity. Most planned activities reflect programme sequencing — the path forward is clear but decisive acceleration is required in 2026.
Common Alerting Protocol (CAP) Baseline — Pre-WRP
1 PICT — CAP Fully Adopted (Solomon Islands)
9 PICs — CAP in Development or Test Mode
2 PICs —
Not Yet Started
2 PICs — No Data Available
KEY 2025 ACHIEVEMENTS
GSMA-PITA Cell Broadcast Workshop: 5-day intensive, ~28 orgs, 3 countries produced implementation roadmaps
Starlink communications installed at Tonga Met Service — first WRP-supported warning infrastructure
COPE book translations contracted for Niue & Tokelau
MHEWS TWG established under Pacific Resilience Partnership
PRIORITY ACTIONS 2026
Commence CAP training across multiple PICs — highest impact KRA 5 activity
Finalise COPE book translations and distribution
Finalise Starlink LOAs for Solomon Islands & Kiribati
Fill Communications Officer vacancy — critical for KRA 5 acceleration

## Slide 14
KRA 6: Risk Information &
Preparedness
AMBER-RED
Ensuring communities have the risk knowledge to translate warnings Into protective action — endorsed Sep 2025
Context: KRA 6 was formally endorsed by the WRP Steering Committee in September 2025 to align with UN Early Warnings for All (EW4All). As a newly established KRA, no Investment Plan has yet been developed and no formal KRA 6-specific activities have commenced.
Early Cross-KRA Contributions
LiDAR Survey
(from KRA 4)
FUGRO contracted for terrain & hazard mapping — contributes to multi-hazard risk data (Output 6.1)
COPE Booklets
(from KRA 5)
Community hazard preparedness booklets for Niue & Tokelau — contributes to inclusive community preparedness (Output 6.2)
MHEWS TWG
(from KRA 1)
First concrete multi-agency coordination mechanism for EW4All alignment under Pacific Resilience Partnership
CRITICAL 2026 PRIORITY: Complete the KRA 6 Investment Plan, Implementation Plan and Funded Work Plan — without it, no KRA 6-specific activity targets can be set or costed, and WRP's EW4All commitments remain without a programmatic vehicle.

## Slide 15: Stories (Qualitative Signals)
KRA 1 — Learning Story 1: Building Something New examines what it truly requires to establish a Pacific-led programme in a sector ready for change: building a capable PMU, coordinating multiple donors and executing agencies, and navigating the operational pressures of a first year — while holding the line on Pacific ownership. (see page 31)
KRA 1 — Learning Story 2: The Skill of Adaptive Management draws on the Severe Weather Forecasting Enhancement Pilot to make a programme-wide argument: that adaptive management is not a licence to deviate from commitments — it is a commitment in itself. The pilot earned the right to adapt by building the feedback infrastructure first. For WRP, this is the model of how the programme should operate across all its work. (see page 33)
KRA 2 — Performance Story 1: From Aviation Briefings to BIP-M Certified follows Lineni Fifita of Tonga, one of nine WRP-funded graduates who returned home in 2025 with an internationally recognised WMO qualification — and what that qualification means for the service she returns to. (see page 38)
KRA 2 — Performance Story 2: Learning to Programme Well, Together documents how GEDSI and MERL were embedded directly into the 2025 WRP Planning Workshop — building the reflective and inclusive programming capability the programme needs to deliver on its own values. (see page 39)
KRA 3 — Impact Story 1: Seeing the Storm Before It Arrives documents what changed for Tonga when its first weather radar became operational — from inference-based forecasting to direct observation, and from generalised warnings to earlier, more specific, more credible alerts. This is the clearest illustration in 2025 of what WRP investment means in practice for communities. (see page 44)

## Slide 16: Qualitative Signals-cont
KRA 3 — Performance Story 3: Seeing the Whole Picture describes how a regional workshop in November 2025 brought together 65 representatives from 14 Pacific Island countries to collectively map the region's observation network crisis for the first time — and turn it into a shared plan of action. (see page 49)
KRA 1 / KRA 4 — Learning Story 3: Getting the Foundations Right follows the IFP journey and what it taught WRP about partnership, shared vision, and the patience that complex change requires. When the Steering Committee did not approve IFP Phases 2 and 3 in May 2025, WRP treated that as signal rather than setback — completing one-on-one meetings with 14 of 15 Met Directors and reforming how major decisions are prepared. (see page 55)
KRA 4 — Performance Story 4: A Safe Space to Get It Right follows the emergence of a peer forecasting community within the Severe Weather Pilot — and the moment a meteorologist from Niue's small service used that community to build the confidence to issue a warning that was right, and that protected lives. (see page 56)
KRA 5 — Performance Story 5: Alert on Every Phone describes WRP's partnership with GSMA on cell broadcasting — technology that sends an alert to every handset in an affected area without requiring credit, a SIM card, or internet connection — and what it means for the Pacific communities most likely to be cut off when warnings matter most. (see page 60)
GEDSI — Performance Story 6: No One Left Behind documents the partnership between SPREP and the Pacific Disability Forum, signed in September 2025, and what it means for a programme whose stated purpose includes reaching the people most at risk and least reached by existing warning systems. (see page 67)

## Slide 17
EFFECTIVENESS
FY2025
Summary
Overall
Solid foundational progress. Moving in the right direction — most consequential delivery lies ahead.
Spotlight
Tonga's first weather radar is changing how forecasters see storms — and how warnings reach communities.
Are we achieving what we set out to achieve?
Early signals are encouraging. Long-term community outcomes will take years to measure.
KRA 1 · Governance & Partnerships
15 partners. 10-yr BoM–SPREP agreement. 3 active development partners.
On track
KRA 2 · People Capability
6 qualified meteorologists. 33 trained. 100% applied skills. 2 CoPs active.
KRA 3 · Observation Networks
~700-station regional stocktake done. Priorities set for 2026 investment.
KRA 4 · Forecasting & IFP
5 tools in active use. IFP peer review endorsed. Design workshop Apr/May 2026.
Needs action
KRA 5 · Warning Communication
Most activities deferred to 2026. Significant acceleration needed.
KRA 6 · Risk Info & Preparedness
Added May 2025. Investment plan needed!
Underway
Underway
On track
Needs action
Notes: In terms of effectiveness, this slide seeks to highlight on

## Slide 18
GEDSI
Gender, Disability
& Social Inclusion
Starting point
WRP starts from a baseline of weak GEDSI-sensitive programming across the sector. 2025 is the beginning of a deliberate shift.
"This partnership ensures that WRP is truly inclusive and serves all members of our communities."
Salesa Nihmei, SPREP
Koror, Palau — Nov 2025
Building an inclusive early warning system — from policy to practice
2025 saw WRP's GEDSI Strategy approved and its first landmark partnership signed — the sector shift is beginning.
Completed
Strategy approved
GEDSI Strategy 2025–2033 approved by SC in September 2025. Twin-track framework: mainstream GEDSI across all programming + targeted interventions for women, persons with disabilities, and marginalised groups.
Completed
SPREP–PDF MOU signed
Landmark MOU between SPREP and Pacific Disability Forum — representing 71 organisations across 22 PICs. Moves disability inclusion from policy into practice across all 6 KRAs.
Underway
Early capacity actions
GEDSI Convening in Nadi (39 participants). GEDSI & MERL training for PMU and EA staff in December. NMHSs GEDSI Focal Points Network established. Staff understanding of strategy rose from 37% to 56%.
2026
Baseline still to come
Sector-wide GEDSI diagnostic assessment planned for 2026. This will establish the formal baseline against which WRP's inclusion progress will be measured going forward.

## Slide 20
Sustainability Framework (10 Benchmarks + guiding questions) approved by SC in September 2025 and embedded in the MERL Framework.
2025 concept notes show growing awareness of sustainability but uneven depth of application — expected for a framework in its first year.
Benchmarks 1 (Pacific ownership) and 2 (shared vision, phased implementation) are well-represented across nearly all concept notes.
Benchmark 4 (sustainable financing) is being addressed structurally through the Asset Management Framework, PFIF, and long-term hydrometeorological financing via the Pacific Meteorological Council.
Benchmarks 5–10 (preconditions, maintenance, embedding change, partnerships, trust, stewardship) are consistently receiving superficial or procedural treatment — noted as 'per Operations Manual' rather than substantively designed into activities.
Two bright spots documented: Learning Story 1 (B1, B4) and Learning Story 3 (B2, B8, B9) demonstrate benchmarks applied with depth and rigour.
20–25% of WRP activities were led by Pacific institutions in 2025 (indicative estimate). Formal tracking via Programme Tracker from 2026.
2026 action: All concept notes to include a completed sustainability guiding question screening as a precondition for PMU assessment.

## Slide 21
SUSTAINABILITY
& ESS
Cross-cutting
Frameworks
Status
Both frameworks are new in 2025. Uneven or partial application is expected. Systematic rollout planned for 2026.
2026 action
All three frameworks (GEDSI, Sustainability, ESS) will be embedded in concept note screening from 2026. ESS/GEDSI Officer recruitment is a critical enabling step.
Sustainability & Environmental and Social Safeguards
Both frameworks were established in 2025. Application is underway but uneven — deeper integration is the 2026 priority.
SUSTAINABILITY
Completed
Framework approved
Sustainability Framework — 10 Benchmarks + guiding questions — approved by SC in September 2025. Benchmarks embedded in MERL Framework.
Partial
Uneven early application - expected
Benchmarks 1 (Pacific ownership) and 2 (shared vision) well-represented. Benchmarks 5–10 receiving superficial treatment for now — noted procedurally rather than substantively designed in.
ENVIRONMENTAL & SOCIAL SAFEGUARDS (ESS)
In progress
Framework in development
ESS Framework development began in 2025. Expected completion mid-2026 as part of Operations Manual. Ops Manual Chapter 12 tabled for SC4 approval.
Underway
SPREP ESMS applied meantime
In absence of WRP ESS Framework, SPREP's ESMS applied activity-by-activity. Specific actions include UXO and geotechnical assessments for Solomon Islands and Samoa radar sites.
Underway
Community engagement begun
Community engagement programme launched in Solomon Islands in December 2025 to support radar installation. ESS screening will be embedded in concept note assessment from 2026.

## Slide 22
4.0 Programme Management & Governance
Contracts & Procurement
Weather Ready Pacific | FY2025 Annual Report
FUNDING AGREEMENTS – till 2025
Total committed funding: USD 28.5 million (excluding SPREP fees) from 3 donors.
Australia DFAT: AUD 30 million across 2 agreements (Nov 2023 & Mar 2025).
New Zealand MFAT: USD 1.33 million across 2 agreements (Aug 2024 & Jun 2025).
UK WISER: USD 0.81 million across 2 agreements (Apr 2024 & Feb 2025).
USD 18.1 million flows through SPREP; remainder managed by NZ MetService, ESNZ, ADB, and UNDRR.
PROCUREMENT
7 SPREP-managed contracts signed in 2025, totalling USD 1.84 million.
Key signed contracts include: Hydrological services & coastal inundation EW (AUD 1.55M); BOM Project Arrangements (AUD 861K); Tonga LOA (USD 83K); GEDSI Consultant Phase 1 (USD 28K).
10 contracts in negotiation, including LOAs for Cook Islands, Kiribati, RMI, Niue, Samoa, Solomon Islands, Tuvalu and Fiji.
1 contract under tender evaluation (Review of WRP Decadal Investment Plan, USD 50K).
Samoa Radar Supplier contract advertised.
Support contracted directly by donors to executing agencies (outside SPREP)
NZ MetService (NZ MFAT): USD 7.M · Earth Sciences NZ (NZ MFAT): USD 3.0M · GEDSI Specialist (UNDRR): USD 86.4K · Governance Adviser (ADB): USD 150K · MERL & Sustainability Consultancy (NZ MFAT): USD 57.9K

## Slide 24
Programme Management & Governance
Recruitment & PMU Staffing
Weather Ready Pacific | FY2025 Annual Report
2025 APPOINTMENTS
Financial Accountant (May 2025)
Infrastructure and ICT Adviser (October 2025)
Capacity Development and Training Adviser (October 2025)
Procurement Officer (November 2025)
TARGETED FOR RECRUITMENT IN 2026
MERLA Officer (FILLED – April 2026)
ESS/GEDSI Officer (IN PROGRESS – MAY 2026)
Communications and Knowledge Management Officer (FILLED – Feb/Mar 2026)
6 staff · Apia, Samoa · 50/50 gender · All Pacific Islanders

## Slide 25
Programme Management & Governance
Weather Ready Pacific | FY2025 Annual Report
OVERALL PROGRAMME
Total committed funding: USD 28.5 million (excl. SPREP fees).
2025 actual expenditure: USD 3.9 million — 14.3% of committed funding.
2025 budget was USD 5.1 million; actual spend was USD 1.3 million below budget.
  Underspend driven by: staff recruitment delays; procurement and contract establishment delays with executing agencies; flow-on delays to activity execution; invoices not yet processed.
26.6% of total WRP spending attributed to personnel and related costs.
SPREP-MANAGED FUNDS – FY2025
USD 7.92 million received from 3 donors; USD 1.74M spent; USD 0.87M committed.
AU DFAT: USD 6.22M received · 18.4% spent · 32.0% spent + committed.
NZ MFAT: USD 1.33M received · 34.7% spent · 34.9% spent + committed.
UK WISER: USD 369K received · 35.6% spent · 40.9% spent + committed.
DFAT's lower spend rate reflects the phased disbursement schedule — 4 further tranches (AUD 20M) due 2026–2028. This is consistent with a programme in establishment phase.
Remaining funds 2026–2029: USD 18.83M programmed — Revised 2026: USD 8.77M · 2027: USD 5.35M · 2028: USD 2.37M · 2029: USD 2.36M.
DFAT tranches 4–7 (AUD 6M–6M–6M–2M) due May 2026 through Oct 2028. UK WISER final disbursement (USD 123K) received Dec 2025.

## Slide 26
Programme Management & Governance
Activity Pipeline & Country Disbursements
Weather Ready Pacific | FY2025 Annual Report
2025 ACTIVITIES DEFERRED TO 2026 (15 items)
Revised WRP Investment Plan (EW4All aligned)
3 PMU recruitment positions (ESS/GEDSI, Comms, MERLA Officers)
Business model review for RTC and RIC
Hydrologists training
CAP installation, training and regional workshop
3 network plans: Upper Air, Ocean & tides, Flood & hydrology
IFP Design and ICT Architecture + Peer review of IFP
LiDAR surveys (Marshall Islands) and Pacific LiDAR strategy
Regional hydrology strategy
ICT Specialist secondment (IFP, KRA 2 & 3)
COPE book translation and printing
Risk WRP-20: Activity Pipeline Compression — rated INCREASING
2025 ACTIVITIES BY COUNTRY (USD)
Solomon Islands*
971,460
Tonga*
609,656
Samoa
357,863
Fiji
336,438
Cook Islands
269,141
Vanuatu
278,527
Kiribati
234,638
Niue
189,922
PNG
162,023
Tuvalu
133,863
FSM
81,824
Tokelau
65,896
Marshall Islands
56,471
Nauru
47,617
Palau
44,509
* Radar installation (single capital investment)

## Slide 27
Critical 2026 Priority Actions
What must happen in 2026 for WRP to deliver on its bold purpose
1
KRA 1
Fill 3 vacant PMU roles: MERLA, ESS/GEDSI, Communications Officers
Q1 2026
2
KRA 6
Complete KRA 6 Investment Plan & Implementation Plan — critical unblocking action
Q1-2 2026
3
KRA 5
Commence CAP training across multiple PICs — highest-impact KRA 5 action in 2026
H1 2026
4
KRA 4
Deliver IFP Phase 1 design workshop (Apr/May 2026, Nadi) and establish project team
Apr 2026
5
KRA 3
Formally adopt Regional Radar Strategy at SC4; complete Solomon Islands radar installation
Jun 2026
6
KRA 3/4
Finalise 7 pending ICT staffing LOAs for NMHSs (Cook Islands, Kiribati, Niue, RMI, Samoa, SI, Tuvalu)
Q1 2026
7
KRA 1
Complete WRP Operations Manual and table at SC4 (DFAT contract deliverable)
Jun 2026
8
KRA 2
Establish Pacific Meteorology Leadership Programme (PMLP)
Sep 2026
Weather Ready Pacific | FY2025 Annual Report | OFFICIAL

## Slide 28
Steering Committee Proposed Resolution
To note, accept and endorse the FY2025 Annual Report
D5
The foundations are holding.
The pathway to Climate and Disaster Security is becoming clearer
with every step taken.
Now we must build faster.

## Slide 29: Questions
Tank yu tumas