## DFAT Changes
Year
KRA | Activity No. | Activity | Project Title | WRP Funding Source | Executing Agency | Funding Modality | 2026 Budget_ | 2027 Budget_ | 2028 Budget_ | 2029 Budget_ | Total WRP Funding Allocated USD_ | Comments
1 | 1.1.1 | Establish the PMU, Operational Processes and WRP pooled fund | Resource Mobilisation Activities | DFAT | WRP | Ring-Fenced | 0 |  |  |  | 0 | Renamed to remove Strategy and replace with Activities
| 1.1.2 | Operational Phase of PMU and coordination activities | Hosting of WRP Steering Group and Liaison Platform | DFAT | WRP | Ring-Fenced | 25000 |  | -25000 |  | 0 | Brought forward 25K from FY 2028 to FY 2026
2 | 2.2.1 | Training of forecasters to BIP-M standard | Meteorologists Training | DFAT | BOM | Ring-Fenced |  | 170000 |  |  | 170000 | Australia Awards Potential 2027 Support
3 | 3.1.1 | Implement observation network plans, asset management, standardised infrastructure, data management and maintenance practices | Network Sustainability and Planning | DFAT | BOM | Ring-Fenced |  |  |  |  | 0 | Combined network plans for Upper Air, Ocean and Tides, Flood and Hydrology, ICT under Network Sustainability and Planning
|  |  | Asset Management Information System Implementation (software & training) | DFAT | WRP | Ring-Fenced | -75000 | -125000 | -20000 | -10000 | -230000 | This allocation now covered by NZ MFAT Funding
Sub Total | [6 empty] | -50000 | 45000 | -45000 | -10000 | -60000
[7 empty] | Australia Awards Funding |  |  |  | 170000
[7 empty] | AX DFAT Funding proposed 2026-2029 workplan |  |  |  | -60000
[7 empty] | To be programmed |  |  |  | 230000

## NZ MFAT Changes
Year
KRA | Activity No. | Activity | Project Title | WRP Funding Source | Executing Agency | Funding Modality | 2026 Budget_ | 2027 Budget_ | 2028 Budget_ | 2029 Budget_ | Total WRP Funding Allocated USD_ | Comments
1 | 1.1.1 | Establish the PMU, Operational Processes and WRP pooled fund | Branding and advertising | MFAT- SPREP | WRP | Ring-Fenced | 10000 | 10000 | 20000 | 20000 | 60000 | Increasing the visibility of WRP
|  |  | Revised WRP Investment plan and implementation plan aligned with EW4ALL | MFAT- SPREP | WRP | Ring-Fenced | 10000 |  |  |  | 10000 | Additional to cover travel
|  |  | Communication Action Plan | MFAT- SPREP | WRP | Ring-Fenced | 5000 | 10000 | 10000 | 10000 | 35000 | Supporting NMHSs Comms
|  |  | PIMS and One Pacific Meteorology Framework Development and Operationalisation |  |  |  |  | 100000 | 50000 | 50000 | 200000 | Operationalising of PIMS and One Pacific Meteorology Framework
| 1.1.2 | Operational Phase of PMU and coordination activities | Hosting of WRP Steering Group and Liaison Platform | MFAT- SPREP | WRP | Ring-Fenced | 67130 | 100000 | 150000 | 100000 | 417130 | Extending support across other years
|  |  | PMU Travel and Workshops | MFAT- SPREP | WRP | Ring-Fenced | 60000 | 100000 | 100000 | 120000 | 380000 | Extending support across other years
|  |  | Staff start up cost (IT, furniture) and communicating & promotion | MFAT- SPREP | WRP | Ring-Fenced | 20000 | 10000 | 20000 | 10000 | 60000 | Extending support across other years
| 1.1.3 | MERL framework establishment and operationalisation | MERL Development, Operations and Programmatic evaluations | MFAT- SPREP | WRP | Ring-Fenced | 20000 | 137500 | 67500 | 142500 | 367500 | Term reviews, operationalising MERL
|  |  | MERL Research | MFAT- SPREP | WRP | Ring-Fenced | 5000 | 15000 | 25000 | 15000 | 60000 | MERL Research
| 1.1.4 | PMU Staff (Management and Delivery Support roles) | Staff: ICT Officer | MFAT- SPREP | WRP | Ring-Fenced |  | 134977 | 134977 | 134977 | 404931 | New Staff - IFP needs
| 1.2.1 | Sustainable hydrometeorological financing investment facility | Sustainable financing and resource mobilisation options | MFAT- SPREP | WRP | Ring-Fenced |  | 50000 | 100000 | 100000 | 250000 | MHEWS Maintenance Facility
| 1.3.1 | GEDSI and social safeguards mainstreamed into WRP | Operational budget for mainstreaming GEDSI into WRP implementation2 | MFAT- SPREP | WRP | Ring-Fenced |  | 30000 |  |  | 30000 | Continuation of service
| 2.1.1 | Establish and operate a Regional Training Centre (RTC) | PIETR panel Training and capacity development roadmap development and implementation |  |  |  |  | 200000 | 200000 |  | 400000 | Developing and accreditation of courses
|  |  | RTC and RIC Operationalisation Support |  |  |  |  | 50000 |  |  | 50000 | Continuation of service
| 2.2.1 | Training of forecasters to BIP-M standard | Meteorologists Training | MFAT- SPREP | NZ Met Services | Ring-Fenced |  | 300000 |  |  | 300000
|  |  | Development of bridging and/or support for BIP-M in collaboration with RTC, USP and PIETR. | MFAT- SPREP | WRP | Ring-Fenced |  | 100000 |  |  | 100000
| 2.2.3 | Training of observers, technicians and ICT specialists, and assessment of competencies | BIP MT Training | MFAT- SPREP | WRP | Ring-Fenced | 100000 |  | 200000 |  | 300000
| 2.2.4 | Establish and deliver a Pacific Meteorology Leadership Programme for mid and senior level staff | Liaison with regional institutions for the development of a Leadership Program for mid-level to senior staff level and deliver the course | MFAT- SPREP | WRP | Ring-Fenced | 17000 | 150000 |  |  | 167000 | Travel and Validation workshop for Leadership Program
| 2.2.5 | Specialised regional workshops and training courses | Installation and training in the common alerting protocol and Regional workshop | MFAT- SPREP | WRP | Ring-Fenced |  | 110000 | 110000 |  | 220000 | Continuation of service
|  |  | AI Capacity Support for NMHSs | MFAT- SPREP | WRP | Ring-Fenced |  | 100000 | 100000 | 200000 | 400000
| 2.3.1 | Twinning programme, ongoing mentoring and communities of practices | Community of practice support | MFAT- SPREP | WRP | Other Support |  | 40000 | 40000 |  | 80000 | Continuation of service that was provided by NZ Met and ESNZ
3 | 3.1.1 | Implement observation network plans, asset management, standardised infrastructure, data management and maintenance practices | Geohazard Partnership Framework Design and Support | MFAT- SPREP | WRP | Ring-Fenced | 100000 | 100000 | 100000 | 100000 | 400000
|  |  | Asset Management Information System Implementation (software & training) | MFAT- SPREP | WRP | Ring-Fenced |  | 415000 | 271500 | 20000 | 706500 | Hire of Consultant, procurement of software and regional validation workhop
| 3.1.3 | Revitalise and expand automatic and manual weather stations | Supply, Install and Support AWS/AWOS | MFAT- SPREP | WRP | Ring-Fenced |  | 30000 |  |  | 30000 | Supporting AWS/AWOS procurement including preferred supplier panel
4 | 4.1.1 | Develop an Integrated Forecasting Platform and strengthen RSMCs (incl WIS, CAP) | IFP Implementation and Roll Out - Progressively by country | MFAT- SPREP | BOM, NZ MetServices | Ring-Fenced |  | 500000 | 800000 | 800000 | 2100000 | Continuation of service
|  |  | Sustaining National and Regional Enabling Infrastructure | MFAT- SPREP | WRP | Ring-Fenced |  | 600000 | 200000 |  | 800000 | Generator and UPS for RSMC, ICT hardware for IFP
| 4.2.1 | Strengthen aviation forecasting | Pacific Aviation Improvement Roadmap and Compliance Support | MFAT- SPREP | WRP | Ring-Fenced |  | 350000 | 350000 | 350000 | 1050000
| 4.2.2 | Strengthen public forecasting | Severe Weather Pilot (3 countries) - strengthen public forecasting | MFAT- SPREP | WRP | Ring-Fenced |  | 100000 |  |  | 100000 | Continuation of service
| 4.2.6 | Provide additional ICT and other technical staff to expand capacity | Hiring ICT staff for Pacific Island Country NMHSs | MFAT- SPREP | WRP | Ring-Fenced |  | 100000 | 170000 | 170000 | 440000 | Continuation of service and extending to other countries
5 | 5.1.1 | Planning for delivery of impact-based messages and warnings to end-users, considering persons with disabilities and vulnerable groups. | National consultation workshops with selected countries to review existing messages and warnings | MFAT- SPREP | WRP | Ring-Fenced |  |  |  | 80000 | 80000 | Continuation of service
|  |  | Regional workshop with NDMOs, NMHS, EW4All to review existing messaging and develop plan for preparation and delivery of response-based messaging and warnings to end users | MFAT- SPREP | WRP | Ring-Fenced |  |  |  | 50000 | 50000 | Continuation of service
| 5.1.4 | Inclusive Community Education and Information-Exchange collectives | Translation and printing of COPE books | MFAT- SPREP | WRP | Ring-Fenced |  | 50000 | 100000 |  | 150000 | Continuation of service
| 5.1.5 | Develop innovative approaches for dissemination of forecasts and warnings to end-users (e.g. cell broadcasting, mobile apps, social media) | Last-mile and community communication systems | MFAT- SPREP | WRP | Ring-Fenced |  | 1000000 | 1000000 |  | 2000000 | Communications systems for Tokelau.
Sub Total | [6 empty] | 414130 | 4992477 | 4318977 | 2472477 | 12198061
[7 empty] | NZ Funding equivalent to be Programmed |  |  |  | 15679826.087
[7 empty] | NZ Funding proposed 2026-2029 workplan |  |  |  | 12198061
[7 empty] | To be programmed |  |  |  | 3481765.087

## UK WISER Changes
Year
KRA | Activity No. | Activity | Project Title | WRP Funding Source | Executing Agency | Funding Modality | 2026 Budget_ | 2027 Budget_ | 2028 Budget_ | 2029 Budget_ | Total WRP Funding Allocated USD_ | Comments
1 | 1.1.2 | Operational Phase of PMU and coordination activities | Hosting of Pacific Meteorology Council and Ministerial Meetings | UK WISER | WRP | Ring-Fenced | 184435.5 |  |  |  | 184435.5 | PMC & PMM M Support | Previous | New
| 1.3.1 | GEDSI and social safeguards mainstreamed into WRP | Operational budget for mainstreaming GEDSI into WRP implementation2 | UK WISER | WRP | Ring-Fenced | -21139.41 | 147548.4 |  |  | 126408.99 | Regional disability-inclusive early warning training course | 88529.04 | 67389.63
2 | 2.2.5 | Specialised regional workshops and training courses | Installation and training in the common alerting protocol and Regional workshop | UK WISER | WRP | Ring-Fenced | 10086.9004 |  |  |  | 10086.9004 |  | 109824.0996 | 119911
| 2.2.6 | Provide additional staff for training and capacity development | Staff: Support to WRP PMU Human Resource | UK WISER | WRP | Ring-Fenced | -46866.67 |  |  |  | -46866.67 |  | 111947 | 65080.33
5 | 5.1.4 | Inclusive Community Education and Information-Exchange collectives | Translation and printing of COPE books | UK WISER | WRP | Ring-Fenced | 77286.165 | 130000 |  |  | 207286.165 | Additional COPE funding | 107587.375 | 184873.54
| 5.1.5 | Develop innovative approaches for dissemination of forecasts and warnings to end-users (e.g. cell broadcasting, mobile apps, social media) | Last-mile and community communication systems | UK WISER | WRP | Ring-Fenced | 73000 |  |  |  | 73000 | Samoa Meteorological Service television weather studio
Sub Total | [6 empty] | 276802.4854 | 277548.4 | 0 | 0 | 554350.8854
[7 empty] | UK WISER 2026-2029 workplan |  |  |  | 534983.9
[7 empty] | Phase 2 reallocation |  |  |  | 19366.9854
[7 empty] | Fully programmed |  |  |  | 554350.8854
Note on H7: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Phase 2 Budget reallocation