## Slide 1: WRP Implementation Plan and Funded Work Plan Update V3.0
Weather Ready Pacific Steering Committee 5
15 September 2026

## Slide 2: Updates
No changes to Activities
Nine (9) new projects proposed
Revised update to reflect:
Budgeting for the new NZ MFAT funding allocation of NZD 32 million (USD 15.68m).
  USD 12,198,061 has been allocated. USD 3,481,765 to be programmed
Budgeting for the new UK WISER funding allocation of GBP 500,000.
  USD 534,984
Budgeting for DFAT Australia Awards funding for 2027 AUD 255,000.
  USD 170,000
Inclusion of nine additional projects since the approval of Version 2.1 by SC4.

## Slide 3: New Proposed Projects
Activity No |  | Project Title | NZ MFAT | UK WISER | 
1 | 1.1.1 | PIMS and One Pacific Meteorology Framework Development and Operationalisation | 200,000 |  | 
2 | 1.1.2 | Hosting of Pacific Meteorology Council and Ministerial Meetings |  | 184,436 | 
3 | 1.1.3 | MERL Development, Operations and Programmatic evaluations | 367,500 |  | 
4 | 2.2.5 | AI Capacity Support for NMHSs | 400,000 |  | 
5 | 2.3.1 | Community of practice support | 80,000 |  | 
6 | 3.1.3 | Supply, Install and Support AWS/AWOS | 30,000 |  | 
7 | 4.1.1 | Sustaining National and Regional Enabling Infrastructure | 800,000 |  | 
8 | 4.2.1 | Pacific Aviation Improvement Roadmap, Quality Management and Compliance Support | 1,050,000 |  | 
9 | 5.1.5 | Last-mile and community communication systems | 2,000,000 | 73,000 | 
 |  |  | 4,927,500 | 257,436 | 5,184,936

## Slide 4: Project Name Change
Activity No | New Project Title | Previous Project Title
1.1.1 | Resource Mobilisation Activities | Resource Mobilisation Strategy
2.1.1 | RTC and RIC Operationalisation Support | Business model review for RTC and RIC
3.1.1 | Network Sustainability and Planning | Combined network plans: 1) Upper Air, 2) Ocean and Tides, 3) Flood and Hydrology, 4) ICT under Network Sustainability and Planning
Note the change of project name changes to encompass project evolution

## Slide 5: Proposed Total Budget Change 2026-2029
 | 2024 Actual_ | 2025 Actual_ | 2026 Budget_ | 2027 Budget_ | 2028 Budget_ | 2029 Budget_ | Total WRP Funding Allocated USD_
Approved Total SC May 2026 Figures | 3,743,228 | 3,939,976 | 10,901,933 | 5,768,245 | 2,056,673 | 2,049,935 | 28,459,991
Proposed Total SC Sept 2026 Figures | 3,743,228 | 3,939,976 | 11,462,866 | 11,093,271 | 6,330,650 | 4,582,412 | 41,152,403
 | - | - | 560,932 | 5,325,025 | 4,273,977 | 2,532,477 | 12,692,412
Note Budget Increase:
USD 12.692 million increase in total funding driven by new contributions from New Zealand MFAT, Australia Awards and UK WISER Phase 3.
Approximately USD 3.482 million has been earmarked for KRA 6: Risk Information and Preparedness Activities.

## Slide 6: Proposed Budget Allocation 2026-2029 by Activity
Activity No | Activity | DFAT | NZ MFAT | UK WISER
1.1.1 | Establish the PMU, Operational Processes and WRP pooled fund |  | USD 305,000 | 
1.1.2 | Operational Phase of PMU and coordination activities |  | USD 857,130 | USD 184,436
1.1.3 | MERL framework establishment and operationalisation |  | USD 427,500 | 
1.1.4 | PMU Staff (Management and Delivery Support roles) - ICT Officer |  | USD 404,931 | 
1.2.1 | Sustainable hydrometeorological financing investment facility |  | USD 250,000 | 
1.3.1 | GEDSI and social safeguards mainstreamed into WRP |  | USD 30,000 | USD 126,409
2.1.1 | Establish and operate a Regional Training Centre (RTC) |  | USD 450,000 | 
2.2.1 | Training of forecasters to BIP-M standard | USD 170,000 | USD 400,000 | 
2.2.3 | Training of observers, technicians and ICT specialists, and assessment of competencies |  | USD 300,000 | 
2.2.4 | Establish and deliver a Pacific Meteorology Leadership Programme for mid and senior level staff |  | USD 167,000 | 
2.2.5 | Specialised regional workshops and training courses |  | USD 620,000 | USD 10,087
2.2.6 | Provide additional staff for training and capacity development |  | USD 0 | -USD 46,867
2.3.1 | Twinning programme, ongoing mentoring and communities of practices |  | USD 80,000 | 
3.1.1 | Implement observation network plans, asset management, standardised infrastructure, data management and maintenance practices | -USD 230,000 | USD 1,106,500 | 
3.1.3 | Revitalise and expand automatic and manual weather stations |  | USD 30,000 | 
4.1.1 | Develop an Integrated Forecasting Platform and strengthen RSMCs (incl WIS, CAP) |  | USD 2,900,000 | 
4.2.1 | Strengthen aviation forecasting |  | USD 1,050,000 | 
4.2.2 | Strengthen public forecasting |  | USD 100,000 | 
4.2.6 | Provide additional ICT and other technical staff to expand capacity |  | USD 440,000 | 
5.1.1 | Planning for delivery of impact-based messages and warnings to end-users, considering persons with disabilities and vulnerable groups. |  | USD 130,000 | 
5.1.4 | Inclusive Community Education and Information-Exchange collectives |  | USD 150,000 | USD 207,286
5.1.5 | Develop innovative approaches for dissemination of forecasts and warnings to end-users (e.g. cell broadcasting, mobile apps, social media) |  | USD 2,000,000 | USD 73,000
 |  | -USD 60,000 | USD 12,198,061 | USD 554,351
 |  | USD 12,692,412 |  | 

## Slide 7: Decision sought from SC
SC5 Dec 6.1.1 - The SC approves the updated WRP Implementation Plan and funded Work Plan 2026 to 2029 v3.0