## PIMOS Workplan_2019
HIGH LEVEL ACTIONS | ACTIVITY | ACTION | 2019 PROGRESS | NEXT STEPS/ IMPEMENTATION PLAN | KEY PERFORMANCE INDICATORS |  | LEAD ORGANSIATION/TASK TEAM | PRIORITY PICTS
| NATIONAL/REGIONAL |  |  |  | REGIONAL | NATIONAL
Observation and forecasting systems to support timely and accurate marine weather and ocean services | National | 1. Have access to downscaled wave models, sea level and international met-ocean forecasts, data and products. | 2 PICS have downscaled wave forecasts: TV (KfW), FJ (WACOP) 2 more in development: KI (CREWS), RMI (PREP2) 1 PIC has Inundation forecast: FJ (CIFDP) 1 PIC in development: TV (CREWS) High resolution wave model in development: TO (CRSP-ADB) Long-term inundation projections: FJ, TV, VU (JICA) | replicate, upscale and further build upon the recent successes of operational models in Marshall Islands, Tuvalu and Fiji | By 2019 3 NMHSs have access to down-scaled wave models | By 2019 a met-ocean forecasts, data and products needs assessment has been conducted for all NMHSs | COASTAL MHEWS TT
| Regional | 1. Support the improvement of marine weather and ocean services through facilitating appropriate infrastructure, products and tools. | Establishment of Pacific Community Centre for Ocean Science (2017) Feasibility study conducted (2018) Strategy and Governance established (2019) | Identify science and service opportunities through PCCOS and the UN Decade of Ocean Science that align with the Pacific Islands Meteorological Strategy (PIMS 2017-2026) | Feasibility assessment of a regional ocean center akin to the Regional Climate Center 2021 |  | UN Decade TT
|  |  | Development of tidal predictions calendars for 4 new Pacific Locations (Neiafu, TO; Vaitupu, TV; Kirimati and Kanton, KI) (COSPPac) | Develop and test regional tide app with users (COSPPac) | Tide app tested and launched in 2020 |  | COSPPac
|  |  | Several GCF proposals in the pipeline to include downscaled wave, current, and circulation models for PICs | Coordinate the development of coastal inundation forecasting and early warning systems in the region to ensure compatability of services and best-practice methods tailored to reef-fronted island coastlines are employed |  |  | COASTAL MHEWS TT
| National | 2. Install/ have access to real-time marine and ocean observations – in-situ and remote sensing including for lagoon areas. | 1 wave buoy in FJ, 3-4 coming (CIFDP) 1 each wave buoy in Kiribati and Tuvalu by the end of 2019 (CREWS) Temporary wave buoys in Tonga (ADB) 2 new tide gauges (TV, TO- COSPPac) Installation of Vatia Tide Gauge in Fiji (JICA). Two real-time tide gauges deployed in Vava'u and Niuatopeutapeu (Tonga) | GCF projects in the pipeline which would include additional wave and environmental monitoring buoys | Through 2027 the PSLMP is maintained and operational | By 2019 a met-ocean real-time marine and ocean observations needs assessment has been conducted for all NMHSs | COASTAL MHEWS TT OA TT
| Regional | 3. Establish a monitoring program to Marine Climate Change and Ocean Acidification | Regional participation in PPOA, PI-TOA, GOA-ON initiatives | Define the roles PMC and NMHS wish to take with respect to monitoring, researching, and/or coordinating responses to ocean acidification under the PIMOS panel |  |  | OA TT
| National | 3. Contribute toward national efforts to monitor and coordinate work on Marine Climate Change and Ocean Acidification | Samoa Met is establishing a national body to coordinate OA MAPCO2 buoys being installed in Palau, FSM, Samoa (KIOST) OA monitoring kits provided to 11 Pacific scientists from 8 Islands (PI-TOA) | Establish baseline monitoring necessary to capture natural variability in ocean carbon chemistry and understand long-term trends Where possible, include ocean acidification in environmental monitoring buoys/platforms |  |  | OA TT
Establish ocean services | National | 1. Conduct stakeholder liaison to develop an ocean services plan. | Ocean stakeholder engagement workshops in 9 PICs since 2015 (6 more since PMC-4: TV, TO, NU, SA, VU, FJ) (COSPPac) Follow up workshops conducted in TV (Nov 2018) and TO (March 2019) | Continued ocean stakeholder engagements through COSPPac with remaining PICs (PNG, KI, FSM, PU, NR) and second level workshops (SI, TO, TV, VU, SA) | Stakeholder input on an ocean services plan conducted by 2021 | By 2023 develop a national ocean services plan | COSPPac
| Regional | 1. Support establishment of ocean services in NMHSs. | SPC hosted 5 NMHS attachments (CK, SI, TV, KI, VU) on Ocean Portal training and Outlook development Ocean Science to Service workshops in TV, TO, NU, SA, VU, FJ (COSPPac) | Link with PICS Panel where appropriate re: development of ocean services roadmap that links to GFCS Explore feasibility of hosting an Ocean-focused PICOF for fisheries/ coral reef monitoring sector | Develop a regional ocean services roadmap by 2021 |  | PIMOS, SPC, SPREP
| National | 2. Use tools currently available for servicing ocean stakeholders - i.e. Pacific Ocean Portal. | 6 PICs have developed Ocean Outlooks (KI, TV, TO, SA, VU, FJ) 2 PICs have Ocean Outlooks in Development (SI, RMI) | Continued support for outlook development (where appropriate), ocean stakeholder engagement and feedback | By 2021 audit available tools and assess stakeholder needs | by 2023 build capacity to use existing tools and develop new tools
Establish QMS for marine weather services and SOLAS obligations | National | 1. Develop and apply NMHS QMS procedures for marine met-ocean services. | No progress to date |  | Adapt and develop QMS procedures by 2023 based on regional guidance | Apply QMS by 2025 | SOLAS TT
| Regional | 1. Coordinate the development of NMHS QMS for marine met-ocean services using JCOMM guidance. | Limited progress to date | Key findings from IMSAS to inform regional development priorities and develop regional MMS roadmap Use a country test case as a guideline for other PICs Aviation QMS SOPs and processes can also serve as a guide. | Develop QMS based on JCOMM standards by 2021
| National | 2. Review all services and standard operating procedures that affect mariners and align with WMO and the Global Maritime Distress and Safety System (SOLAS). | 9 PIC IMO members have been audited under IMSAS (Palau and RMI remain) | NMHSs should participate in existing maritime committees and receive IMSAS results reports Share information from key IMSAS findings related to the delivery of Marine Meteorological Services with the PIMOS panel to support regional coordination | Review by 2021
| Regional | 2. Raise awareness of and improve understanding of obligations to provide marine safety information under SOLAS. | Inputs to PMC-4 and PMC-5 from SPC's Oceans and Maritime Program Advice provided to many NMHSs in advance of IMSAS audit Promotion of inclusion of NMHSs in regional ocean policies and processes (e.g. UN Ocean Decade) | Development partners coordinate with the PIMOS Panel a regional approach to implement Quality Management Systems and stakeholder engagement fora for the enhanced delivery of Marine Meteorological Services in accordance with international conventions, codes and guidelines and for the safety of all ocean users. | Establish a regional coordinator for MSI by 2021
Marine weather and ocean services stakeholder engagement | National | 1. Develop marine weather and ocean service level agreements with marine agencies i.e. to support early warnings, shipping, search and rescue, inter-island boat operators etc. (Marine Safety Information) | MOU developed between Met and Maritime sectors in Tonga Initial Ocean stakeholder engagement workshops in 9 PICs since 2015 (6 more since PMC-4: TV, TO, NU, SA, VU, FJ) (COSPPac) Follow up workshops conducted in TV (Nov 2018) and TO (March 2019) | Further development of service level agreements based upon consultation and relationship development | Agreements by 2023 |  | SOLAS TT
| Regional | 1. Coordinate a regional marine weather and ocean services program to support linking NMHS with partners and users of these services. | Initial Ocean stakeholder engagement workshops in 9 PICs since 2015 (6 more since PMC-4: TV, TO, NU, SA, VU, FJ) (COSPPac) Follow up workshops conducted in TV (Nov 2018) and TO (March 2019) | Establish an annual regional Maritime stakeholder forum to develop user relationships and share best practices | An annual Maritime/Met stakeholder forum is held before PMC-6
Develop a regional marine weather and ocean services program by 2019
| Regional | 2. Raise awareness of and improve understanding of obligations under UNCLOS and SOLAS agreements among NMHSs, governments and various stakeholders of the marine sectors | Inputs to PMC-4 and PMC-5 from SPC's Oceans and Maritime Program Promotion of inclusion of NMHSs in regional ocean policies and processes (e.g. UN Ocean Decade) |  | Develop a regional ocean services roadmap by 2021 | Develop communications materials and strategy on commitments under UNCLOS and SOLAS convention for stakeholders by 2019
WMO Competency and capacity development for marine weather and ocean services | National | 1. Improve capability of staff to undertake marine meteorology and oceanography programs, taking into account advice by WMO bodies such as JCOMM. | Oceanographers hired at NMHSs (SBx1, PNGx2) Online marine met module being developed by WMO in consultation with FJ, VU, TO, CK, and SB for roll out in late 2019, early 2020 |  | X staff per year trained through WMO and other programs | By 2021 develop a distance training platform for marine meteorology and oceanography | PIMOS, SPC, SPREP, USP, WMO
| Regional | 1. Coordinate regional capacity development in the fields of marine meteorology and oceanography. | NMHS Ocean attachments at SPC (KI, VU, TV, SB, CK) ITIC and PTWC tsunami science, warning, and SOP training (FJ, TO, PNG) | PCCOS to become a regional host for Ocean Teacher Global Academy IODE courses and BoM tide training
| National | 2. Provide staff training towards marine meteorology certification. | Participation in USP Ocean remote sensing course (SB) Participation in IODE Ocean Obs training (TO) |  | By 2020 develop competency standards | after 2021 X staff per year receiving competency certification
| Regional | 2. Assist Members to implement competency assessment for marine meteorology and co-ordinate support for on-going mentoring post certification. | Initial marine met products assessment conducted by SPC in countries that have received COSPPac Ocean Workshop
Marine meteorology and oceanographic research | National | Undertake or contribute to studies related to priority sectors | 1 PhD candidate (TO) 2 Masters theses (SO, FJ) focused on oceanography, modelling, TC inundation co-supervised by USP/SPC VU contributed toward white paper on ocean services published for OceanObs'19 9 NMHS science posters to be presented at OceanObs'19 in Hawaii (Sept 2019) thru COSPPac | Identify science and service opportunities through PCCOS and the UN Decade of Ocean Science that align with the Pacific Islands Meteorological Strategy (PIMS 2017-2026) Prioritise science and research led by Pacific Islands and/or conducted in close consultation with an aim toward strengthening local capacity and access to technology | Opportunities and priorities are mapped by the end of 2020 Support and contribute to the TPOS-2020 review and upgrade | Identify priority science and research needs by 2021 | PIMOS, SPC, SPREP, USP, WMO
| Regional | Coordinate and support Marine Meteorology and oceanographic research, including Marine Scientific Research and Technology Transfer under the provision of UNCLOS | SPC contributions to BBNJ negotiations under UNCLOS and UN Ocean Decade with explicit contributions on CD and TMT SPC published white paper on Pacific Island Capacity Building in Ocean Observations and Applications | BBNJ, PCCOS and UN Decade of Ocean Science for Sustainable Development (IOC-UNESCO) to prioritise Pacific capacity building and tech transfer | Identify opportunities for Technology Transfer under UNCLOS | Identify regional priority science and research needs
Note on E1: Molly G. Powers: To be further developed

## PKO-2 (PIMOS)
HIGH LEVEL ACTIONS | ACTIVITY | ACTION | KEY PERFORMANCE INDICATORS |  | LEAD ORGANSIATION/PANEL | PRIORITY PICTS | POTENTIAL PARTNERS | TIMEFRAME |  |  |  |  | NOTES
| NATIONAL/REGIONAL | [6 empty] | 2019 | 2021 | 2023 | 2025 | 2027
Observation and forecasting systems to support timely and accurate marine weather and ocean services | National | 1. Have access to downscaled wave models, sea level and international met-ocean forecasts, data and products. | By 2019 3 NMHSs have access to down-scaled wave models | By 2019 a met-ocean forecasts, data and products needs assessment has been conducted for all NMHSs | [8 empty] | Tuvalu has a downscaled wave forecast (KfW) that is being turned into an inundation forecast (CREWS). Fiji has a downscaled wave forecast (WACOP) and an inundation forecast (CIFDP). Kiribati downscaled wave forecast and inundation forecast are being developed thru CREWS (Tarawa). RMI downscaled wave forecast and inundation forecast are being developed (PREP II). High resolution wave model is being developed for Tonga (CRSP-ADB, NIWA).
| Regional | 1. Support the improvement of marine weather and ocean services through facilitating appropriate infrastructure, products and tools. | Feasibility assessment of a regional ocean center akin to the Regional Climate Center 2021 | [9 empty] | Establishment of Pacific Community Centre for Ocean Science
| National | 2. Install/ have access to real-time marine and ocean observations – in-situ and remote sensing including for lagoon areas. | Through 2027 the PSLMP is maintained and operational | By 2019 a met-ocean real-time marine and ocean observations needs assessment has been conducted for all NMHSs | [8 empty] | Installation of wave buoy in 1 site in Fiji, 1-2 more to come (CIFDP). 1 each wave buoy in Kiribati and Tuvalu by the end of 2019 (CREWS). WB project in Tonga with NIWA deployment of temporary wave buoys (x?). 2 new tide gauges (Tuvalu and Tonga). Installation of Vatia Tide Gauge in Fiji (JICA). Two real-time tide gauges deployed in Va'vau and Niuatopeutapeu (Tonga).
Establish ocean services | National | 1. Conduct stakeholder liaison to develop an ocean services plan. | Stakeholder input on an ocean services plan conducted by 2021 | By 2023 develop a national ocean services plan | [8 empty] | Kiribati, Tonga, Tuvalu, Samoa, Fiji, Vanuatu all producing Ocean Outlooks for these stakeholders
| Regional | 1. Support establishment of ocean services in NMHSs. | Develop a regional ocean services roadmap by 2021 | [9 empty] | 4 new tide predictions available (Neiafu, TO; Kiritimati, KI; Kanton, KI; Vaitupu, TV)
| National | 2. Use tools currently available for servicing ocean stakeholders - i.e. Pacific Ocean Portal. | By 2021 audit available tools and assess stakeholder needs | by 2023 build capacity to use existing tools and develop new tools
Establish QMS for marine weather services and SOLAS obligations | National | 1. Develop and apply NMHS QMS procedures for marine met-ocean services. | Adapt and develop QMS procedures by 2023 based on regional guidance | Apply QMS by 2025 | [8 empty] | 1. PIMOS Panel to develop Tsunami Competencies (Tonga) 2. Working group to discuss timings (Aust) 3. Cautious approach re: new services and sustainable funding (Aust) - manage expectations SPREP) 4. Ocean services vs NMS (Samoa) - could sit under various PKOs e.g. CC
| Regional | 1. Coordinate the development of NMHS QMS for marine met-ocean services using JCOMM guidance. | Develop QMS based on JCOMM standards by 2021
| National | 2. Review all services and standard operating procedures that affect mariners and align with WMO and the Global Maritime Distress and Safety System (SOLAS). | Review by 2021
| Regional | 2. Raise awareness of and improve understanding of obligations to provide marine safety information under SOLAS. | Establish a regional coordinator for MSI by 2021
Marine weather and ocean services stakeholder engagement | National | 1. Develop marine weather and ocean service level agreements with marine agencies i.e. to support early warnings, shipping, search and rescue, inter-island boat operators etc. (Marine Safety Information) | Agreements by 2023 | [9 empty] | Tuvalu has developed an obsevations log and is socialising this with local vessels to collect additional weather observations.
| Regional | 1. Coordinate a regional marine weather and ocean services program to support linking NMHS with partners and users of these services. | Develop a regional marine weather and ocean services program by 2019 | [9 empty] | COSPPac
| Regional | 2. Raise awareness of and improve understanding of obligations under UNCLOS and SOLAS agreements among NMHSs, governments and various stakeholders of the marine sectors | Develop a regional ocean services roadmap by 2021 | Develop communications materials and strategy on commitments under UNCLOS and SOLAS convention for stakeholders by 2019 | [8 empty] | COSPPac, PRNI Mock Audits
WMO Competency and capacity development for marine weather and ocean services | National | 1. Improve capability of staff to undertake marine meteorology and oceanography programs, taking into account advice by WMO bodies such as JCOMM. | X staff per year trained through WMO and other programs | By 2021 develop a distance training platform for marine meteorology and oceanography | [8 empty] | COSPPac, KfW, CIFDP
| Regional | 1. Coordinate regional capacity development in the fields of marine meteorology and oceanography. | [10 empty] | USP is offering an undergraduate course in physical oceanography. The USP post-graduate course in Climate Change includes training on the Pacific Ocean Portal. USP offered the Ocean remote sensing course, attended by 2 Pacific NMS staff. Two Pacific NMS staff have attended DBCP-3 (China) and one (Tonga) attended IODE Ocean Teacher Global Training on Ocean Observation course (China).
| National | 2. Provide staff training towards marine meteorology certification. | By 2019 develop competency standards | after 2021 X staff per year receiving competency certification
| Regional | 2. Assist Members to implement competency assessment for marine meteorology and co-ordinate support for on-going mentoring post certification.
Marine meteorology and oceanographic research | National | Undertake or contribute to studies related to priority sectors | Support and contribute to the TPOS-2020 review and upgrade | Identify priority science and research needs by 2021 | [8 empty] | Moleni Tu'uholoaki starting his PhD focused on Tropical Cyclone inundation in Tonga. Co-supervising Lency Muna and Yogesh Masters Theses on Physical Oceanography and Modelling. Development of journal paper on Vanuatu first-of- its-kind probabalistic cyclone inundation hazard assessment- TC Pam KfW funded (underway). Methodology developed will be further developed by Moleni.
| Regional | Coordinate and support Marine Meteorology and oceanographic research, including Marine Scientific Research and Technology Transfer under the provision of UNCLOS | Identify opportunities for Technology Transfer under UNCLOS | Identify regional priority science and research needs | [8 empty] | Ocean Obs,'19 UFORIC working group, paper in review, University of Cantabria partnership under PREP II,
HAZARD and RISK | Regional | collecting asset data in 14 countries and collecting hazard data and transforming hazard data into risk by looking at the impact of hazard on assets
| National | *Focus on Tuvalu, Fiji,